## Sheet1
Project Title | 01 Target Start Date | 01 Actual Start Date | 01 Target Completion Date | 01 Actual Completion Date | 01 Planned Revenue Date | 01 Actual Revenue Date | 01 Revenue | 01 Invoiced Revenue | 02 Target Start Date | 02 Actual Start Date | 02 Target Completion Date | 02 Actual Completion Date | 02 Planned Revenue Date | 02 Actual Revenue Date | 02 Revenue | 02 Invoiced Revenue | 03 Target Start Date | 03 Actual Start Date | 03 Target Completion Date | 03 Actual Completion Date | 03 Planned Revenue Date | 03 Actual Revenue Date | 03 Revenue | 03 Invoiced Revenue | 04 Target Start Date | 04 Actual Start Date | 04 Target Completion Date | 04 Actual Completion Date | 04 Planned Revenue Date | 04 Actual Revenue Date | 04 Revenue | 04 Invoiced Revenue | 05 Target Start Date | 05 Actual Start Date | 05 Target Completion Date | 05 Actual Completion Date | 05 Planned Revenue Date | 05 Actual Revenue Date | 05 Revenue | 05 Invoiced Revenue | 06 Target Start Date | 06 Actual Start Date | 06 Target Completion Date | 06 Actual Completion Date | 06 Planned Revenue Date | 06 Actual Revenue Date | 06 Revenue | 06 Invoiced Revenue | 07 Target Start Date | 07 Actual Start Date | 07 Target Completion Date | 07 Actual Completion Date | 07 Planned Revenue Date | 07 Actual Revenue Date | 07 Revenue | 07 Invoiced Revenue | 08 Target Start Date | 08 Actual Start Date | 08 Target Completion Date | 08 Actual Completion Date | 08 Planned Revenue Date | 08 Actual Revenue Date | 08 Revenue | 08 Invoiced Revenue | 09 Target Start Date | 09 Actual Start Date | 09 Target Completion Date | 09 Actual Completion Date | 09 Planned Revenue Date | 09 Actual Revenue Date | 09 Revenue | 09 Invoiced Revenue | 10 Target Start Date | 10 Actual Start Date | 10 Target Completion Date | 10 Actual Completion Date | 10 Planned Revenue Date | 10 Actual Revenue Date | 10 Revenue | 10 Invoiced Revenue
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996
BBVA Compass Bank - SO9870 License Update
General Mills - SO11778 - Avaya aWFO |  | 2014-04-01 04:00 |  | 2014-04-01 04:00 |  |  |  |  | 2014-04-01 04:00 |  | 2014-04-18 04:00 | 2014-04-08 04:00 | 2014-04-25 04:00 | 2014-04-11 04:00 | 21933.25 |  |  | 2014-04-08 04:00 |  | 2014-04-08 04:00 | [5 empty] | 2014-04-08 04:00 |  | 2014-04-08 04:00 | [5 empty] | 2014-04-14 04:00 | 2014-05-12 04:00 | 2014-05-12 04:00 |  |  |  |  | 2014-04-14 04:00 |  | 2014-04-25 04:00 | 2014-04-30 04:00 | 2014-04-30 04:00 | 2014-04-30 04:00 | 43866.5 |  | 2014-05-19 04:00 |  | 2014-06-13 04:00 | [5 empty] | 2014-06-16 04:00 |  | 2014-06-16 04:00 | [5 empty] | 2014-06-16 04:00 |  | 2014-06-16 04:00 | 2014-05-30 04:00 | 2014-06-16 04:00 | 2014-05-30 04:00 | 21933.25 |  | 2014-06-23 04:00 |  | 2014-06-23 04:00
Williams Sonoma - SO11768 - AVAYA WFO Implementation V10 to V12 |  | 2014-04-23 04:00 |  | 2014-04-23 04:00 | [6 empty] | 2014-05-22 01:09 | 2014-05-21 13:50 | 2014-06-04 04:00 | 2014-05-21 04:00 | 24171.75 | [9 empty] | 2014-05-02 04:00 | 2014-05-02 04:00 | 2014-05-02 04:00 | 2014-05-09 04:00 |  |  |  |  | 2014-05-12 04:00 | 2014-06-02 04:00 | 2014-05-16 04:00 | 2014-06-02 04:00 |  |  |  |  | 2014-05-19 04:00 |  | 2014-06-02 04:00 | 2014-06-12 04:00 | 2014-06-30 04:00 | 2014-06-12 04:00 | 48343.5 |  | 2014-06-09 04:00 |  | 2014-06-27 04:00 | [5 empty] | 2014-06-30 04:00 |  | 2014-07-11 04:00 | [7 empty] | 2014-07-14 04:00 |  | 2014-08-04 04:00 |  | 24171.75
Progrexion - SO11813 - Dialer Integration |  | 2014-05-14 04:00 |  | 2014-05-14 04:00 | [36 empty] | 2014-05-14 04:00 | 2014-05-14 04:00 | 2014-06-30 04:00 |  | 2014-06-16 04:00 |  | 3800
Verint PMO Revenue - July 2014 | [10 empty] | 2014-05-23 14:31 |  |  |  | 0 | [27 empty] | 2014-06-23 14:31 |  |  |  | 0 | 0 | [18 empty] | 2014-07-23 14:31 |  |  |  | 0
Verint MAC Revenue - July 2014 | [10 empty] | 2014-05-23 14:34 |  |  |  | 0 | 0 | [26 empty] | 2014-06-23 14:34 |  |  |  | 0 | 0 | [18 empty] | 2014-07-23 14:34 |  |  |  | 0 | 0
Verint PMO Revenue - August 2014 | [10 empty] | 2014-05-23 14:36 |  |  |  | 0 | 0 | [24 empty] | 2014-08-01 04:00 |  | 2014-08-29 04:00 |  |  |  | 0 | 0 | [18 empty] | 2014-07-23 14:36 |  |  |  | 0 | 0
Verint MAC Revenue - August 2014 | [10 empty] | 2014-05-23 14:42 |  |  |  | 0 | 0 | [24 empty] | 2014-08-01 04:00 |  | 2014-08-29 04:00 |  |  |  | 0 | 0 | [18 empty] | 2014-07-23 14:42 |  |  |  | 0 | 0
Verint PMO Revenue - September 2014 | [10 empty] | 2014-05-23 14:45 |  |  |  | 0 | 0 | [24 empty] | 2014-09-01 04:00 |  | 2014-09-30 04:00 |  |  |  | 0 | 0 | [18 empty] | 2014-07-23 14:45 |  |  |  | 0 | 0
Verint MAC Revenue - September 2014 | [10 empty] | 2014-05-23 14:47 |  |  |  | 0 | [25 empty] | 2014-09-01 04:00 |  | 2014-09-30 04:00 |  |  |  | 0 | [19 empty] | 2014-07-23 14:47 |  |  |  | 0
Ministry of Health - Canada - SO11805 - RFP for 230 seats of oWFM + TOM + SB | 2014-05-09 04:00 |  | 2014-05-09 04:00 | 2014-05-09 04:00 |  |  |  |  | 2014-05-12 04:00 |  | 2014-06-06 04:00 | [5 empty] | 2014-05-23 04:00 |  | 2014-05-23 04:00 | [5 empty] | 2014-05-19 04:00 |  | 2014-05-19 04:00 | [5 empty] | 2014-05-26 04:00 |  | 2014-06-13 04:00 | [7 empty] | 2014-06-24 15:46 |  | 2014-07-08 04:00 |  | 17945 |  | 2014-06-23 04:00 |  | 2014-07-07 04:00 | [5 empty] | 2014-07-11 04:00 |  | 2014-07-11 04:00 | [7 empty] | 2014-07-24 15:46 |  | 2014-08-07 04:00 |  | 17945
Diligenta - SO3508 - SKY AWFM solution - 606 agents of AWFM (3 years) |  |  |  | 2014-06-10 14:29 | [6 empty] | 2014-05-24 18:40 |  | 2014-06-07 04:00 |  | 10400 | [27 empty] | 2014-06-24 18:40 |  | 2014-07-08 04:00 |  | 20800 | [19 empty] | 2014-07-24 18:40 |  | 2014-08-07 04:00 |  | 10400 | 0
Commerce Bank - SO11798 - WFM Adapter Fix |  | 2014-04-25 04:00 |  | 2014-04-28 04:00 | [36 empty] | 2014-04-29 04:00 | 2014-04-29 04:00 | 2014-04-29 04:00 | 2014-04-29 04:00 | 2014-04-30 04:00 | 2014-04-30 04:00 | 800 | 0 | [24 empty] | 2014-05-05 04:00 | 2014-04-29 04:00 | 2014-05-05 04:00 | 2014-04-30 04:00
Flagstar -SOxxxx - PS support - 4 days | [72 empty] | 2014-05-05 04:00 |  | 2014-05-30 04:00 |  | 2014-06-13 04:00 |  | 8800
Etrali Trading Solutions - SO11801 - Onsite Installation | [10 empty] | 2014-05-25 17:41 |  | 2014-06-08 04:00 |  | 2350 | [27 empty] | 2014-06-25 17:41 |  | 2014-07-09 04:00 |  | 2350
Johnson Controls Inc. - SO11809 Avaya QM Training | [10 empty] | 2014-05-29 14:35 |  | 2014-06-12 04:00 |  | 0 | 0 | [25 empty] | 2014-04-14 04:00 | 2014-06-29 14:35 | 2014-04-18 04:00 | 2014-07-13 04:00 | 2014-04-29 04:00 | 5400 | 0 |  |  |  | 2014-04-29 14:36 | [14 empty] | 2014-07-29 14:35 |  | 2014-08-12 04:00 |  | 0 | 0 |  |  |  | 2014-04-29 17:37
Wageworks - SO11827 - oWFM + TOM + SB | 2014-05-30 04:00 | 2014-05-30 04:00 | 2014-06-02 04:00 | 2014-06-03 04:00 |  |  |  |  | 2014-06-03 04:00 | 2014-06-03 04:00 | 2014-06-09 04:00 | 2014-06-09 04:00 | 2014-06-30 04:00 | 2014-06-09 04:00 | 11000 |  | 2014-05-30 04:00 |  | 2014-06-06 04:00 | 2014-06-06 04:00 |  |  |  |  | 2014-06-09 04:00 | 2014-06-09 04:00 | 2014-06-10 04:00 | 2014-06-16 04:00 |  |  |  |  | 2014-06-17 04:00 |  | 2014-06-18 04:00 | [5 empty] | 2014-06-19 04:00 |  | 2014-06-25 04:00 |  | 2014-07-01 04:00 |  | 22000 |  | 2014-07-14 04:00 |  | 2014-07-25 04:00 | [15 empty] | 2014-07-28 04:00 |  | 2014-07-31 04:00 |  | 11000 |  |  |  | 2014-07-31 04:00
Mastercard - SO11819 - oQM Implementation + PCI | [10 empty] | 2014-06-30 04:00 |  | 2014-07-04 04:00 |  | 16459.5 | [27 empty] | 2014-06-30 21:04 |  | 2014-07-14 04:00 |  | 32919 | [19 empty] | 2014-08-15 04:00 |  | 2014-08-29 04:00 |  | 16459.5
Fabricut - SO11823 - QM expansion - 10 Licenses - Remote Install | [42 empty] | 2014-07-05 18:46 | 2014-06-06 13:08 | 2014-07-19 04:00 | 2014-06-06 04:00 | 750 | [26 empty] | 2014-06-06 04:00 |  | 2014-06-06 04:00
Centocor - SO11830 - Malvern, PA - PCI-D16 DIGI - Onsite Installation |  | 2014-05-08 04:00 |  | 2014-05-08 04:00 | [36 empty] | 2014-05-13 04:00 |  | 2014-05-14 04:00 | 2014-05-30 04:00 | 2014-05-30 04:00 | 2014-05-30 04:00 | 4000 | [25 empty] | 2014-05-19 04:00 |  | 2014-05-23 04:00
IHC Dixie - SO11841 - Avaya QM Services | [9 empty] | 2014-05-01 04:00 | 2014-05-23 04:00 | 2014-05-30 14:00 | 2014-05-30 04:00 | 2014-05-30 04:00 | 4500 | [35 empty] | 2014-06-06 04:00 |  | 2014-06-30 04:00 |  | 4500 | [17 empty] | 2014-06-16 04:00 |  | 2014-06-30 04:00
BMW - SO10979 - Onsite Installation Services
BMW - SO10982 - Onsite Installation Services
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats
Nissan - SO11007 - Dialogic Expansion Chassis
MolDev - IGR (France) - SO10777 - 2 Days of Installation
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation
HSBC - PM - March 2014
HSBC - PM - January 2014
HSBC - PM - February 2014
Windstream - Bausch and Lomb - SO11042
BMW - SO11055 - GM installation on 9 servers
Verint PMO Revenue - January 2014
Verint RRI Revenue - January 2014
Verint MAC Revenue - January 2014
Verint PMO Revenue - February 2014
Verint MAC Revenue - February 2014
Verint PMO Revenue - March 2014
APAC - SO9872 - Dialogic Install
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J
Medco - SO1208699 02/01/13 Remote - Fred J
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J
Medtronic - SO 1197187 01/25/13 Remote - Fred J
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T
Unused Resource - SO99999 01/07/13 Fred J
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T
Unused - SO99999 01/14/13 - 01/16/13 Fred J
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T
Intact - SO 1213063 01/02/13 Remote - Robb D
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J
McKesson - SO1202191 01/02/13 Remote - Aziz H
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H
APAC - SO9888 Remote Services
Mizuho Corporate Bank - SO9897 Remote License Upgrade
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training
Apple Inc - Onsite v11 Server Installation - SO10129
NACR - CoBank - SO10144 - Server Rebuild and eQM Training
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Training
Verint - Amway Services - SO10138 - John R
NACR - CoBank - SO10165 - After Hours Support
Verint - California Casualty - SO10162 Onsite Services
Molecular Devices - SO10125- Germany - Research 10
NACR - CoBank - SO10177 - Remote License Install
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM
Verint - WellPoint - SO10206 - HD Repair - Aziz H
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats
Molecular Devices - SO10170 - MedImmune HCS Solution
Progressive Casualty - SO10291 - PCIE 48 Remote Install
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption
Charter Communications - SO10307 Hard Drive Solution Services
Johnson & Johnson - SO10313 On Site Card Install
ACS Technologies - SO10315 - Dell Server Remote Services
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services
Alticor, Inc. Amway - SO10370 - Op QM v11 Install
CDW - Comerica SO9679 License Update
Siemens - Peoples Natural Gas SO10359 v11 WFO
Coventry Management Services - SO10373 - PCIE Remote Install
Verint - AAA NC SO10402 Card Issues - John R
Siemens - Medstar Health - SO10404 License Addition
CDW - Comerica - SO10300 Training
City of Chicago - SO11678 - SSL Enablement
Avista - SO11661 - Cutover Support
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training
Google - SO11769 - Lab Implementation
SCANA - SO11255 - PCIe 120/96 Digi Remote Install
Bluegreen - SO11254 - GM Installation
Memphis Light, Gas and Water - SO11247
AtlantiCare - SO11277 - Onsite Installation
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install
Amway - SO11094 - GM Installation
Medstar - SO11299 - 12 Additional Licenses
Level One - SO9944 QM Training - Verint Services
Medical Mutual - SO9946 Remote Config
MolDev - SO9595 - Russia HCS Quest 64
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers)
Nissan North America - SO9975 Irving TX Onsite
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install
Google - SO11457
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation
Henry Ford Health System - SO 11422 Remote Dialogic
Questar - SO11489 - DPA
Weber Stephen Products - SO11468 - oWFM
Verizon - SO11477 - oRec v7.8 + Import Manager
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM
Chesapeake Bank -SO11523 - oREC 12 Seats
CMS Medicare - SO11536 - Analytics Part 1: Speech
Charter - SO11502 - F5 Implementation
Citizens Bank - SO11524 - Remote training for v9.3 Express
Express Scripts -SO11748 - Services - Onsite Weekend - Tampa
HSBC - PM - July 2014
Nissan - SO11528 - Remote Services
CMS Medicare - SO11536 - Analytics Part 2: DPA
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion
Verint PMO Revenue - June 2014
Verint MAC Revenue - June 2014
Pleasant Holidays - SO11617 - ODBC Drivers
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats
NMAC - SO11637 - Remote Services
Iron Mountain - SO11645 - WFO Onsite Training
Nissan North America - SO11605 - Change Order
Wide Open West SO11652 - Avaya QM Services
Texas Guarantee - SO11646 - Avaya oQM services
MedImpact - SO11659 - Additional Recorder and PCI
Charter - GM as part of Platinum Support
The Jay Group - SO9980 - Troubleshooting CT Connect
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite
Progressive Casualty Insurance - SO10009 Dialogic Install Remote
CDW - AFNI - SO9988 Server Builds (Bobby D)
Siemens - Academy Sports - SO9893 - Remote License Install
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade
Express Scripts - SO10047 Ft. Worth - HW Move
Express Scripts - SO10048 Franklin Lakes - HW Move
APAC - SO10050 PCI Exp D480 Onsite Install
Nissan North America - SO10063 analog hardware - Atlanta
Hydro One Networks - SO10066 - D480 Remote After Hours Install
Healthgrades - SO11115 - Addition of 20 Licenses
HEB Grocery - SO11127 - oQM
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours
Wellpoint - SO11131 - D480 Replacement
Verint MAC Revenue - March 2014
Verint PMO Revenue - April 2014
Verint MAC Revenue - April 2014
PCNA - SO11153 - Verint v11.1 oRec/Compliance
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3
CDW - Comerica - SO7206 v7.8 Op QM
Region of York - SO11390 - Addtional Licenses
HEB Grocery - SO11389 - Onsite Support
Toyota - SO11393 - Training Credits
Capital One - SO11405 - MDC CoreroLoadBalancer
Medstar - SO11442 - oQM UMH GCOA - 35 seats
Bristol Meyers Squibb - SO11435 - oQM Install Services
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN
Sunturn - NuSkin SO10547 - Server Move - Provo
SCANA - SO10457 - Aiken - Remote Card Install
Healthgrades - SO10554 - WFM + TOM 60 Seats
State of Oregon - SO10565 - DP6409 Onsite Install
AFNI - SO10571 - GM Install and Config
CDW - AFNI - SO10572 - Install of 6 Recorders
Intuitive - Pizza Hut- SO10506- SaaS oWFM
Stevens Communications - Kohls - SO10601 - Radware
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer
CDW - CBeyond - SO10615 - oWFM
MolDev - Methodist Hospital - SO10614 - Quest
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration)
MolDev - PepsiCo (California) - SO10561 - Quest
NACR - Pleasant Holidays - SO10633 - Avaya WFM
Telus Comm - Access - SO10632 - WFM Training
MolDev - Bayer (France) - SO10655 - Research 10
BBVA - SO10677 - Health Check
Exelon - GM Install (Platinum Support Upgrade)
BBVA - Intl Weatlh Mgmt - SO10737
Charter - SO10692 - Recorders at Multiple Sites
NACR - Texas Tech - SO10698 - Encryption
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts
ACS - Xerox - SO10700 Health Check for Support Renewal
Verint PMO Revenue - August 2013
Verint PMO Revenue - September 2013
Verint PMO Revenue - October 2013
Verint RRI Revenue - August 2013
Verint MAC Revenue - August 2013
Verint PMO Revenue - November 2013
Verint PMO Revenue - December 2013
Verint RRI Revenue - September 2013
Verint RRI Revenue - November 2013
Verint RRI Revenue - October 2013
Verint RRI Revenue - December 2013
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration
Verint MAC Revenue - September 2013
Verint MAC Revenue - October 2013
Verint MAC Revenue - November 2013
Verint MAC Revenue - December 2013
ADVANtel - Consumer Cellular - SO10736
Siemens - Medstar - SO10746
Region of York - SO10747 - oWFM 30 Seats
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install
Innovation Group - SO10754 - oWFO
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy
Medstar - SO10779 - oQM + Lesson Mgmt
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses
ACCC Insurance Co - SO10741 - oWFM
Pittsburgh Glass Works - SOxxxx - DP6409
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats
Merrill Assoc - HireRight - SO10808 - aWFM + LM
NACR - Intrust Bank - SO10809 - Express Troubleshooting
Johnson & Johnson - SO10813 - Voice Card Install
Nissan - SO10758 - Remote Services
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET
Test Company - SOxxxxx - WFO/400 seats/Services portion | [10 empty] | 2014-06-15 17:12 |  | 2014-06-29 17:12 |  | 2.5 | [27 empty] | 2014-07-15 17:12 |  | 2014-06-29 17:12 |  | 5 | [19 empty] | 2014-08-15 17:12 |  | 2014-08-29 17:12 |  | 2.5
Southern Farm Bureau - SO11869 - Avaya oWFO and oQM + SSO - 144 Seats and 50 seats | [10 empty] | 2014-06-20 21:41 |  | 2014-06-30 04:00 |  | 16112.5 | [27 empty] | 2014-09-30 04:00 |  | 2014-09-30 04:00 |  | 32225 | [19 empty] | 2014-10-31 04:00 |  | 2014-10-31 04:00 |  | 16112.5 |  | 2014-10-31 04:00 |  | 2014-10-31 04:00
V-RBS Ipswich-Power Down-061213 | [10 empty] | 2014-06-21 14:04 |  | 2014-07-05 14:04 |  | 501.25 | [27 empty] | 2014-07-21 14:04 |  | 2014-08-04 14:04 |  | 1002.5 | [19 empty] | 2014-08-21 14:04 |  | 2014-09-04 14:04 |  | 501.25
Vodafone DC loadbalancers | [10 empty] | 2014-06-23 15:53 |  | 2014-07-07 15:53 |  | 2050 | [27 empty] | 2014-07-23 15:53 |  | 2014-08-06 15:53 |  | 4100 | [19 empty] | 2014-08-23 15:53 |  | 2014-09-06 15:53 |  | 2050
Veterans Administration/Avaya QM Training | [10 empty] | 2014-06-23 16:10 | 2014-05-27 14:05 | 2014-07-07 16:10 |  | 0 | [26 empty] | 2014-04-29 04:00 | 2014-05-30 04:00 | 2014-04-30 04:00 | 2014-05-30 04:00 | 2014-05-27 04:00 | 2400 | [28 empty] | 2014-05-27 04:00
BT America's - SO11890 - Audiocodes Boards + remote install | [42 empty] | 2014-07-23 19:35 |  | 2014-07-31 04:00 |  | 500
Horizon BCBS- SO11885 - Strategic planner training - 2 days | [50 empty] | 2014-06-27 04:00 |  | 2014-07-11 04:00 |  | 4400
Southern Farm Bureau - SO11870 - Avaya oWFO - Louisiana Site | [10 empty] | 2014-06-20 04:00 |  | 2014-06-30 04:00 |  | 3450 | [27 empty] | 2014-07-25 04:00 |  | 2014-07-31 04:00 |  | 6900 | [19 empty] | 2014-08-27 16:16 |  | 2014-09-10 16:16 |  | 3450
HSBC - PM - October 2014 | [72 empty] | 2014-10-01 04:00 |  | 2014-10-30 04:00 |  | 2014-10-31 04:00 |  | 17000
Champion Energy ¦ SKY oWFM ¦ 49 seats | [10 empty] | 2014-06-29 22:08 |  | 2014-07-13 22:08 |  | 6695.75 | [27 empty] | 2014-07-29 22:08 |  | 2014-08-12 22:08 |  | 13391.5 | [19 empty] | 2014-08-29 22:08 |  | 2014-09-12 22:08 |  | 6695.75
Electrolux - Avaya SSO/LDAP Implementation | 2014-06-09 04:00 | 2014-06-09 04:00 | 2014-06-09 04:00 | 2014-06-09 04:00 |  |  |  |  | 2014-06-09 04:00 |  | 2014-06-20 04:00 | 2014-06-13 04:00 | 2014-07-19 19:34 | 2014-06-13 04:00 | 7566 | [25 empty] | 2014-06-16 04:00 | 2014-06-16 04:00 | 2014-06-30 04:00 |  | 2014-07-10 04:00 |  | 7566
Lahey Clinic - SOxxxxx - Avaya WFM |  |  |  | 2014-06-17 14:37 |  |  |  |  | 2014-06-10 04:00 |  | 2014-07-03 04:00 |  | 2014-07-19 19:55 |  | 12600 | [25 empty] | 2014-07-07 04:00 |  | 2014-07-18 04:00 |  |  |  | 0 |  | 2014-07-14 04:00 | [17 empty] | 2014-09-05 19:55 |  | 2014-09-19 19:55 |  | 12600
Laurentienne Bank - SOxxxxx - Avaya oWFO | [10 empty] | 2014-07-05 20:03 |  | 2014-07-19 20:03 |  | 25306.5 | [27 empty] | 2014-08-05 20:03 |  | 2014-08-19 20:03 |  | 0 | [19 empty] | 2014-09-05 20:03 |  | 2014-09-19 20:03 |  | 25306.5
QT10758 Fujitsu America, Inc Dialogic Cards | [10 empty] | 2014-07-05 20:03 |  | 2014-07-19 20:03 |  | 125 | [27 empty] | 2014-08-05 20:03 |  | 2014-08-19 20:03 |  | 250 | [19 empty] | 2014-09-05 20:03 |  | 2014-09-19 20:03 |  | 125
VA DMV - SOxxxxx - Avaya aWFO | [10 empty] | 2014-07-05 20:15 |  | 2014-07-19 20:15 |  | 44950 | [27 empty] | 2014-08-05 20:15 | [23 empty] | 2014-09-05 20:15 |  | 2014-09-19 20:15 |  | 44950
HSBC - PM - November 2014 | [72 empty] | 2014-11-01 04:00 |  | 2014-11-30 05:00 |  | 2014-11-30 05:00 |  | 16000
Professional services to reconfigure ports | [10 empty] | 2014-07-10 11:53 |  | 2014-07-24 11:53 |  | 187.5 | [27 empty] | 2014-08-10 11:53 |  | 2014-08-24 11:53 |  | 375 | [19 empty] | 2014-09-10 11:53 |  | 2014-09-24 11:53 |  | 187.5
MGM - SO11950 - QM Training | [48 empty] | 2014-06-18 04:00 |  | 2014-06-20 04:00 |  | 2014-06-27 04:00 |  | 3000
Commerce Bank - SO11968 - Remote WFM Consulting | [58 empty] | 2014-07-31 04:00 |  | 2014-08-14 04:00 |  | 1600
Reed Elsevier - Replace NGX2400 & PS - 130614 | [10 empty] | 2014-07-17 08:57 |  | 2014-07-31 08:57 |  | 210 | [27 empty] | 2014-08-17 08:57 |  | 2014-08-31 08:57 |  | 420 | [19 empty] | 2014-09-17 08:57 |  | 2014-10-01 08:57 |  | 210
QT11407 HCS-Quest64 | [10 empty] | 2014-07-17 12:38 |  | 2014-07-31 12:38 |  | 823.75 | [27 empty] | 2014-08-17 12:38 |  | 2014-08-31 12:38 |  | 1647.5 | [19 empty] | 2014-09-17 12:38 |  | 2014-10-01 12:38 |  | 823.75
QT11409 HCS-Research10 Germany Installation | [10 empty] | 2014-07-17 15:22 |  | 2014-07-31 15:22 |  | 793.75 | [27 empty] | 2014-08-17 15:22 |  | 2014-08-31 15:22 |  | 1587.5 | [19 empty] | 2014-09-17 15:22 |  | 2014-10-01 15:22 |  | 793.75
QT10414 Johnson & Johnson Dialogic VTG replacement | [10 empty] | 2014-07-17 16:35 |  | 2014-07-31 16:35 |  | 1000 | [27 empty] | 2014-08-17 16:35 |  | 2014-08-31 16:35 |  | 2000 | [19 empty] | 2014-09-17 16:35 |  | 2014-10-01 16:35 |  | 1000
Commonwealth of Kentucky - Avaya QM Training SO11700
Region of York - SO11390 TOM Addition
Healthgrades - SO11704 - License expansion qty 10 v11.1
Charter - SO11720 - Voice Screen Recording Servers for Billings MT - Onsite Normal Hours
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation
Wells Fargo - SO11619 - Remote Training
Plymouth Rock - SO11737 - WFM Training
Digital Credit Union - SO11740 - Avaya WFO R10 Training
HSBC - PM - August 2014
HSBC - PM - September 2014
CalPERS - SO11770 - QM v11.1 - 146 Seats | [10 empty] | 2014-05-16 16:33 | 2014-05-30 23:14 | 2014-05-30 04:00 | 2014-05-30 04:00 | 15250 | [9 empty] | 2014-05-12 04:00 | 2014-05-15 04:00 | 2014-05-12 04:00 | 2014-05-23 04:00 |  |  |  |  | 2014-05-19 04:00 |  | 2014-05-23 04:00 | 2014-05-27 04:00 |  |  |  |  | 2014-05-26 04:00 |  | 2014-06-06 04:00 |  | 2014-06-30 04:00 |  | 30500 |  | 2014-07-07 04:00 |  | 2014-07-11 04:00 | [5 empty] | 2014-07-14 04:00 |  | 2014-07-18 04:00 | [5 empty] | 2014-07-16 04:00 |  | 2014-07-16 16:33 |  | 2014-07-31 04:00 |  | 15250 |  | 2014-07-16 04:00 |  | 2014-07-16 04:00
Mitsubishi Motors - SO11760 - Complete SAT |  |  |  | 2014-04-28 04:00 | [38 empty] | 2014-05-16 04:00 | 2014-04-29 04:00 | 2014-05-23 04:00 | 2014-04-29 04:00 | 1600
Brady Group - SO11327 - Remote installation - 5 seat license
Northwest Natural Gas - SO11306 - LDAP Integration
Apple - SO11312 - Onsite Services
USG - SO11375 - SKY oWFO - 130 Seats
HireRight - SO11385 - SSO Implementation
Verint PMO Revenue - May 2014
Verint MAC Revenue - May 2014
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion
Comerica - SO11339 - JTAPI Services - After Hours
Comerica - SO11350 - Change order for Campaign Changes
Credit Union One - SO11363 - oWFM
HSBC - PM - June 2014
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper
Vanguard SO11382 - PS custom data
MedImpact - SO11345 - License Adds
Toyota Canada, Inc. - SO10414 v11 Project
Molecular Devices - SO10201 - Germany - Quest System
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs
Siemens - Medstar Health - SO10443 - Remote install of new licenses
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition
CDW - AFNI - SO10447 - License Moves
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch
Molecular Devices - SO10431 - Research 10 California
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET
HSBC - PM - April 2014
CMS Medicare Phase II - Cluster 2
HSBC - PM - May 2014
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only
VWR - SO11215 - 350 seats of OWFM SKY
CMS Medicare Phase II - Cluster 3
CMS Medicare Phase II - Cluster 4
CMS Medicare Phase II - Cluster 5
CMS Medicare Phase II - Cluster 1
BBVA - SO11207 - Remote License Adds
Vanguard - SO11238 - Pro Svcs Mapping Project
Commonwealth of Mass - SO11219 - Avaya v12 oWFO
Starwood Hotels and Resorts - SO11230 - D480 Remote Install
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training)
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training
Bluegreen - SO11253 - Avaya v12 aWFO
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO
BBVA - SO10837 - Information Security-BROCK 12 Seats
BBVA - SO10836 - Information Security-BROCK 19 Seats
CDW - Laureate - SO10850 - AIM Configuration
Trulia - SO10853 - SKY aWFM - 60 Seats
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats
Toyota Canada - SO10877 - Services to Install v11 AIM
Carousel - Contra Costa County - SO10870 - Change order to existing project
BMW - SO10862 - GM Installation and Configuration
Golfsmith - SO10863 - SKY aWFM - 35 Seats
BBVA - SO10834 - Information Security - BROCK 14 Seats
BBVA -SO10893 - Services_HUB Recovery Project
HSBC PM - August 2013
HSBC - PM - September 2013
HSBC - PM - October 2013
HSBC - PM - November 2013
HSBC - PM - December 2013
HSBC - Admin - September 2013
HSBC - Admin - August 2013
Flagstar - SO10909 - Health Check and SSL services
HSBC - Admin - October 2013
HSBC - Admin - November 2013
HSBC - Admin - December 2013
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication
Laureate/Adviceline
NGS
MolDev - SO10939 - Research 10 - Europe
Xerox - SO10936 - Wellness Check
Arrow - Shared Technologies - Summit Medical - SO8768 - License Upgrade
Fairmont Hotels - SO8751 - Remote Services
State of Texas - SO8803 - v7.8 Server Move
CDW - Federal Mogul (Training without Services) SO8783
HSBC - SO8823 June PM Resource
HSBC - SO8825 June Admin Support Resource
HSBC - SO8824
Verizon - Mohegan Sun - SO8826 Remote Services
University of Maryland - SO8821 Remote Expansion Chassis Addition
Neiman Marcus - SO8805 Remote NMS Board Config
HSBC - SO8811 Brandon Elmhurst Onsite Services
Vangent - SO8828 Remote Configuration CT Connect Dongle
Unused Resource - SO99999 - 06/25/12 Fred Jurs
Royal Carribean Bank - SO67446 06/26/12 - 06/29/12 Remote Fred J
CSC Holdings - 06/25/12 - 06/29/12 Remote Chris M
Select Quote - SO1187963 06/25/12 - 06/29/12 Bobby D
New York University - SO1161838 06/26/12 - 06/29/12 Remote - Michael T
Unused Resource - SO99999 06/18/12 -6/22/12 Fred Jurs
Discover Financial Services - SO1172115 06/18/12 - 06/22/12 Remote Chris M
Select Quote - SO1187963 06/18/12 - 06/22/12 Bobby D
Unused Resource - SO99999 06/11/12 - 06/15/12 Fred J
City of Charlotte - SO1190416 06/13/12 Remote Fred J
Sprint Spectrum - SO1190416 06/11/12 - 06/15/12 Chris M
T. D. Bank NA - SO1187532 06/11/12 - 06/15/12 Bobby D
Discover Financial Services - SO1172115 06/12/12 - 06/15/12 Remote - Michael T
CDW - State Auto - SO8846 Training Credits (No Services)
Combined Insurance - SO1173421 07/02/12 - 07/06/12 (4 days) Remote - Travis C
CSC Holdings- SO1181602 07/02/12 - 07/06/12 Remote (4 days) Michael T
Sitel - SO1189087 07/02/12 Remote - Bobby D
Ameren - SO1191669 07/05/12 Remote - Bobby D
Select Quote - SO1187963 07/06/12 Remote - Bobby D
Mol Dev - Los Angeles BioMedical Research Institute - 1 Day - Fred J
New York Life - Tampa SO7506 - Onsite Hardware
F5 Networks - SO1195134 07/09/12 - 07/13/12 Remote - Fred J
First Data Corp - SO1174200 07/09/12 - 07/13/12 Remote - Chris M
Purolater Courier - SO1190084 07/09/12 - 07/13/12 Remote - Michael T
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites**
CDW - Federal Mogul - SO8940 Planning & Design
Network Solutions - SO8906 - Support T & M
CDW - Brady Electromark - SO8912 - 8 seat update
Presidio - Lab Corp - SO8874 Remote Support
Siemens - Medstar - SO8894 - Op QM
Pepsico - Fargo SO8958 - Dialogic Install
Josten's - SO1191672 07/23/12 - 07/26/12 Remote - Fred J
F5 Networks - SO1195134 07/27/12 - Remote - Fred J
Purolater Courier - SO1190084 07/23/12 - 07/27/12 Remote - Michael T
Purolater Courier - SO1190084 07/16/12 - 07/20/12 Remote - Michael T
F5 Networks - SO1195134 07/19/12 - 07/20/12 - Remote - Fred J
Progrexion Marketing - SO1189292 07/23/12 - 07/27/12 SLC - Chris M
Progrexion Marketing - SO1189292 07/16/12 - 07/20/12 SLC - Chris M
Unused Resource - SO99999 - 07/16/12 - 07/17/12 Fred Jurs
Genentech - SO1191159 07/18/12 .5 Days - Remote - Fred J
Emblem Health - SO1186830 - 07/18/12 .5 days - Remote - Fred J
HSBC - SO8975 - Rack/Stack and setup for IP Recorders at Vernon Hills, Volo & Jersey City
HSBC - SO8973 Offshore Recorder services
Bluewater - Webster Bank - SO8981 v11 w/AET
HSBC - SO8988 07/01/12 - 07/31/12 Remote Admin - July
HSBC - SO8989 07/01/12 - 07/31/12 PM Services - July
HSBC - SO8992 Vernon Hills and Jersey City
HSBC - SO8991 Onshore/Offshore Screen Recorder Services
Flagstar - SO8970 PCI Exp Chassis
JEA - SO8978 NMS Config
Siemens - Halifax Healthcare - SO9006 License Update
HSBC - SO8623 Verona Data Split
Cross Country - SO8447 Onsite Server Build
CDW - TMG - SO9016 v11 Install
Siemens - Watson Clinic - SO9014 eQM License Update
Agilent - SO9022 NGX Card Install (Colorado Springs)
Knology - SO9038 Trunk Tap Remote
APAC - SO9058 Remote Dialogic Config
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move
Affiliated Computer Services - SO9412 Chassis Move (Aziz H)
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J
Unused Resource - SO99999 10/18/12 Fred J
Ally Financial - SO65577 10/19/12 Remote - Fred J
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W
Ally Financial - SO65577 10/22/12 Remote - Fred J
Auto Protection - SO1205178 10/25/12 Remote - Fred J
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J
Unused Resource - SO99999 10/26/12 Fred J
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D
HSBC - SO9454 - PM October - Matt Hogan
HSBC - SO9455 October Admin
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J
Baptist Hospital - SO9500 Remote Config
BBVA Compass Bank - SO9502 Global Monitor Trial
BBVA Compass Bank - SO9515 SIP Trunk Change
CDW - Brady Corp - SO9518 Remote License Addition
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss)
Greater Toronto Airport Authority - SO9545 Card Install
Pearson Education - SO9553 Voice Card Consolidation
HSBC - SO9601 - November PM - Matt Hogan
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin
Medtronic - SO1198187 10/29/12 Remote - Fred J
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J
Medtronic - SO1197187 11/02/12 Remote - Fred J
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D
Medtronic - SO1197187 11/05/12 Remote - Fred J
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D
HSBC - SO9619 v11 TDM Upgrades
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D
APAC - SO9641 Dialogic Card Install - Remote
VistaCom - SO9654 - License Upgrade - Remote
CDW - AFNI SO9677 Global Monitor Planning & Design
APAC (Davenport) - SO9690 Dialogic Card Install - Remote
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J
TOS - Region of Waterloo - SO9735 V11 WFO
Seimens _ Medstar SO9740 QM Supervisor Training
CDW - Vectren Energy SO10032 Op QM
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D
Siemens - Watson Clinic - SO9772 Add Licensing - Remote
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T
FabriCut, Inc. - SO9367 v11 Install
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12
Verizon - SO9291 Hardware Upgrade
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J
Covidien - SO1203233 09/26/12 Remote - Fred J
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W
Siemens - H E B Grocery SO9320 Op QM Install
Siemens - Utah Retirement Systems SO9292 Upgrade to v11
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany)
Siemens - Peoples Natural Gas SO9328 License Update Remote
CDW - Allianz SO9330 Telephone Playback Server
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs
Siemens - Medstar - SO9280 3rd site Op QM
CDW - TMG Health - SO9372 Additional Training
Ronco Communications - SO9092 Remote NGX Configuration
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D
Accenture (Burnaby, BC) - SO8594 - Remote NGX Config
Access Communications - SO 8196 - TRE Adapter - June H
Acer America - SO8075 Server Build
ACS - SO 65257 05/29/12 - 06/01/12 Travis C
Affiliated Computer Services - SO1184427 03/19/12 - Remote Chris M
Affiliated Computer Services - SO8353 NGX Cards and Server
Allstate - SO1163209 - 01/19/12 - 01/20/12 Fred Jurs
Allstate Insurance - SO1171712 - 12/13/11 Remote Chris M
Altisource Holdings - SO 213297 03/02/12 Bobby D
Altisource Holdings - SO1175891 04/05/12
Altisource Holdings - SO1178591 04/16/12 Remote - Chris M
Altisource Holdings - SO213297 03/05/12 Remote - Bobby D
AmeriGroup Corp. - SO1186340 04/23/12 - 04/27/12 Fred J
Anderson Windows - SO1178196 04/23/12 - 04/27/12 Chris M
Anderson Windows - SO1178196 05/23/12 - 05/25/12 (2.5 days remote) - Chris M
Atos - SO62982 - 12/27/11 Remote Fred Jurs
Bank of Nova Scotia - SO1177189 04/18/12 - 04/20/12 Remote - Bobby D
BCBS MN CT Connect Remote
BCD Travel - SO1077358 - 03/19/12 - 03/21/12 Remote - Bobby D
Bell Canada - SO1177940 - 01/30/12 - 01/31/12 Remote Bobby D
Bell Canada - SO1177940 02/06/12 - 02/10/12 Bobby D Remote
California Casualty Management - SO1150205 10/31/11 Chris M
California Casualty Management - SO1150205 11/02/11 - 11/04/11 Chris M
Capital One Services - SO1175592 - 01/17/12 Chris McGuire
Capital One Services - SO1175592 - 01/24/12 Chris M - Remote
Capital One Services - SO1175592 01/15/12 - 01/17/12
Capital One Services - SO1175592 02/06/12 - 02/10/12 Chris M Remote
Carousel - Allegis Group - SO8503 Data Migration
Carousel - Flint Energies SO
CDW - Laureate University - SO8513 v11 Planning and Design
CDW - Laureate Education SO8512 LAB Site Install
CDW - Mondial - Services SO7955
CDW - State Auto Insurance - SO8515
CDW - TMG - SO8721 WFO Consulting
Ceridian - SO66040 01/15/12 Remote Fred J
City of Clarkston - SO8483 Shoretel Installation
Commission Santa Et Securities - SO1170515 - 12/12/11 Remote Fred J
Commission Santa Et Securities - SO1170515 12/09/11 Remote Fred Jurs
Compass Bank - SO1172220 11/14/11 Remote Chris M
Compass Bank - SO1172220 11/15/11 Remote Chris M
Compass Bank - SO1172220 11/16/11 - 11/17/11 Remote Chris M
Compass Bank - SO1172220 11/18/11 Remote Chris M
Computer Science Corp - SO61148 04/16/12 Remote - Fred J
Defense Information Logistics - SO 65053 02/27/12 - 03/02/12 Fred J
Defense Information Logistics - SO65053 - 02/21/12 - 02/24/12 Fred J
Defense Logistics Agency - SO65053 05/03/12 - 05/04/12 Remote - Fred J
DirectTV - SO235670-WWO 04/09/12 - 04/13/12 WFM Training - June H.
DirectTV - SO235760-WWO 03/26/12 - 03/30/12 WFM Training - June H
Duke Energy - SO1150692 12/12/11 Remote Chris M
FCCC MolDev SO8637 Fred J
Fiedlity - SO1180466 - 04/02/12 - 04/04/12 Remote - Travis C
First Comp Insurance - SO 66197 02/13/12 - 02/14/12 Remote Fred J
First Comp Insurance - SO66197 02/16/12 - 02/17/12 Remote Fred J
First Data Corporation - Hagerstown - Dan Sabo
FL Dept of Revenue - SO1113677 12/13/11 Remote Fred J
Florida Dept of Revenue - SO1113677 01/09/12 Fred Jurs
Gannett - SO64689 11/28/11 - 12/02/11 Remote Fred Jurs
GEICO - SO8448 11 Sites
Gexel - SO64173 04/18/12 Remote - Fred J
Gexel Telecom - SO64173 03/19/12 - 03/23/12 Remote - Fred J
Global Partitions - ShoreTel Install - SO8334
Grand Hall USA - Siemens - SO8471 eQM Upgrade
Green Tree - SO8378 Voice Cards - Remote
Green Tree Servicing - SO1184822 - 04/10/12 - 04/13/12 Remote - Travis C.
Green Tree Servicing - SO8221 CT Connect Upgrade - Dan
Halifax Medical Center - SO7857 Global Monitor - Robb Delaney
Home Depot - SO1185741 05/07/12 - 05/10/12 Remote - Fred J
Home Security of America - SO1164955 05/22/12 - 05/25/12 Remote - Travis C
HSBC - Training and Travel
HSBC - Buffalo Tower - SO8372 - Services
HSBC - SO 7947 Phase 1 - On Site Vernon Hills Top Layer
HSBC - POC - Vernon Hills - Top Layer SO007933
HSBC - SO8039 01/27/12 - 01/29/12 Bobby Dupa
HSBC - SO8371 Atrium and New Castle
HSBC - SO8523 Matt Hogan PM Contract
HSBC - SO8618 Top Layer and GMS Configuration
HSBC - SO8679 Matt Hogan PM Contract May 2012
HSBC - SO8681 - May Administrative Contractors
HSBC- Atrium - SO8407 Services - Tape Drive POC
Humana - SO1177300 01/25/12 Chris M - Remote
ING - SO1174000 - 11/28/11 - 11/29/11 Remote Chris McGuire
ING - SO1174000 11/18/11 - 11/19/11 Weekend Rates Chris M
ING - SO1174000 11/30/11 - 12/01/11 Remote Chris McGuire
ING - SO1174000 12/02/11 Remote Weekend Rate Chris McGuire
Intercontinental Hotel Group - SO1176660 02/21/12 - 02/22/12 Remote - Bobby D
Intercontinental Hotel Group - SO1176660 02/23/12 Remote Bobby D
Intercontinental Hotel Group - SO1176660 02/24/12 Remote Bobby D
Intercontinental Hotels Group - SO 1176660 02/16/12 Remote Bobby D
Intercontinental Hotels Group - SO1176660 02/13/12 - 02/14/12 Remote Bobby D
Intercontinental Hotels Group - SO1176660 02/15/12 Remote Bobby D
Intercontinental Hotels Group - SO1176660 02/17/12 Remote Bobby D
Intercontinental Hotels Group - SO1176660 03/06/12 Remote - Bobby D
Inventure Solutions - SO61773 01/10/12 - 01/11/12 Fred Jurs
Johns Hopkins Health Care - SO61120 05/24/12 - 05/25/12 Remote - Fred J
Johns Hopkins Physics Lab - SO61120 05/14/12 - 05/18/12 Fred J
Just Energy - SO 1179669 02/29/12 - 03/01/12 Remote Bobby D
Keystone Mercy Health Plan - SO 1170268 11/14/11 Remote Fred Jurs
Keystone Mercy Health Plan - SO1170268 - 10/31/11 - 11/04/11 Fred Jurs
Keystone Mercy Health Plan - SO1170268 - 11/07/11 - 11/11/11 Fred Jurs
LA County Employee Retirement - SO66361 03/12/12 - 03/16/12 Fred J
Life Protection Corp. - SO1173163 12/09/11 Remote Chris M
LifeLock - SO8124 Telephony Update 02/16/12
Lincoln National - SO1169194 - 11/22/11 - 11/23/11 REMOTE C McGuire
Lincoln National Insurance - SO1169194 01/09/12 Chris M
Mass Mutual Insurance - SO1175033 12/14/11 - 12/15/11 Fred J
McKesson - SO8174 DP6409 Card Install Michael T 02/22/12
Medco - Fair Lawn - SO7895 - Top Layer - Jay Schwartz
Medco - Memphis - SO7893 - Top Layer
Medco Health Solutions - SO1131855 02/21/12 -02/22/12 Remote - Travis C
MUD IT - Omaha SO 8765 v11 Upgrade (Verint)
Mutual Life Insurance - SO1175033 01/03/12 - 01/06/12 Fred Jurs
NASD Corporate Purchasing - SO8644 - Remote Dialogic
Newsday Media - SO1169226 - 11/21/11 Remote Chris M
Newsday Media - SO1170152 - 01/18/12 - 01/20/12 Chris M
Newsday Media - SO1170152 01/26/12 - 01/27/12 Chris M - Remote
Newsday Media - SO1170152 02/13/12 - 02/14/12 Remote Chris M
Nordstrom - SO452634791WWO - 03/26/12 - 03/27/12 Remote - Fred J
Northrop Grumman - SO59322 01/25/12 Travis Coates - Remote
Northrop Grumman - SO59322 02/06/12 - 02/08/12 Travis C Remote
Northrop Grumman - SO59322 02/13/12 - 02/15/12 Remote Travis C
Northrop Grumman - SO64246 02/24/12 - 02/26/12 Remote -Travis C
OGE Energy Corp - SO007866 - OKC - Dialogic
Osram Sylvania - SO1174121 02/08/12 Chris M Remote
Paetec Communications - SO62205 04/09/12 - 04/12/12 Remote - Fred J.
Paychex - SO63963 12/12/11 Remote Fred J
Paychex - SO65181 03/28/12 - 03/30/12 Remote Chris M
Paychex - SO65181 04/02/12 - 04/06/12 Remote - Fred J
Pearson Education - SO1177549 03/19/12 - 03/23/12 Travis C
Pearson Education - SO1177549 03/26/12 - 03/30/12
Pearson Education - SO7899 - Dialogic/Equinox - Dan Sabo
PNC Bank - SO1174023 12/05/11 - 12/06/11 Remote Chris M
PNC Bank - SO1179279 03/20/12 - Remote Chris M
Policy Studies - SO1184874 - 04/02/12 - 04/06/12 Chris M
Policy Studies - SO1184874 03/26/12 - 03/30/12 Chris M
Policy Studies - SO1184874 04/09/12 - 04/13/12 Remote - Chris M
PPL Services Corp - SO1147488 - 01/30/12 Remote - Chris M
Prudential Insurance - SO1185418 04/16/12 - 04/17/12 Remote - Bobby D
PSECU - SO1185209 05/14/12 - 05/18/12 Chris M
PSECU - SO1185209 05/21/12 - 05/23/12 (2.5 days remote) - Chris M
Residential Funding - SO1176678 05/21/12 Remote - Fred J
Restaurant Technology Services - SO65125 12/06/11 - 12/08/11 Remote Fred Jurs
Sage Software - SO1175076 03/05/12 - 03/09/12 Remote - Fred J
Sage Software - SO1175076 -1/12/12 - 01/13/12 Fred Jurs
Sage Software - SO1187424 04/17/12 - 04/20/12 Remote - Chris M
Santee Cooper (Presidio) SO8003 eWFM - June Haycraft
SAP - SO1170176 - 11/07/11 - 11/11/11 Chris M
SAP - SO1170176 12/14/11 - 12/16/11 Remote Chris M
Select Portfolio Servicing
Select Portfolio Servicing - SO1166714 12/07/11 - 12/08/11 Remote Chris M
Select Portfolio Servicing - SO1166714 FOC - 12/16/11 .5 days Remote - Chris M
Selective Insurance Company - SO8130 Card Install
Siemens - City of Rocky Mount, NC SO8369
Siemens - HEB Grocery Virtualization
Siemens - Henry Ford Health System - SO9002 Remote Card Install
Siemens - Intuition - SO8344 v11 Upgrade
Siemens - Jackson Memorial - SO8044 - RemoteTraining
Siemens - Univ of California- eQM SO 7978 - Bobby Dupa
Siemens - Watson Clinic - SO8392 License Update
Siemens (Atos) - SO58904 12/16/11 Remote Fred J
Siemens Building Technologies (Irving) - SO8595 - eQM Install
Siemens -Watson Clinic - SO8343 License Upgrade
Small Business Administration - SO64144 02/06/12 - 02/10/12 Fred J Remote
Sprint Spectrum - SO221677 WWO - 05/29/12 - 06/01/12 Chris M
Sprint Spectrum - SO221677WWO - 06/04/12 - 06/08/12 Chris M
Stanley Convergent - SO 7715 Remote Services
State of Oregon (Verizon) SO8270 03/15/12 - Bobby D
T D Bank N. A. - SO1175812 01/11/12 - 01/13/12 Chris M
Tampa Electric - SO1181568 04/24/12 Remote - Bobby D
TBL Networks - VA Department of Taxation SO8518 WFO
TD Bank N.A. - SO1175812 01/10/12 Chris M
Think Tech - SO1182504 04/13/12 Remote - Fred J.
Thrivent Financial - SO1181284 04/23/12 Remote - Bobby D
TOS - Chrysler Canada - Upgrade to v10 - Bobby Dupa (Remote)
TriNet - SO58476 12/19/11 - 12/23/11 Remote Fred Jurs
U S Small Business Administration - SO64144 01/23/12 - 01/27/12 Fred Jurs
United Airlines - SO1135019 02/29/12 - 03/01/12 Chris M
United Airlines - SO1135019 03/21/12 - 03/23/12 Chris M
United Stationers Supply - SO#8235 - 03-07-12 Dialogic install - REMOTE (Dan Sabo)
Unused Resource - Fred Jurs - SO99999 05/01/12 - 05/02/12
Unused Resource - Fred Jurs - SO99999 05/11/12
Unused Resource - SO99999 01/03/12 - 01/04/12 Chris M
US Small Business Administration - SO64144 04/20/12 Remote - Fred J
Vangent - SO8164 - CT Connect Upgrade
Vanguard - SO8748 Direct Hardware Configuration
Viking River Cruises - SO65183 11/15/11 - 11/18/11 Remote Fred Jurs
Visa Desjardins - SO1175638 - 12/19/11 - 12/23/11 Remote Chris M
Visa Desjardins - SO1175638 01/05/12 - 01/06/12 Chris M
VistaCom - Ashley Furniture SO8401 License Upgrade
Wescom Credit Union - SO65668 - 01/17/12 - 01/18/12 Fred Jurs
Worldcom Exchange - SO8757 Trunk Tap Onsite
HSBC - SO9101 - August PM Resource - M Hogan
HSBC - SO9100 - August Admin Support Resources
Ericsson, Inc. - SO9111 Level 3 Support
R J Reynolds - SO9109 - v11 Compliance
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J
Unused Resource - SO99999 08/03/12 Fred Jurs
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M
Unused Resource - SO99999 08/16/12 Chris McGuire
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J
Edward Jones - SO1180791 08/20/12 Remote - Michael T
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T
Unused Resource - SO99999 Michael Taylor
Unused Resource - SO99999 08/27/12 Fred Jurs
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T
Telus Communications - Prospera SO9205 WFM Move
Siemens - Capital City Bank - SO9240 eQM License Update
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T
Siemens - Dematic Corp. - SO9847
Nissan North America - SO9777 On Site Services
CDW - TMG - SO9856 - Additional Recorders
APAC - SO9862 Tucson - Dialogic Install