## Sheet1
Primary Contact | Sales Order | Customer PO | Customer PO Received Date | COS Received | COS Received Date | pj Title | ms Stage | pj current Milestone | pj Type | pj Booked Services Revenue | pj Services Revenue | ms % Earned Revenue | ms Earned Revenue | ms % Invoiced Revenue | ms Invoiced Revenue | pj Start Date | pj Est Completion Date | ms Target Start Date | ms Actual Start Date | ms Target Completion Date | ms Actual Completion Date | tm Name | tm Start Date | ms Completed | pj Partner | ms Owner | ms Executor 1 | ms Executor 2 | tm Owner | pj Owner | tm Num Hours | tm End Date
Helene Thompson | 10833 | 210931 | 2013/09/25 | False |  | Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 2429-09-02 | 2429-09-02 | 1900-01-19 | 2005-12-06 | 1900-01-14 | 2005-12-06 | 2013/10/02 | 2014/01/31 |  |  | 2013/11/29 | 2013/11/29 | Hello test 1 | 2014/04/11 | True | Verint Channel | Tim Johnson | Adam Ip | Libby Lasseigne | Adam Ip | Stewart Futcher | 3 | 2014/04/18
Helene Thompson | 10833 | 210931 | 2013/09/25 | False |  | Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 2429-09-02 | 2429-09-02 | 1900-01-19 | 2005-12-06 | 1900-01-14 | 2005-12-06 | 2013/10/02 | 2014/01/31 |  |  | 2013/11/29 | 2013/11/29 | Hello test 1 | 2014/04/11 | True | Verint Channel | Tim Johnson | Adam Ip | Libby Lasseigne | Adam Ip | Stewart Futcher | 3 | 2014/04/18
Helene Thompson | 10833 | 210931 | 2013/09/25 | False |  | Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 2429-09-02 | 2429-09-02 | 1900-01-19 | 2005-12-06 | 1900-01-14 | 2005-12-06 | 2013/10/02 | 2014/01/31 |  |  | 2013/11/29 | 2013/11/29 | Hello test 2 | 2014/04/23 | True | Verint Channel | Tim Johnson | Adam Ip | Libby Lasseigne | Adam Ip | Stewart Futcher | 5.25 | 2014/04/25
Helene Thompson | 10833 | 210931 | 2013/09/25 | False |  | Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 2429-09-02 | 2429-09-02 | 1900-01-19 | 2005-12-06 | 1900-01-14 | 2005-12-06 | 2013/10/02 | 2014/01/31 |  |  | 2013/11/29 | 2013/11/29 | Hello test 2 | 2014/04/23 | True | Verint Channel | Tim Johnson | Adam Ip | Libby Lasseigne | Adam Ip | Stewart Futcher | 5.25 | 2014/04/25