## Time Slot
pj Title | ms Stage | pj current Milestone | pj Type | pj Services Revenue | pj Booked Services Revenue | pj rec Owner | ms % Earned Revenue | ms Earned Revenue | ms % Invoiced Revenue | ms Invoiced Revenue | pj Start Date | pj Est Completion Date | ms Target Start Date | ms Actual Start Date | ms Target Completion Date | ms Actual Completion Date | ms rec Owner | tm Name | tm Type | tm Start Date | tm End Date | tm Num Hours | tm Executor | tm rec Owner | ms Completed | Primary Contact | Sales Order | Customer PO | Customer PO Received Date | COS Received | COS Received Date
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Planning & Design | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Hardware / Software Procurement | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Product Installation | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Product Integration | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Project Closure | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 100 | 5270 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
BBVA Compass Bank - SO9870 License Update | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Support Turnover | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BMW - SO10979 - Onsite Installation Services | Project Kick Off | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Planning & Design | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Hardware / Software Procurement | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Product Installation | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 | 2013/10/31 |  | 2013/10/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Project Closure | Project Closure |  | 7050 | 14100 | Philip Haskings | 100 | 7050 | 0 | 0 | 2013/10/14 | 2013/12/12 | 2013/11/01 |  | 2013/12/12 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Project Kick Off | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Planning & Design | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Hardware / Software Procurement | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Product Installation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  | 2013/11/18 | 2013/11/18 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Project Closure | Project Closure |  | 7050 | 0 | Philip Haskings | 100 | 7050 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  | 2013/12/12 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  | 2013/10/15 |  | 2013/10/16 | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  | 2013/10/15 |  | 2013/10/17 | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Readiness Validation | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Product Installation | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/10/21 |  | 2013/10/25 |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Product Integration | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 50 | 165000 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/10/28 |  | 2013/10/31 | 2013/10/31 | John Randall | [7 empty] | True | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Training | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/11/18 |  | 2013/11/26 |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Project Closure | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 50 | 165000 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/11/27 |  | 2013/11/27 | 2013/11/29 | John Randall | [7 empty] | True | Mary King | 10996 | 16423 | 2013/10/15 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Project Kick Off | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Planning & Design | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/18 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/10/31 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Product Installation | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/19 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Product Integration | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 100 | 750 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Project Closure | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  | 2013/12/31 |  | Philip Haskings | [7 empty] | False | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Project Kick Off | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Planning & Design | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Hardware / Software Procurement | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Product Installation | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 | 2013/12/08 |  | 2013/12/11 | 2013/12/13 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Project Closure | Project Closure |  | 3580 | 0 | Philip Haskings | 100 | 3580 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Project Kick Off | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Planning & Design | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Hardware / Software Procurement | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Product Installation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 | 2013/12/08 |  | 2013/12/11 | 2013/12/13 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Project Closure | Project Closure |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
HSBC - PM - March 2014 | Project Kick Off | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Planning & Design | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Readiness Validation | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Product Installation | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Product Integration | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Training | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Support Turnover | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Project Closure | Project Closure |  | 17280 | 0 | Tim Johnson | 100 | 17280 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  | 2014/03/31 | 2014/03/24 | Matt Hogan | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - January 2014 | Project Kick Off | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Planning & Design | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Hardware / Software Procurement | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Readiness Validation | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Product Installation | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Product Integration | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Training | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Consulting & Technical Reviews | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Support Turnover | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Project Closure | Project Closure |  | 20160 | 0 | Tim Johnson | 100 | 20160 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - February 2014 | Project Kick Off | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Planning & Design | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Readiness Validation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Product Installation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Product Integration | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Training | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Support Turnover | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Project Closure | Project Closure |  | 17280 | 0 | Matt Hogan | 100 | 17280 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
Windstream - Bausch and Lomb - SO11042 | Project Kick Off | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Planning & Design | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  | 2013/10/30 | 2013/10/31 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Consulting & Technical Reviews | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 | 2013/11/01 |  | 2013/11/03 | 2013/11/02 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Project Closure | Project Closure |  | 5600 | 0 | Philip Haskings | 100 | 5600 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  | 2013/12/09 | 2013/12/16 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
BMW - SO11055 - GM installation on 9 servers | Project Kick Off | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  | 2014/01/08 | Philip Haskings | [7 empty] | True | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Planning & Design | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Product Integration | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Support Turnover | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Project Closure | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
Verint PMO Revenue - January 2014 | Project Kick Off | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Planning & Design | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Readiness Validation | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Product Installation | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Product Integration | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Training | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Support Turnover | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Project Closure | Project Closure |  | 10200 | 10200 | Kent Pylant | 100 | 10200 | 0 | 0 | 2014/01/01 | 2014/01/31 | 2014/01/01 | 2014/01/01 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint RRI Revenue - January 2014 | Project Kick Off | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Planning & Design | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Readiness Validation | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Product Installation | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Product Integration | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Training | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Support Turnover | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Project Closure | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 100 | 12906.25 | 0 | 0 | 2014/01/02 | 2014/02/04 | 2014/01/02 | 2014/01/02 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 | 2014/01/01 | 2014/01/02 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - February 2014 | Project Kick Off | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Planning & Design | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Readiness Validation | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Product Installation | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Product Integration | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Training | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Support Turnover | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Project Closure | Project Closure |  | 0 | 7000 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 | 2014/02/01 | 2014/02/01 | 2014/02/28 | 2014/02/28 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Project Kick Off | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Planning & Design | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Readiness Validation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Product Installation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Product Integration | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Training | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Support Turnover | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Project Closure | Project Closure |  | 0 | 1400 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 | 2014/02/01 | 2014/02/03 | 2014/02/28 | 2014/02/28 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Project Kick Off | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Planning & Design | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Readiness Validation | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Product Installation | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Product Integration | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Training | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Support Turnover | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Project Closure | Project Closure |  | 0 | 3500 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 | 2014/03/01 | 2014/03/03 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - March 2014 | Project Closure | Project Closure |  | 0 | 1400 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 | 2014/03/01 | 2014/03/03 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/02/03 | False
APAC - SO9872 - Dialogic Install | Project Kick Off | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Planning & Design | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Hardware / Software Procurement | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Readiness Validation | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Product Installation | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Product Integration | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Training | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Consulting & Technical Reviews | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Support Turnover | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Project Closure | Project Closure |  | 1300 | 0 | Philip Haskings | 100 | 1300 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Medco - SO1208699 02/01/13 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Planning & Design | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Product Installation | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Product Integration | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Training | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Support Turnover | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Project Closure | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Planning & Design | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Product Installation | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Product Integration | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Training | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Support Turnover | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Project Closure | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Unused Resource - SO99999 01/07/13 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Planning & Design | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Product Installation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Product Integration | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Training | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Support Turnover | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Project Closure | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Intact - SO 1213063 01/02/13 Remote - Robb D | Project Kick Off | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Planning & Design | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Readiness Validation | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Product Installation | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Product Integration | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Training | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Support Turnover | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Project Closure | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Project Kick Off | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Planning & Design | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Hardware / Software Procurement | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Readiness Validation | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Product Installation | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Product Integration | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Training | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Consulting & Technical Reviews | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Support Turnover | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Project Closure | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
McKesson - SO1202191 01/02/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Planning & Design | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Product Installation | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Product Integration | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Training | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Support Turnover | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Project Closure | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
APAC - SO9888 Remote Services | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | False |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Project Kick Off | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Planning & Design | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Hardware / Software Procurement | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Readiness Validation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Product Installation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Product Integration | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Training | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Consulting & Technical Reviews | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Support Turnover | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Project Closure | Project Closure |  | 1800 | 0 | Stewart Futcher | 100 | 1800 | 0 | 0 | [5 empty] | 2013/04/05 | Tim Johnson | [7 empty] | True |  | 9740 | 7700237041
Apple Inc - Onsite v11 Server Installation - SO10129 | Project Kick Off | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Planning & Design | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Hardware / Software Procurement | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Readiness Validation | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Product Installation | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Product Integration | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Consulting & Technical Reviews | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Support Turnover | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Project Closure | Project Closure |  | 13500 | 0 | Philip Haskings | 100 | 13500 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Project Kick Off | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Planning & Design | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Training | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Support Turnover | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Project Closure | Project Closure |  | 1600 | 0 | Philip Haskings | 100 | 1600 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Project Kick Off | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Planning & Design | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Hardware / Software Procurement | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Readiness Validation | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Product Installation | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Product Integration | Project Closure |  | 45000 | 0 | Philip Haskings | 90 | 40500 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Training | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Consulting & Technical Reviews | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Support Turnover | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Project Closure | Project Closure |  | 45000 | 0 | Philip Haskings | 10 | 4500 | 0 | 0 |  | 2014/02/28 |  |  | 2014/02/28 | 2014/02/26 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Training | Training | Project Closure |  | 25000 | 0 | Philip Haskings | 50 | 12500 | 0 | 0 | 2013/01/01 | 2013/09/30 |  |  | 2013/10/31 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 9297 | 2120930-01 | 2013/01/01 | True | 2013/10/15
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Training | Project Closure | Project Closure |  | 25000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/30 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 9297 | 2120930-01 | 2013/01/01 | True | 2013/10/15
Verint - Amway Services - SO10138 - John R | Project Kick Off | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Planning & Design | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Hardware / Software Procurement | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Readiness Validation | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Product Installation | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Product Integration | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Training | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Consulting & Technical Reviews | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Support Turnover | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Project Closure | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
NACR - CoBank - SO10165 - After Hours Support | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
Verint - California Casualty - SO10162 Onsite Services | Project Kick Off | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Planning & Design | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Hardware / Software Procurement | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Readiness Validation | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Product Installation | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Product Integration | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Training | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Consulting & Technical Reviews | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Support Turnover | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Project Closure | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services |  | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 | 2013/04/16 | 2013/04/16 | 2013/04/16 | 2013/04/16 | Kent Pylant | [7 empty] | True |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services |  | 7 - Training |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2013/04/17 | 2013/04/19 | 2013/04/17 | 2013/04/17 | 2013/04/19 | 2013/04/19 | Kent Pylant | [7 empty] | True |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Molecular Devices - SO10125- Germany - Research 10 | Project Kick Off | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Planning & Design | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Product Installation | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Product Integration | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Project Closure | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
NACR - CoBank - SO10177 - Remote License Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Project Kick Off | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Planning & Design | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Product Installation | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Product Integration | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Support Turnover | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Project Closure | Project Closure |  | 1000 | 0 | Philip Haskings | 100 | 1000 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Planning & Design | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Product Installation | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/03 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Product Integration | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/03 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Project Closure | Project Closure |  | 7200 | 0 | Philip Haskings | 100 | 7200 | 0 | 0 | [5 empty] | 2013/07/08 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Project Kick Off | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/13 | 2013/05/13 | 2013/05/13 | 2013/05/13 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Planning & Design | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/20 | 2013/05/20 | 2013/05/20 | 2013/05/24 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/15 | 2013/05/15 | 2013/05/15 | 2013/05/15 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Readiness Validation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/03 | 2013/06/03 | 2013/06/03 | 2013/06/04 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Product Installation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Product Integration | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Training | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/09/16 |  | 2013/09/20 |  | Tim Johnson | [7 empty] | False |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/05 | 2013/08/05 | 2013/08/23 | 2013/08/23 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Support Turnover | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/26 |  | 2013/08/26 |  | Tim Johnson | [7 empty] | False |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Project Closure | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 22400 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/19 |  | 2013/08/30 | 2013/08/30 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Project Kick Off | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/06 | 2013/05/06 | 2013/05/06 | 2013/05/06 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Planning & Design | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/13 | 2013/05/13 | 2013/05/13 | 2013/05/24 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/03 | 2013/05/03 | 2013/05/03 | 2013/05/10 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Readiness Validation | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/03 | 2013/06/03 | 2013/06/03 | 2013/06/04 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Product Installation | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Product Integration | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 95 | 29735 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Training | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2014/01/20 |  | 2014/01/31 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/05 | 2013/08/05 | 2013/08/16 | 2013/08/19 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Support Turnover | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/26 | 2013/08/27 | 2013/08/26 | 2013/08/27 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Project Closure | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/09/27 |  | 2013/09/27 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Project Kick Off | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Planning & Design | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Hardware / Software Procurement | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Readiness Validation | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Product Installation | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Product Integration | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Training | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Consulting & Technical Reviews | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Support Turnover | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Project Closure | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 |  |  | 2013/05/28 | 2013/05/28 | 2013/05/31 | 2013/05/31 | Tim Johnson | [7 empty] | True |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
Molecular Devices - SO10170 - MedImmune HCS Solution | Project Kick Off | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Planning & Design | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Hardware / Software Procurement | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Product Installation | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Project Closure | Project Closure |  | 5270 | 0 | Philip Haskings | 100 | 5270 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/10/10 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/08 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Training | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Project Kick Off | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/16 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Planning & Design | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Hardware / Software Procurement | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/21 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Readiness Validation | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/22 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Product Installation | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Product Integration | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Consulting & Technical Reviews | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Project Closure | Project Closure |  | 5500 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
Charter Communications - SO10307 Hard Drive Solution Services | Project Kick Off | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Planning & Design | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Product Installation | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/20 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Project Closure | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 100 | 14100 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Johnson & Johnson - SO10313 On Site Card Install | Project Kick Off | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Planning & Design | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Hardware / Software Procurement | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Product Installation | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Project Closure | Project Closure |  | 4000 | 0 | Philip Haskings | 100 | 4000 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
ACS Technologies - SO10315 - Dell Server Remote Services | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/08/14 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/05/29 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Project Kick Off | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Planning & Design | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Hardware / Software Procurement | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Readiness Validation | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Product Installation | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Product Integration | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Training | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Consulting & Technical Reviews | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Support Turnover | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Project Closure | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
CDW - Comerica SO9679 License Update | Project Kick Off | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Planning & Design | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Readiness Validation | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Product Installation | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Product Integration | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Training | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Support Turnover | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Project Closure | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 500 | 0 | 0 | 2013/05/28 | 2013/05/29 |  | 2013/05/20 |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9679 | KAU6719 |  | True
Siemens - Peoples Natural Gas SO10359 v11 WFO | Project Kick Off | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/06/17 | 2013/06/17 | 2013/06/17 | 2013/06/17 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Planning & Design | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/03 | 2013/07/03 | 2013/07/12 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Hardware / Software Procurement | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/08 | 2013/07/08 | 2013/07/08 | 2013/07/10 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Readiness Validation | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/09 | 2013/07/11 | 2013/07/09 | 2013/07/11 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Product Installation | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/15 | 2013/07/15 | 2013/07/19 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Product Integration | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/22 | 2013/07/22 | 2013/07/26 | 2013/07/26 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Training | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/12 | 2013/08/12 | 2013/08/16 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Consulting & Technical Reviews | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/12 | 2013/08/12 | 2013/08/19 | 2013/08/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Support Turnover | Project Closure |  | 48800 | 0 | Stewart Futcher | 100 | 48800 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/26 | 2013/08/19 | 2013/08/26 | 2013/08/30 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Project Closure | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/09/20 | 2013/09/24 | 2013/09/20 | 2013/09/24 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Coventry Management Services - SO10373 - PCIE Remote Install | Project Kick Off | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Planning & Design | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/15 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/15 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Product Installation | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/25 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Project Closure | Project Closure |  | 1000 | 0 | Philip Haskings | 100 | 1000 | 0 | 0 | [5 empty] | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Verint - AAA NC SO10402 Card Issues - John R | Project Kick Off | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Planning & Design | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Hardware / Software Procurement | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Readiness Validation | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Product Installation | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Product Integration | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Training | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Consulting & Technical Reviews | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Support Turnover | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Project Closure | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Siemens - Medstar Health - SO10404 License Addition | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
CDW - Comerica - SO10300 Training | Project Kick Off | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Planning & Design | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Hardware / Software Procurement | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Readiness Validation | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Product Installation | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Product Integration | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Training | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Consulting & Technical Reviews | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Support Turnover | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Project Closure | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 100 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  | 2013/06/28 | Tim Johnson | [7 empty] | True |  | 10300 | 10184-2 | 2013/06/07 | False
City of Chicago - SO11678 - SSL Enablement | Project Kick Off | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  | 2014/03/20 | Tim Johnson | [7 empty] | True | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Planning & Design | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 50 | 5175 | 0 | 0 | 2014/03/25 | 2014/05/30 |  | 2014/03/20 | 2014/04/11 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Hardware / Software Procurement | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Readiness Validation | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Product Installation | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Product Integration | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 50 | 5175 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/03/31 |  | 2014/05/16 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Training | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Consulting & Technical Reviews | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Support Turnover | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Project Closure | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/21 |  | 2014/04/30 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
Avista - SO11661 - Cutover Support | Support Turnover | 8 - Consulting & Technical Reviews |  | 3800 | 0 | Stewart Futcher | 100 | 3800 | 0 | 0 | 2014/03/26 | 2014/04/04 |  |  | 2014/04/04 |  | Stewart Futcher | [7 empty] | False | Susan Anderson | 11661 | 213614 | 2014/03/20 | False
Avista - SO11661 - Cutover Support | Project Closure | 8 - Consulting & Technical Reviews |  | 3800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/26 | 2014/04/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Susan Anderson | 11661 | 213614 | 2014/03/20 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Project Kick Off | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/22 |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Planning & Design | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 25 | 1287.5 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/22 |  | 2014/04/25 |  | Rebecca Chaussinand | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Hardware / Software Procurement | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Readiness Validation | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/01 |  | 2014/05/02 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Product Installation | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/05 |  | 2014/05/06 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Training | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 75 | 3862.5 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/28 |  | 2014/05/30 |  | Rebecca Chaussinand | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Project Closure | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/30 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Google Lab Implementation - Jon Sant | Project Kick Off | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Planning & Design | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 25 | 11200 | 0 | 0 |  |  |  |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Hardware / Software Procurement | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Readiness Validation | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Product Installation | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Product Integration | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 50 | 11200 | 0 | 0 |  |  |  |  | 2014/05/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Training | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Consulting & Technical Reviews | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Support Turnover | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 25 | 11200 | 0 | 0 |  |  |  |  | 2014/06/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Project Closure | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Project Kick Off | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/09 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Planning & Design | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Hardware / Software Procurement | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Product Integration | Project Closure |  | 500 | 500 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  | 2014/01/31 | 2014/01/30 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Project Closure | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/30 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
Bluegreen - SO11254 - GM Installation | Project Kick Off | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Planning & Design | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Hardware / Software Procurement | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Readiness Validation | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Product Installation | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Product Integration | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Training | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Support Turnover | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Project Closure | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  | 2014/05/31 |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Memphis Light, Gas and Water - SO11247 | Project Kick Off | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/04 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Planning & Design | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Product Integration | Project Closure |  | 3500 | 0 | Philip Haskings | 100 | 3500 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Project Closure | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
AtlantiCare - SO11277 - Onsite Installation | Project Kick Off | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Planning & Design | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Hardware / Software Procurement | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Product Installation | Project Closure |  | 4000 | 4000 | Philip Haskings | 100 | 4000 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Project Closure | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Project Kick Off | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Planning & Design | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Hardware / Software Procurement | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Readiness Validation | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Product Installation | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Product Integration | Project Closure |  | 18000 | 18000 | John Randall | 100 | 18000 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/21 | John Randall | [7 empty] | True | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Training | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Consulting & Technical Reviews | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Support Turnover | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Project Closure | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Project Kick Off | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/01/09 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Planning & Design | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Hardware / Software Procurement | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Readiness Validation | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Product Installation | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Product Integration | Project Closure |  | 14500 | 14500 | Philip Haskings | 100 | 14500 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  | 2014/03/07 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Consulting & Technical Reviews | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 | 2014/03/03 |  | 2014/03/03 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Project Closure | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 | 2014/03/14 |  | 2014/03/14 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Amway - SO11094 - GM Installation | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Support Turnover | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Medstar - SO11299 - 12 Additional Licenses | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/25 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/27 | 2014/03/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Level One - SO9944 QM Training - Verint Services | Project Kick Off | Project Closure |  | 3100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Level One - SO9944 QM Training - Verint Services | Training | Project Closure |  | 3100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Level One - SO9944 QM Training - Verint Services | Project Closure | Project Closure |  | 3100 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/27 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Medical Mutual - SO9946 Remote Config | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/29 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
MolDev - SO9595 - Russia HCS Quest 64 | Project Kick Off | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Planning & Design | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Hardware / Software Procurement | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Product Installation | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Product Integration | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Support Turnover | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Project Closure | Project Closure |  | 4995 | 0 | Philip Haskings | 100 | 4995 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Project Kick Off | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Planning & Design | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Hardware / Software Procurement | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Product Installation | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Product Integration | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Support Turnover | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Project Closure | Project Closure |  | 9990 | 0 | Philip Haskings | 100 | 9990 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
Nissan North America - SO9975 Irving TX Onsite | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/02 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Project Kick Off | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Planning & Design | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Hardware / Software Procurement | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Readiness Validation | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Product Installation | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Product Integration | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Training | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Consulting & Technical Reviews | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Support Turnover | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Project Closure | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Project Kick Off | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/24 |  | 2014/01/24 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Planning & Design | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/24 |  | 2014/01/24 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Product Integration | Project Closure |  | 700 | 700 | Philip Haskings | 100 | 700 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/25 | 2014/02/03 | 2014/01/25 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Project Closure | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  |  |  | 2014/02/03 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Project Kick Off | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Planning & Design | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Hardware / Software Procurement | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Product Integration | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 100 | 6600 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/03/18 |  | Philip Haskings | [7 empty] | False | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Project Closure | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Google - SO11457 | Project Kick Off | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Planning & Design | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Hardware / Software Procurement | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Readiness Validation | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Product Installation | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Product Integration | Project Closure |  | 4800 | 0 | Stewart Futcher | 100 | 4800 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/25 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Training | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Consulting & Technical Reviews | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Support Turnover | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Project Closure | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
United BioSource a divisio of Express Scripts l OEM | Project Kick Off | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Planning & Design | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Readiness Validation | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Product Installation | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Product Integration | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Training | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Support Turnover | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Project Closure | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Project Kick Off | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Planning & Design | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Readiness Validation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Product Installation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Product Integration | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 100 | 6700 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Training | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Support Turnover | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Project Closure | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Project Kick Off | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Planning & Design | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Readiness Validation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Product Installation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Product Integration | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 100 | 6700 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Training | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Support Turnover | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Project Closure | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Project Kick Off | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Planning & Design | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Hardware / Software Procurement | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Product Installation | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Product Integration | Project Closure |  | 750 | 750 | Philip Haskings | 100 | 750 | 0 | 0 | 2014/02/04 | 2014/03/31 | 2014/03/19 |  | 2014/03/20 | 2014/03/20 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Project Closure | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  | 2014/03/28 | 2014/03/31 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Questar - SO11489 - DPA | Project Kick Off | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Planning & Design | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Hardware / Software Procurement | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Readiness Validation | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Product Installation | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Product Integration | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 100 | 30600 | 0 | 0 | 2014/02/03 | 2014/02/07 | 2014/04/07 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Training | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Consulting & Technical Reviews | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Support Turnover | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Project Closure | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Weber Stephen Products - SO11468 - oWFM | Project Kick Off | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Planning & Design | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Hardware / Software Procurement | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Readiness Validation | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Product Installation | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Product Integration | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Training | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Support Turnover | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Project Closure | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Project Kick Off | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  | 2014/02/20 |  | 2014/02/20 | Tim Johnson | [7 empty] | True | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Planning & Design | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Hardware / Software Procurement | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Readiness Validation | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Product Installation | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Product Integration | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Training | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Consulting & Technical Reviews | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Support Turnover | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 100 | 44420 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  | 2014/06/20 |  | Charlene Dennis | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Project Closure | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Project Kick Off | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Planning & Design | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 25 | 5850 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/04/11 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Hardware / Software Procurement | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Readiness Validation | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Product Installation | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Product Integration | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 50 | 11700 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/05/09 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Training | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Consulting & Technical Reviews | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Support Turnover | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 25 | 5850 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/06/06 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Project Closure | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Project Kick Off | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Planning & Design | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Hardware / Software Procurement | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Readiness Validation | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Product Installation | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Product Integration | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/04/01 |  | Philip Haskings | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Training | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Consulting & Technical Reviews | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Support Turnover | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Project Closure | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Project Kick Off | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/14 | 2014/03/14 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Planning & Design | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 25 | 3600 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/12 | 2014/03/12 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Hardware / Software Procurement | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/10 | 2014/03/05 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Readiness Validation | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/14 |  | 2014/03/17 | 2014/03/21 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Product Installation | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/24 |  | 2014/03/28 | 2014/03/26 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Product Integration | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 50 | 7200 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/24 |  | 2014/03/28 | 2014/03/28 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Training | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/21 |  | 2014/04/25 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Consulting & Technical Reviews | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/21 |  |  |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Support Turnover | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 25 | 3600 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/28 |  | 2014/04/30 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Project Closure | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/30 |  | 2014/04/30 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Project Kick Off | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  |  | 2014/02/27 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Planning & Design | 5 - Product Installation |  | 220000 | 0 | John Randall | 50 | 110000 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  | 2014/02/28 | 2014/02/28 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Hardware / Software Procurement | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  |  | 2014/04/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Readiness Validation | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/04/07 | 2014/04/10 | 2014/04/07 | 2014/04/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Product Installation | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/04/10 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Product Integration | 5 - Product Installation |  | 220000 | 0 | John Randall | 50 | 110000 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  | 2014/05/30 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Training | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/05/12 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Consulting & Technical Reviews | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Support Turnover | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Project Closure | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
Charter - SO11502 - F5 Implementation | Project Kick Off | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  | 2014/02/21 |  | 2014/02/21 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Planning & Design | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  | 2014/02/21 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/21 | 2014/02/21 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Readiness Validation | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/24 | 2014/02/24 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Product Installation | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/25 | 2014/02/25 | 2014/02/26 | 2014/02/25 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Product Integration | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/26 | 2014/02/25 | 2014/02/26 | 2014/02/25 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Training | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/26 | 2014/02/26 | 2014/02/26 | 2014/02/26 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/02/26 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Support Turnover | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/03/12 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Project Closure | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/03/12 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Project Kick Off | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Planning & Design | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Training | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 100 | 1150 | 0 | 0 | 2014/02/19 | 2014/04/30 | 2014/04/21 |  | 2014/04/21 |  | Philip Haskings | [7 empty] | False | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Project Closure | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Project Kick Off | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  | 2014/02/17 | Philip Haskings | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Planning & Design | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Product Integration | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 100 | 16750 | 0 | 0 | 2014/02/20 | 2014/03/31 | 2014/03/23 |  | 2014/03/27 |  | Philip Haskings | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Project Closure | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
HSBC - PM - July 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  | 2014/07/31 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
Nissan - SO11528 - Remote Services | Project Kick Off | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Planning & Design | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Hardware / Software Procurement | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Product Integration | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Project Closure | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Project Kick Off | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Planning & Design | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 50 | 106000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/02/28 | 2014/02/28 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Readiness Validation | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Product Installation | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Product Integration | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 50 | 106000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/05/16 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Training | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Support Turnover | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Project Closure | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Project Kick Off | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Planning & Design | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 50 | 90000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/03/31 | 2014/03/24 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Readiness Validation | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Product Installation | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Product Integration | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 50 | 90000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/06/20 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Training | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Support Turnover | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Project Closure | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Project Kick Off | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/11 | 2014/03/11 | 2014/03/11 | 2014/03/11 | Stewart Futcher | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Planning & Design | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 50 | 44675 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/24 | 2014/03/24 | 2014/03/28 | 2014/03/31 | Stewart Futcher | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Hardware / Software Procurement | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/17 | 2014/03/17 | 2014/03/17 | 2014/03/18 | Tim Johnson | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Readiness Validation | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/31 | 2014/04/01 | 2014/03/31 | 2014/04/07 | Tim Johnson | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Product Installation | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/04/08 | 2014/04/08 | 2014/04/18 |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Product Integration | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 50 | 44675 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/04/08 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Training | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Consulting & Technical Reviews | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Support Turnover | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Project Closure | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
McKesson - SOxxxx - Radware Implementation | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Training | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
Verint PMO Revenue - June 2014 | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Project Kick Off | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Planning & Design | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Readiness Validation | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Product Installation | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Product Integration | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Training | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Consulting & Technical Reviews | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Support Turnover | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Project Closure | Project Closure |  | 1000 | 1000 | Kent Pylant | 100 | 1000 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Pleasant Holidays - SO11617 - ODBC Drivers | Product Integration | Project Closure |  | 1000 | 0 | Rebecca Chaussinand | 100 | 1000 | 0 | 0 | 2014/03/06 | 2014/03/14 |  | 2014/03/07 | 2014/03/21 | 2014/03/07 | Rebecca Chaussinand | [7 empty] | True | Heather Gault | 11617 | 159029 | 2014/03/06 | False
Pleasant Holidays - SO11617 - ODBC Drivers | Project Closure | Project Closure |  | 1000 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/06 | 2014/03/14 |  |  |  | 2014/03/19 | Rebecca Chaussinand | [7 empty] | True | Heather Gault | 11617 | 159029 | 2014/03/06 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Project Kick Off | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 34 | 7480 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/21 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Planning & Design | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Hardware / Software Procurement | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Readiness Validation | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Product Installation | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 33 | 7260 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/24 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Product Integration | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Consulting & Technical Reviews | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 33 | 7260 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/31 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Project Closure | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/06/20 |  | Philip Haskings | [7 empty] | False | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
NMAC - SO11637 - Remote Services | Project Kick Off | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Planning & Design | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Hardware / Software Procurement | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Product Integration | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 100 | 375 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Project Closure | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
Iron Mountain - SO11645 - WFO Onsite Training | Project Kick Off | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/05/30 |  |  |  | 2014/03/25 | Tim Johnson | [7 empty] | True | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Iron Mountain - SO11645 - WFO Onsite Training | Training | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 100 | 6200 | 0 | 0 | 2014/03/18 | 2014/05/30 | 2014/04/01 |  | 2014/04/03 |  | Rebecca Chaussinand | [7 empty] | False | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Iron Mountain - SO11645 - WFO Onsite Training | Project Closure | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/05/30 |  |  | 2014/04/30 |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Nissan North America - SO11605 - Change Order | Project Kick Off | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Planning & Design | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  | 2014/03/27 | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Hardware / Software Procurement | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Product Integration | Project Closure |  | 4000 | 0 | Philip Haskings | 100 | 4000 | 0 | 0 | 2014/03/18 | 2014/04/30 | 2014/03/20 | 2014/03/20 | 2014/03/21 | 2014/03/31 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Project Closure | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | False | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Wide Open West SO11652 - Avaya QM Services | Project Kick Off | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Planning & Design | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 25 | 2321.25 | 0 | 0 |  |  |  |  | 2014/04/18 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Hardware / Software Procurement | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Readiness Validation | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Product Installation | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Product Integration | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 50 | 4642.5 | 0 | 0 |  |  |  |  | 2014/04/30 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Training | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Consulting & Technical Reviews | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Support Turnover | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 25 | 2321.25 | 0 | 0 |  |  |  |  | 2014/06/18 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Project Closure | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Texas Guarantee - SO11646 - Avaya oQM services | Project Kick Off | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Planning & Design | 7 - Training |  | 137682 | 137682 | Kent Pylant | 25 | 34420.5 | 0 | 0 | 2014/03/10 | 2014/03/31 |  | 2014/02/24 | 2014/03/28 | 2014/03/06 | Kent Pylant | [7 empty] | True | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Hardware / Software Procurement | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Readiness Validation | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Product Installation | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Product Integration | 7 - Training |  | 137682 | 137682 | Kent Pylant | 50 | 68841 | 0 | 0 | 2014/03/10 | 2014/03/31 |  | 2014/03/08 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | True | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Training | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Consulting & Technical Reviews | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Support Turnover | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  | 2014/06/18 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Project Closure | 7 - Training |  | 137682 | 137682 | Kent Pylant | 25 | 34420.5 | 0 | 0 | 2014/03/10 | 2014/03/31 | 2014/05/01 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
QT11141 Nissan Smyrna | Project Kick Off | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Planning & Design | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 25 | 750 | 0 | 0 |  |  |  |  | 2014/04/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Hardware / Software Procurement | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Readiness Validation | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Product Installation | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Product Integration | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 50 | 750 | 0 | 0 |  |  |  |  | 2014/05/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Training | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Consulting & Technical Reviews | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Support Turnover | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 25 | 750 | 0 | 0 |  |  |  |  | 2014/06/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Project Closure | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
MedImpact - SO11659 - Additional Recorder and PCI | Project Kick Off | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Planning & Design | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 25 | 2750 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/04/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Hardware / Software Procurement | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Readiness Validation | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Product Installation | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Product Integration | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 50 | 5500 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/05/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Training | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Consulting & Technical Reviews | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Support Turnover | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 25 | 2750 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Project Closure | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
Charter - GM as part of Platinum Support | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 25 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 50 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/05/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Training | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 25 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
The Jay Group - SO9980 - Troubleshooting CT Connect | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Project Kick Off | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Planning & Design | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Hardware / Software Procurement | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Readiness Validation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Product Installation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Product Integration | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Support Turnover | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Project Closure | Project Closure |  | 7050 | 0 | Philip Haskings | 100 | 7050 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/22 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
CDW - AFNI - SO9988 Server Builds (Bobby D) | Project Kick Off | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Planning & Design | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Hardware / Software Procurement | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Product Installation | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Product Integration | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Support Turnover | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 4800 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Project Closure | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
Siemens - Academy Sports - SO9893 - Remote License Install | Project Kick Off | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Planning & Design | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Product Installation | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Product Integration | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Support Turnover | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Project Closure | Project Closure |  | 350 | 0 | Philip Haskings | 100 | 350 | 0 | 0 | [5 empty] | 2013/04/10 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Project Kick Off | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Planning & Design | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Hardware / Software Procurement | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Readiness Validation | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Product Installation | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Product Integration | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Training | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Consulting & Technical Reviews | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Support Turnover | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Project Closure | Project Closure |  | 1600 | 0 | Stewart Futcher | 100 | 1600 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  | 2013/06/03 | Stewart Futcher | [7 empty] | True |  | 10041 | KIJ7575 |  | True | 2013/06/03
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/03/20 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/29 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/03/20 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/29 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Nissan North America - SO10063 analog hardware - Atlanta | Project Kick Off | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/03/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Planning & Design | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/03/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Hardware / Software Procurement | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Product Installation | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/19 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Project Closure | Project Closure |  | 2350 | 0 | Philip Haskings | 100 | 2350 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Project Kick Off | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Planning & Design | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Product Integration | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Support Turnover | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Project Closure | Project Closure |  | 700 | 0 | Philip Haskings | 100 | 700 | 0 | 0 | [5 empty] | 2013/05/01 | Tim Johnson | [7 empty] | True |  | 100066 | 4500252087 |  | True
Healthgrades - SO11115 - Addition of 20 Licenses | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
Healthgrades - SO11115 - Addition of 20 Licenses | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
Healthgrades - SO11115 - Addition of 20 Licenses | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
HEB Grocery - SO11127 - oQM | Project Kick Off | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 | 2013/11/20 |  | 2013/11/22 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Planning & Design | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Hardware / Software Procurement | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Readiness Validation | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Product Installation | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/23 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Product Integration | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 100 | 25600 | 0 | 0 | 2013/11/08 | 2014/01/31 | 2014/03/17 | 2014/03/18 | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Training | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Consulting & Technical Reviews | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Support Turnover | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Project Closure | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Project Kick Off | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  | 2013/11/15 |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Planning & Design | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Hardware / Software Procurement | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Product Integration | Project Closure |  | 6700 | 6700 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Project Closure | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Project Kick Off | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Planning & Design | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Hardware / Software Procurement | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Product Integration | Project Closure |  | 6700 | 6700 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Project Closure | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Wellpoint - SO11131 - D480 Replacement | Project Kick Off | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/11/13 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Hardware / Software Procurement | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Product Integration | Project Closure |  | 6500 | 6500 | Philip Haskings | 100 | 6500 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Project Closure | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Verint MAC Revenue - March 2014 | Project Kick Off | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Planning & Design | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Readiness Validation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Product Installation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Product Integration | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Training | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Support Turnover | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Project Kick Off | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Planning & Design | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Hardware / Software Procurement | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Readiness Validation | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Product Installation | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Product Integration | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Training | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Consulting & Technical Reviews | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Support Turnover | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Project Closure | Project Closure |  | 7000 | 0 | Kent Pylant | 100 | 7000 | 0 | 0 | 2014/04/01 | 2014/04/30 | 2014/04/01 | 2014/04/01 | 2014/04/30 | 2014/04/30 | Kent Pylant | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/04/01 | 2014/04/30 | 2014/04/01 | 2014/04/01 | 2014/04/30 | 2014/04/30 | Kent Pylant | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Project Kick Off | Project Closure |  | 17875 | 0 | Philip Haskings | 25 | 4468.75 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2013/12/31 | 2013/12/11 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Planning & Design | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/12 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Hardware / Software Procurement | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/14 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Readiness Validation | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Product Installation | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/22 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Product Integration | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2013/12/13 | 2014/02/27 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Training | Project Closure |  | 17875 | 0 | Philip Haskings | 50 | 8937.5 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/14 | 2014/02/27 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Consulting & Technical Reviews | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/07 |  | Philip Haskings | [7 empty] | False | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Support Turnover | Project Closure |  | 17875 | 0 | Philip Haskings | 25 | 4468.75 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/14 | 2014/04/07 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Project Closure | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Project Kick Off | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Planning & Design | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Hardware / Software Procurement | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Readiness Validation | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Product Installation | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Product Integration | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Training | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Consulting & Technical Reviews | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Support Turnover | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Project Closure | Project Closure |  | 6333 | 0 | Stewart Futcher | 100 | 6333 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 9930 | 7700238024 |  | True
CDW - Comerica - SO7206 v7.8 Op QM | Project Kick Off | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  | 2013/01/01 |  | 2013/01/15 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Planning & Design | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Hardware / Software Procurement | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Readiness Validation | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Product Installation | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Product Integration | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Training | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Consulting & Technical Reviews | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Support Turnover | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Project Closure | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 100 | 91892 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
Region of York - SO11390 - Addtional Licenses | Project Kick Off | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 | 2014/01/10 | 2014/01/10 | 2014/01/10 | 2014/01/10 | Tim Johnson | [7 empty] | True | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Planning & Design | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Hardware / Software Procurement | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Readiness Validation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Product Installation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Product Integration | Project Closure |  | 500 | 500 | John Randall | 100 | 500 | 0 | 0 | 2014/01/09 | 2014/01/31 |  | 2014/01/29 | 2014/01/31 | 2014/01/31 | John Randall | [7 empty] | True | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Training | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Consulting & Technical Reviews | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Support Turnover | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Project Closure | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Project Kick Off | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Planning & Design | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Hardware / Software Procurement | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Readiness Validation | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Product Installation | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Product Integration | Project Closure |  | 1600 | 7200 | Kent Pylant | 100 | 1600 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  | 2014/03/21 | 2014/03/31 | Kent Pylant | [7 empty] | True | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Training | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Consulting & Technical Reviews | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Support Turnover | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Project Closure | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
Toyota - SO11393 - Training Credits | Project Kick Off | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  |  | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Planning & Design | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  |  | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Hardware / Software Procurement | Project Closure |  | 0 | 3128 | Philip Haskings | 100 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  | 2014/02/03 | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Project Closure | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  | 2014/02/17 | 2014/02/26 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Project Kick Off | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/29 | 2014/01/29 | 2014/01/29 | 2014/01/29 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Planning & Design | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/29 | 2014/01/29 | 2014/01/29 | 2014/01/29 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Hardware / Software Procurement | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/30 |  | 2014/01/30 |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Readiness Validation | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Product Installation | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Product Integration | Project Closure |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/15 | 2014/03/31 |  | 2014/03/04 | 2014/03/07 | 2014/03/28 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Training | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Consulting & Technical Reviews | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Support Turnover | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Project Closure | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/02/07 |  | 2014/02/07 | 2014/03/28 | Tim Johnson | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Project Kick Off | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  | 2014/01/28 | 2014/02/03 | 2014/01/28 | Tim Johnson | [7 empty] | True | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Planning & Design | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Hardware / Software Procurement | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Readiness Validation | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Product Installation | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Product Integration | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Training | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Consulting & Technical Reviews | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Support Turnover | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 100 | 6400 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  | 2014/05/16 |  | Charlene Dennis | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Project Closure | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Project Kick Off | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/01/28 |  | 2014/01/28 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Planning & Design | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 25 | 8775 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/17 | 2014/02/07 | 2014/02/17 | Charlene Dennis | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Hardware / Software Procurement | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/18 |  | 2014/02/18 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Readiness Validation | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/21 |  | 2014/02/21 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Product Installation | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/02/24 | 2014/02/24 | 2014/03/27 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Product Integration | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 50 | 17550 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/03/17 |  | 2014/03/31 |  | Charlene Dennis | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Training | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/03/26 |  | 2014/03/31 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Consulting & Technical Reviews | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/01 |  | 2014/04/03 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Support Turnover | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 25 | 8775 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/30 |  | 2014/04/30 |  | Charlene Dennis | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Project Closure | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/30 |  | 2014/04/30 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
Sunturn - NuSkin SO10547 - Server Move - Provo | Project Kick Off | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 | 2013/07/11 |  | 2013/07/12 |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Planning & Design | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Hardware / Software Procurement | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Readiness Validation | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Product Installation | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 | 2013/07/19 |  | 2013/07/22 |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Product Integration | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Training | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Consulting & Technical Reviews | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Support Turnover | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Project Closure | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Project Kick Off | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Planning & Design | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Readiness Validation | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Product Installation | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Product Integration | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Training | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Support Turnover | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Project Closure | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Project Kick Off | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/13 |  | 2013/08/19 | 2013/08/20 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Planning & Design | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/21 | 2013/08/21 | 2013/08/26 | 2013/09/10 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Hardware / Software Procurement | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/27 | 2013/08/27 | 2013/08/29 | 2013/09/02 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Readiness Validation | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/02 | 2013/09/10 | 2013/09/04 | 2013/09/19 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Product Installation | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/04 | 2013/09/19 | 2013/09/05 | 2013/09/19 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Product Integration | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 50 | 15100 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/06 | 2013/09/30 | 2013/10/11 | 2013/10/28 | John Randall | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Training | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/11/04 | 2013/11/04 | 2013/11/15 | 2013/11/15 | Tim Johnson | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/11/04 |  | 2013/12/13 | 2014/03/25 | Tim Johnson | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Support Turnover | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 50 | 15100 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2014/02/27 |  | 2014/03/21 | 2014/03/31 | John Randall | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Project Closure | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2014/02/07 |  | 2014/02/07 |  | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
State of Oregon - SO10565 - DP6409 Onsite Install | Project Kick Off | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/07/31 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Planning & Design | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/12 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Hardware / Software Procurement | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Product Installation | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/17 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Product Integration | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/17 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Project Closure | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 100 | 7200 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  | 2013/09/30 | 2013/09/19 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
AFNI - SO10571 - GM Install and Config | Project Kick Off | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  | 2013/07/29 | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Planning & Design | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Hardware / Software Procurement | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Readiness Validation | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Product Installation | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Consulting & Technical Reviews | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Support Turnover | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Project Closure | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 100 | 8500 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  | 2014/07/31 |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Project Kick Off | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Planning & Design | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Hardware / Software Procurement | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Readiness Validation | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Product Installation | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Product Integration | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Project Closure | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 100 | 19200 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  | 2013/11/29 | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Project Kick Off | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 |  | 2013/08/02 |  | 2013/08/02 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Planning & Design | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/05 |  | 2013/08/09 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Hardware / Software Procurement | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Readiness Validation | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/09 |  | 2013/08/15 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Product Installation | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/19 |  | 2013/08/21 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Product Integration | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 100 | 25500 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/21 |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Training | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/13 | 2014/02/03 | 2014/01/24 | 2014/02/21 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Consulting & Technical Reviews | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/13 |  | 2014/01/24 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Support Turnover | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/28 | 2014/02/28 | 2014/01/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Project Closure | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/28 | 2014/02/28 | 2014/01/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Stevens Communications - Kohls - SO10601 - Radware | Project Kick Off | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Planning & Design | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Readiness Validation | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Product Installation | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Product Integration | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Training | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Support Turnover | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Project Closure | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Project Kick Off | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Planning & Design | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  | 2013/07/26 |  | 2013/07/26 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Hardware / Software Procurement | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Readiness Validation | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Product Installation | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Product Integration | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Training | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Consulting & Technical Reviews | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 100 | 1600 | 0 | 0 | 2013/07/26 | 2013/07/29 | 2013/07/29 | 2013/07/29 | 2013/07/29 | 2013/07/31 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Support Turnover | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Project Closure | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  | 2013/07/29 |  | 2013/08/01 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Project Kick Off | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/02/01 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Planning & Design | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Readiness Validation | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  | 2013/07/15 |  | 2013/07/26 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Product Installation | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  | 2013/07/09 |  | 2013/02/15 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Product Integration | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Training | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Support Turnover | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 | 2013/08/13 |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Project Closure | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 100 | 6450 | 0 | 0 | 2013/08/06 | 2013/08/13 | 2013/08/13 |  | 2013/08/13 | 2013/08/13 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
CDW - CBeyond - SO10615 - oWFM | Project Kick Off | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 |  |  |  | 2013/08/29 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Planning & Design | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/16 |  | 2013/09/16 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Hardware / Software Procurement | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/16 |  | 2013/09/20 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Readiness Validation | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/20 |  | 2013/09/20 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Product Installation | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/23 | 2013/09/23 | 2013/09/27 | 2013/09/27 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Product Integration | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 75 | 17707.5 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/30 |  | 2013/10/31 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Training | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/10/21 | 2013/10/15 | 2013/10/23 | 2013/10/23 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/10/28 |  | 2013/11/01 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Support Turnover | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 25 | 5902.5 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/11/04 |  | 2013/11/04 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Project Closure | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/11/05 |  | 2013/11/11 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
MolDev - Methodist Hospital - SO10614 - Quest | Project Kick Off | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/08/26 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Planning & Design | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Hardware / Software Procurement | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Product Installation | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/12 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Project Closure | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Project Kick Off | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/19 | 2013/08/19 | 2013/08/19 | 2013/08/19 | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Planning & Design | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/22 | 2013/08/22 | 2013/08/26 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Hardware / Software Procurement | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/09 | 2013/08/09 | 2013/08/12 | 2013/08/13 | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Readiness Validation | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/27 | 2013/08/27 | 2013/08/27 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Product Installation | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/09 |  | 2013/09/27 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Product Integration | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 50 | 64775 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/09 |  | 2013/09/27 | 2013/09/27 | Tim Johnson | [7 empty] | True | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Training | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/07 |  | 2013/10/25 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Consulting & Technical Reviews | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/23 |  | 2013/09/30 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Support Turnover | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 50 | 64775 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/25 |  | 2013/10/25 | 2013/10/31 | Stewart Futcher | [7 empty] | True | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Project Closure | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/31 |  | 2013/10/31 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
MolDev - PepsiCo (California) - SO10561 - Quest | Project Kick Off | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Planning & Design | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Hardware / Software Procurement | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Product Installation | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Project Closure | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Project Kick Off | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Planning & Design | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Hardware / Software Procurement | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Readiness Validation | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Product Installation | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 | 2013/08/12 |  | 2013/08/16 |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Product Integration | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 | 2013/08/12 |  | 2013/08/16 | 2013/08/26 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Training | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Support Turnover | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Project Closure | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
Telus Comm - Access - SO10632 - WFM Training | Project Kick Off | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 |  |  |  | 2013/08/09 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Planning & Design | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 |  |  |  | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Training | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 100 | 2500 | 0 | 0 | 2013/08/09 | 2013/10/28 | 2013/10/28 |  | 2013/10/28 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Project Closure | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 | 2013/10/28 |  | 2013/10/28 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Project Kick Off | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/03 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Planning & Design | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Product Installation | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/10/24 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Project Closure | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
BBVA - SO10677 - Health Check | Project Kick Off | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/14 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Planning & Design | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Product Integration | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Project Closure | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 100 | 9000 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/28 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - Intl Weatlh Mgmt - SO10737 | Project Kick Off | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Planning & Design | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Hardware / Software Procurement | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Product Integration | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  | 2013/10/31 | 2013/09/17 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Project Closure | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/25 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
Charter - SO10692 - Recorders at Multiple Sites | Project Kick Off | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/09/10 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Planning & Design | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/10/16 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Hardware / Software Procurement | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/10/01 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Readiness Validation | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/11/29 | 2013/11/29 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Product Installation | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/13 | 2013/12/03 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Product Integration | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/13 | 2013/12/03 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Project Closure | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 100 | 56100 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/16 | 2013/12/31 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Project Kick Off | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/08/26 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Planning & Design | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/02 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Hardware / Software Procurement | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/02 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Product Installation | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/09 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Product Integration | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 100 | 7800 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Project Closure | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  | 2013/11/29 | 2013/12/20 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Project Kick Off | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/25 | 2013/09/25 | 2013/09/25 | 2013/09/25 | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Planning & Design | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/26 | 2013/09/26 | 2013/12/09 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Hardware / Software Procurement | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/26 | 2013/09/26 | 2013/12/09 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Readiness Validation | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/12/06 |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Product Installation | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/12/16 |  | 2013/12/16 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Product Integration | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 75 | 25638.75 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/01/27 |  | 2014/02/14 | 2014/02/26 | John Randall | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Training | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/02/17 |  | 2014/02/28 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/03 |  | 2014/03/14 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Support Turnover | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 25 | 8546.25 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/17 |  | 2014/03/17 | 2014/03/28 | John Randall | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Project Closure | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/17 |  | 2014/03/17 | 2014/03/28 | Tim Johnson | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
ACS - Xerox - SO10700 Health Check for Support Renewal | Project Kick Off | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Planning & Design | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  | 2013/09/24 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Product Installation | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 | 2013/09/27 |  | 2013/09/27 | 2013/09/27 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Project Closure | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal |  | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
Verint PMO Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Training | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 100 | 45500 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - September 2013 | Project Kick Off | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Planning & Design | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Readiness Validation | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Product Installation | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Product Integration | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Training | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Support Turnover | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Project Closure | Project Closure |  | 20300 | 0 | Kent Pylant | 100 | 20300 | 0 | 0 | 2013/09/01 | 2013/09/30 |  | 2013/09/02 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Training | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 100 | 21700 | 0 | 0 | 2013/10/01 | 2013/10/01 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Training | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 100 | 27912.5 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Training | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 100 | 3150 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - November 2013 | Project Kick Off | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Planning & Design | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Readiness Validation | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Product Installation | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Product Integration | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Training | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Support Turnover | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Project Closure | Project Closure |  | 16100 | 0 | Kent Pylant | 100 | 16100 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/10/28 | 2013/11/30 | 2013/11/30 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - December 2013 | Project Kick Off | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Planning & Design | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Readiness Validation | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Product Installation | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Product Integration | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Training | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Support Turnover | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Project Closure | Project Closure |  | 9100 | 0 | Kent Pylant | 100 | 9100 | 0 | 0 | 2013/12/01 | 2013/12/31 |  | 2013/12/02 | 2013/12/31 | 2013/12/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - September 2013 | Project Kick Off | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Planning & Design | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Readiness Validation | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Product Installation | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Product Integration | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Training | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Support Turnover | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Project Closure | Project Closure |  | 21393.75 | 0 | Kent Pylant | 100 | 21393.75 | 0 | 0 | 2013/09/01 | 2013/09/30 |  | 2013/09/02 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - November 2013 | Project Kick Off | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Planning & Design | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Readiness Validation | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Product Installation | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Product Integration | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Training | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Support Turnover | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Project Closure | Project Closure |  | 41606.25 | 0 | Kent Pylant | 100 | 41606.25 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/11/01 | 2013/11/30 | 2013/11/29 | Kent Pylant | [7 empty] | True | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Training | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 100 | 31150 | 0 | 0 | 2013/10/01 | 2013/10/31 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - December 2013 | Project Kick Off | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Planning & Design | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Readiness Validation | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Product Installation | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Product Integration | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Training | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Support Turnover | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Project Closure | Project Closure |  | 23362.5 | 0 | Kent Pylant | 100 | 23362.5 | 0 | 0 | 2013/12/01 | 2013/12/31 |  | 2013/12/02 | 2013/12/31 | 2013/12/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Project Kick Off | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2013/10/08 | 2013/10/08 | 2013/10/08 | 2013/10/08 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Planning & Design | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/03/07 | 2014/03/07 | 2014/03/10 | 2014/03/10 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Hardware / Software Procurement | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/02/17 | 2014/02/17 | 2014/02/21 | 2014/02/21 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Readiness Validation | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/03/24 | 2014/03/24 | 2014/03/27 | 2014/03/27 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Product Installation | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/01 | 2014/04/01 | 2014/04/04 | 2014/04/04 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Product Integration | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 75 | 70897.5 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/01 | 2014/04/01 | 2014/04/11 |  | Stewart Futcher | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Training | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/21 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Consulting & Technical Reviews | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/30 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Support Turnover | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 25 | 23632.5 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/05/30 |  | 2014/05/30 |  | Stewart Futcher | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Project Closure | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 |  |  | 2014/03/07 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Verint MAC Revenue - September 2013 | Project Kick Off | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Planning & Design | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Readiness Validation | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Product Installation | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Product Integration | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Training | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Support Turnover | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Project Closure | Project Closure |  | 900 | 0 | Kent Pylant | 100 | 900 | 0 | 0 | 2013/09/30 | 2013/09/30 |  | 2013/09/30 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Training | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - November 2013 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/10/28 | 2013/11/30 | 2013/12/02 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - December 2013 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 | 2013/12/01 | 2013/12/02 | 2013/12/31 | 2013/12/30 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
ADVANtel - Consumer Cellular - SO10736 | Project Kick Off | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Planning & Design | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Hardware / Software Procurement | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Readiness Validation | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Product Installation | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Product Integration | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 100 | 3200 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  | 2013/10/03 | 2013/10/07 | Tim Johnson | [7 empty] | True |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Training | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Consulting & Technical Reviews | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Support Turnover | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Project Closure | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
Siemens - Medstar - SO10746 | Project Kick Off | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/04 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Planning & Design | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/10 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Hardware / Software Procurement | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/24 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Product Installation | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 | 2013/10/04 |  | 2013/10/04 | 2013/10/15 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Project Closure | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/09/04 | 2013/10/07 | 2013/10/07 |  | 2013/10/07 | 2013/10/15 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Project Kick Off | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/08 |  | 2013/10/08 | 2013/10/09 | Tim Johnson | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Planning & Design | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/09 |  | 2013/10/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Hardware / Software Procurement | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/01 |  | 2013/10/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Readiness Validation | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/29 |  | 2013/10/30 | 2013/11/04 | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Product Installation | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/11/11 | 2013/11/11 | 2013/11/11 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Product Integration | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 17.66 | 4503.3 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/11/12 | 2013/11/11 | 2013/12/20 | 2013/12/17 | John Randall | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Training | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/03 |  | 2014/03/14 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/17 |  | 2014/03/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Support Turnover | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 82.34 | 20996.7 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Project Closure | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Project Kick Off | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Planning & Design | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/11 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Product Integration | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/11 | Philip Haskings | [7 empty] | False |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Project Closure | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 100 | 3200 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  | 2013/09/13 | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Innovation Group - SO10754 - oWFO | Project Kick Off | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/10/17 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Planning & Design | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/09/30 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Hardware / Software Procurement | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/09/20 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Readiness Validation | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/26 | 2013/09/30 | 2013/09/27 | 2013/09/30 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Product Installation | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/25 | 2013/09/30 | 2013/10/21 | 2013/10/20 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Product Integration | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 80 | 46640 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/26 | 2013/09/30 | 2013/10/31 | 2013/10/30 | John Randall | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Training | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/11/18 | 2013/11/18 | 2014/02/14 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Consulting & Technical Reviews | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/10/28 |  | 2013/11/15 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Support Turnover | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 20 | 11660 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2014/03/31 |  | 2014/03/31 | 2014/03/28 | John Randall | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Project Closure | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2014/01/06 |  | 2014/01/06 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Project Kick Off | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/16 | 2013/09/16 | 2013/09/17 | 2013/09/17 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Planning & Design | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/23 | 2013/09/24 | 2013/10/04 | 2013/10/04 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Hardware / Software Procurement | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/23 | 2013/09/23 | 2013/09/23 | 2013/09/24 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Readiness Validation | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/04 | 2013/10/04 | 2013/10/04 | 2013/10/07 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Product Installation | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/07 | 2013/10/07 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Product Integration | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/07 | 2013/10/07 | 2013/10/25 | 2013/10/25 | Stewart Futcher | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Training | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 100 | 62400 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Consulting & Technical Reviews | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/12/20 | 2014/10/30 | Tim Johnson | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Support Turnover | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/11/23 | 2014/02/19 | Stewart Futcher | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Project Closure | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/12/30 | 2014/02/19 | Stewart Futcher | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Project Kick Off | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Planning & Design | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Hardware / Software Procurement | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Readiness Validation | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/21 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Product Installation | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/28 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Product Integration | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 75 | 6675 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Training | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Consulting & Technical Reviews | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Support Turnover | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 25 | 2225 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Project Closure | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Project Kick Off | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Planning & Design | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Hardware / Software Procurement | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Readiness Validation | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Product Installation | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Product Integration | 7 - Training |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/29 | Stewart Futcher | [7 empty] | True |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Training | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Consulting & Technical Reviews | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Support Turnover | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Project Closure | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/29 | Tim Johnson | [7 empty] | True |  | 10703 | 7700241820 | 2013/09/11 | False
ACCC Insurance Co - SO10741 - oWFM | Project Kick Off | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  | 2014/02/20 | Philip Haskings | [7 empty] | True | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Planning & Design | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Hardware / Software Procurement | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Readiness Validation | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Product Installation | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Product Integration | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 100 | 25500 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  | 2014/05/02 |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Training | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Consulting & Technical Reviews | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Support Turnover | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Project Closure | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  | 2013/12/31 |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Project Kick Off | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Planning & Design | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Readiness Validation | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Product Installation | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Product Integration | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Training | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Support Turnover | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Project Closure | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/09 | 2013/10/09 | 2013/10/09 | 2013/10/09 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/21 | 2013/10/21 | 2013/10/31 | 2013/11/08 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/14 | 2013/10/14 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Readiness Validation | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/06 | 2013/11/08 | 2013/11/08 | 2013/11/12 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Product Installation | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/04 | 2013/11/04 | 2013/11/29 | 2013/11/29 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Product Integration | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 75 | 44400 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/04 | 2013/11/04 | 2013/12/13 | 2013/12/17 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Training | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/03/03 | 2014/03/03 | 2014/03/07 | 2014/03/07 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/03/03 | 2014/03/03 | 2014/04/25 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 25 | 14800 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/04/25 |  | 2014/04/25 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Project Closure | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/04/28 |  | 2014/04/28 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Project Kick Off | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/01 | 2013/09/19 | 2013/10/01 | 2013/09/19 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Planning & Design | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/09/25 |  | 2013/09/25 | 2013/10/01 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Hardware / Software Procurement | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/01 | 2013/09/19 | 2013/10/01 | 2013/09/20 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Readiness Validation | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/14 | 2013/10/17 | 2013/10/14 | 2013/10/17 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Product Installation | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/21 | 2013/10/18 | 2013/10/25 | 2013/10/22 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Product Integration | Project Closure |  | 46400 | 54740 | Philip Haskings | 66 | 30624 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/28 |  | 2013/11/01 | 2013/11/06 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Training | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/11/12 |  | 2013/11/21 | 2014/03/05 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Consulting & Technical Reviews | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/11 |  | 2013/12/11 | 2014/03/05 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Support Turnover | Project Closure |  | 46400 | 54740 | Philip Haskings | 34 | 15776 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/13 |  | 2014/02/07 | 2014/02/21 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Project Closure | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/16 |  | 2013/12/16 | 2014/03/11 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Readiness Validation | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Product Installation | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Training | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Consulting & Technical Reviews | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Support Turnover | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/16 | 2013/09/16 | 2013/09/16 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/17 | 2013/09/17 | 2013/09/17 | 2013/09/17 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/18 | 2013/09/18 | 2013/09/18 | 2013/09/18 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Planning & Design | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 |  | 2013/09/20 |  | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Project Kick Off | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/10/01 | 2013/09/20 | 2013/10/01 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Product Installation | Project Closure |  | 4700 | 4700 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/09/09 |  | 2013/09/24 | 2013/09/24 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Project Closure | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/10/31 |  | 2013/10/31 | 2013/09/25 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Nissan - SO10758 - Remote Services | Project Kick Off | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Planning & Design | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Product Integration | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Project Closure | Project Closure |  | 2200 | 0 | Philip Haskings | 100 | 2200 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Project Kick Off | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/10/07 | 2013/10/10 | 2013/10/10 | 2013/10/10 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/29 | 2013/11/18 | 2013/11/29 | 2013/11/29 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/25 | 2013/11/25 | 2013/11/25 | 2014/02/28 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Readiness Validation | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/04 | 2013/11/06 | 2013/11/15 | 2014/01/01 | Stewart Futcher | Testing by Adam | Billable | 2014/04/23 | 2014/04/23 | 5.2 | Libby Lasseigne | Adam Ip | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Product Installation | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/12/09 | 2013/12/09 | 2013/12/27 | 2013/12/27 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Product Integration | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 40 | 77384 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/12/09 | 2013/12/09 | 2014/04/18 |  | Stewart Futcher | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Training | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/02/10 | 2014/02/10 | 2014/02/21 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/02/10 | 2014/02/10 | 2014/02/10 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Support Turnover | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/05/01 |  | 2014/05/30 |  | Stewart Futcher | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Project Closure | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/05/05 |  | 2014/05/05 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Project Kick Off | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Planning & Design | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 | 2014/03/24 | 2014/03/24 | 2014/04/01 | 2014/04/01 | Kent Pylant | [7 empty] | True | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Readiness Validation | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Product Installation | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Product Integration | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 100 | 11300 | 0 | 0 | 2014/03/24 | 2014/04/25 | 2014/04/21 |  | 2014/04/25 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Training | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Support Turnover | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  | 2014/07/01 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Project Closure | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Region of York - SO11390 TOM Addition | Project Kick Off | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Planning & Design | Project Closure |  | 500 | 500 | John Randall | 25 | 125 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Hardware / Software Procurement | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Readiness Validation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Product Installation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Product Integration | Project Closure |  | 500 | 500 | John Randall | 50 | 250 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Training | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Consulting & Technical Reviews | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Support Turnover | Project Closure |  | 500 | 500 | John Randall | 25 | 125 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Project Closure | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Project Kick Off | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Planning & Design | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 25 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/05/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Hardware / Software Procurement | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Readiness Validation | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Product Installation | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Product Integration | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 50 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/06/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Training | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Support Turnover | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 25 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/07/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Project Closure | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
QT11192 Pearson Education Support | Project Kick Off | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Planning & Design | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 25 | 1000 | 0 | 0 |  |  |  |  | 2014/05/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Hardware / Software Procurement | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Readiness Validation | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Product Installation | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Product Integration | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 50 | 1000 | 0 | 0 |  |  |  |  | 2014/06/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Training | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Consulting & Technical Reviews | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Support Turnover | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 25 | 1000 | 0 | 0 |  |  |  |  | 2014/07/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Project Closure | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Project Kick Off | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Hardware / Software Procurement | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Product Integration | 1 - Project Kick Off |  | 250 | 250 | John Randall | 100 | 250 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  | 2014/06/03 |  | John Randall | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Project Closure | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Flagstar l PS support l 4 days | Project Kick Off | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Planning & Design | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 25 | 10800 | 0 | 0 |  |  |  |  | 2014/05/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Hardware / Software Procurement | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Readiness Validation | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Product Installation | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Product Integration | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 50 | 10800 | 0 | 0 |  |  |  |  | 2014/06/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Training | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Consulting & Technical Reviews | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Support Turnover | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 25 | 10800 | 0 | 0 |  |  |  |  | 2014/07/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Project Closure | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Project Kick Off | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Planning & Design | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 25 | 9100 | 0 | 0 |  |  |  |  | 2014/05/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Hardware / Software Procurement | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Readiness Validation | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Product Installation | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Product Integration | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 50 | 9100 | 0 | 0 |  |  |  |  | 2014/06/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Training | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Consulting & Technical Reviews | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Support Turnover | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 25 | 9100 | 0 | 0 |  |  |  |  | 2014/07/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Project Closure | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Project Kick Off | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Planning & Design | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  | 2014/05/09 |  | Philip Haskings | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Product Integration | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  | 2014/06/09 |  | Philip Haskings | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Project Closure | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
Wells Fargo - SO11619 - Remote Training | Project Kick Off | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Planning & Design | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 50 | 2700 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  | 2014/04/18 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Hardware / Software Procurement | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Readiness Validation | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Training | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 50 | 2700 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  | 2014/05/16 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Project Closure | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Project Kick Off | Project Closure |  | 500 | 500 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/19 | 2014/01/31 |  | 2013/12/20 |  | 2013/12/20 | Tim Johnson | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Product Installation | Project Closure |  | 500 | 500 | Charlene Dennis | 100 | 500 | 0 | 0 | 2013/12/19 | 2014/01/31 |  | 2014/01/08 | 2014/01/31 | 2014/01/08 | Charlene Dennis | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Project Closure | Project Closure |  | 500 | 500 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/19 | 2014/01/31 |  |  |  | 2014/01/10 | Tim Johnson | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Project Kick Off | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Planning & Design | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Hardware / Software Procurement | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Readiness Validation | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Product Installation | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Product Integration | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 100 | 8900 | 0 | 0 | 2013/12/17 | 2014/07/31 | 2014/06/16 |  | 2014/07/25 |  | Philip Haskings | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Training | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Consulting & Technical Reviews | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Support Turnover | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Project Closure | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Apple - SO11312 - Onsite Services | Project Kick Off | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Hardware / Software Procurement | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Product Installation | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  | 2013/12/20 | 2013/12/19 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Consulting & Technical Reviews | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/19 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Project Closure | Project Closure |  | 8000 | 8000 | Philip Haskings | 100 | 8000 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  | 2013/12/27 | 2013/12/31 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
USG - SO11375 - SKY oWFO - 130 Seats | Project Kick Off | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/01/14 |  | 2014/01/14 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Planning & Design | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/01/15 |  | 2014/01/31 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Hardware / Software Procurement | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Readiness Validation | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Product Installation | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/02/10 | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Product Integration | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 100 | 39300 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/02/28 | 2014/02/28 | 2014/04/28 |  | Charlene Dennis | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Training | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/03/10 | 2014/03/10 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Consulting & Technical Reviews | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Support Turnover | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Project Closure | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
HireRight - SO11385 - SSO Implementation | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Training | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
Verint PMO Revenue - May 2014 | Project Kick Off | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Planning & Design | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Hardware / Software Procurement | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Readiness Validation | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Product Installation | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Product Integration | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Training | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Consulting & Technical Reviews | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Support Turnover | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Project Closure | Project Closure |  | 3500 | 3500 | Kent Pylant | 100 | 3500 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Project Kick Off | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Planning & Design | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Readiness Validation | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Product Installation | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Product Integration | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Training | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Support Turnover | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Project Closure | Project Closure |  | 1400 | 1400 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Project Kick Off | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/03/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Planning & Design | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Hardware / Software Procurement | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Readiness Validation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Product Installation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Product Integration | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/06 | 2014/04/30 | 2014/05/31 |  | 2014/05/31 |  | John Randall | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Training | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Consulting & Technical Reviews | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Support Turnover | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Project Closure | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Project Kick Off | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/02/18 |  | 2014/02/18 | Tim Johnson | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Planning & Design | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 25 | 6975 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/21 | 2014/03/21 | 2014/03/28 | Charlene Dennis | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Hardware / Software Procurement | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/07 |  | 2014/04/09 | Tim Johnson | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Readiness Validation | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/07 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Product Installation | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/04/14 |  |  |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Product Integration | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 50 | 13950 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/04/28 |  | 2014/04/30 |  | Charlene Dennis | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Training | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/06 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Consulting & Technical Reviews | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/12 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Support Turnover | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 25 | 6975 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/26 |  | 2014/05/26 |  | Charlene Dennis | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Project Closure | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/26 |  | 2014/05/26 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Project Kick Off | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/01/14 |  | 2014/01/14 | Charlene Dennis | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Planning & Design | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 25 | 20391.25 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/02/07 | 2014/02/28 | 2014/02/28 | Charlene Dennis | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Hardware / Software Procurement | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/03/04 |  | 2014/03/06 | Tim Johnson | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Readiness Validation | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/03/07 |  | 2014/03/07 | Tim Johnson | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Product Installation | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/03/17 |  | 2014/05/15 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Product Integration | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 50 | 40782.5 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/03/15 |  | 2014/05/15 |  | Charlene Dennis | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Training | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/04/07 |  | 2014/03/21 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Consulting & Technical Reviews | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/05/23 |  | 2014/05/23 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Support Turnover | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 25 | 20391.25 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/06/04 |  | 2014/07/11 |  | Charlene Dennis | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Project Closure | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/06/04 |  | 2014/06/04 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Project Kick Off | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/01/09 |  | 2014/01/09 | Charlene Dennis | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Planning & Design | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/02/19 |  | 2014/02/19 | Tim Johnson | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Product Integration | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 100 | 4800 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/02/22 | 2014/02/24 | 2014/02/24 | Charlene Dennis | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Project Closure | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  |  |  | 2014/03/05 | Tim Johnson | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11350 - Change order for Campaign Changes | Project Kick Off | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Planning & Design | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Hardware / Software Procurement | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Readiness Validation | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Product Installation | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Product Integration | 7 - Training |  | 1800 | 1800 | Tim Johnson | 100 | 1800 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  | 2014/01/07 | 2014/01/07 | Tim Johnson | [7 empty] | True | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Training | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Consulting & Technical Reviews | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Support Turnover | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Project Closure | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Project Kick Off | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/02/20 | Philip Haskings | [7 empty] | True | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Planning & Design | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/02/25 | Philip Haskings | [7 empty] | True | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Hardware / Software Procurement | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Readiness Validation | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Product Installation | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Product Integration | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Training | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Consulting & Technical Reviews | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Support Turnover | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 100 | 32400 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  | 2014/05/30 |  | Philip Haskings | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Project Closure | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
HSBC - PM - June 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  | 2014/06/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Project Kick Off | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/03/31 | Tim Johnson | [7 empty] | True | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Planning & Design | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Hardware / Software Procurement | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Readiness Validation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Product Installation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Product Integration | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/06 | 2014/04/30 | 2014/05/31 |  | 2014/05/31 |  | John Randall | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Training | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Consulting & Technical Reviews | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Support Turnover | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Project Closure | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
Vanguard SO11382 - PS custom data | Project Kick Off | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Planning & Design | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Hardware / Software Procurement | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Readiness Validation | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Product Installation | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Product Integration | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Training | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Consulting & Technical Reviews | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Support Turnover | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Project Closure | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 100 | 3900 | 0 | 0 | 2014/01/20 | 2014/01/28 | 2014/01/20 | 2014/01/20 | 2014/01/21 | 2014/01/28 | Tim Johnson | [7 empty] | True | Steven Smith |  | 1 | 2014/01/06 | False
MedImpact - SO11345 - License Adds | Project Kick Off | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Planning & Design | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Hardware / Software Procurement | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Readiness Validation | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Product Installation | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Product Integration | Project Closure |  | 800 | 0 | Stewart Futcher | 100 | 800 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  | 2014/01/31 | 2014/01/28 | Stewart Futcher | [7 empty] | True | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Training | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Consulting & Technical Reviews | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Support Turnover | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Project Closure | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  | 2014/01/31 | Stewart Futcher | [7 empty] | True | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
Toyota Canada, Inc. - SO10414 v11 Project | Project Kick Off | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/10 | 2013/06/10 | 2013/06/10 | 2013/06/11 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Planning & Design | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/17 | 2013/06/17 | 2013/06/28 | 2013/06/28 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Hardware / Software Procurement | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/14 | 2013/06/14 | 2013/06/17 | 2013/06/17 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Readiness Validation | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/08 | 2013/07/08 | 2013/07/09 | 2013/07/09 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Product Installation | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/15 | 2013/07/15 | 2013/07/26 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Product Integration | Project Closure |  | 31300 | 0 | Stewart Futcher | 100 | 31300 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/15 | 2013/07/15 | 2013/08/30 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Training | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/16 |  | 2013/09/20 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Consulting & Technical Reviews | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/08/19 | 2013/08/19 | 2013/08/26 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Support Turnover | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/17 |  | 2013/09/17 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Project Closure | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/23 |  | 2013/09/23 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Molecular Devices - SO10201 - Germany - Quest System | Project Kick Off | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Planning & Design | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Hardware / Software Procurement | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Product Installation | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Product Integration | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Project Closure | Project Closure |  | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | [5 empty] | 2013/07/19 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Project Kick Off | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Planning & Design | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Hardware / Software Procurement | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Readiness Validation | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Product Installation | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Product Integration | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Project Closure | Project Closure |  | 6400 | 0 | Philip Haskings | 100 | 6400 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Project Kick Off | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Planning & Design | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Hardware / Software Procurement | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/25 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Product Installation | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/25 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Project Closure | Project Closure |  | 750 | 0 | Philip Haskings | 100 | 750 | 0 | 0 | [5 empty] | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Project Kick Off | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/06/24 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Planning & Design | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  | 2013/07/22 |  | 2013/07/03 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Hardware / Software Procurement | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/03 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Product Installation | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Project Closure | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 100 | 750 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
CDW - AFNI - SO10447 - License Moves | Project Kick Off | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Planning & Design | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Hardware / Software Procurement | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Product Integration | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/08/21 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Project Closure | Project Closure |  | 950 | 0 | Philip Haskings | 100 | 950 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  | 2013/09/30 | 2013/08/21 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Project Kick Off | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  |  | 2013/06/21 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Planning & Design | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  |  | 2013/07/31 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Product Installation | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 | 2013/08/22 |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Project Closure | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 4800 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  | 2013/09/10 | 2013/09/10 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Molecular Devices - SO10431 - Research 10 California | Project Kick Off | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Planning & Design | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  |  |  | 2013/07/09 |  | 2013/07/12 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/09 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Product Installation | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Product Integration | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Project Closure | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Project Kick Off | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/13 | 2014/01/13 | 2014/01/14 | 2014/04/08 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Planning & Design | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/20 | 2014/01/20 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Hardware / Software Procurement | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/27 | 2014/01/27 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Readiness Validation | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/27 | 2014/01/28 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Product Installation | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/02/17 | 2014/02/17 | 2014/02/21 | 2014/02/21 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Product Integration | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 60 | 53250 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/02/10 | 2014/03/10 | 2014/02/21 | 2014/02/28 | Stewart Futcher | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Training | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 20 | 17750 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/04/28 |  | 2014/05/02 |  | Stewart Futcher | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Consulting & Technical Reviews | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/05/09 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Support Turnover | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 20 | 17750 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/05/02 |  | 2014/05/09 |  | Stewart Futcher | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Project Closure | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
HSBC - PM - April 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  | 2014/04/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
CMS Medicare Phase II - Cluster 2 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  | 2013/12/17 | 2013/12/23 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
HSBC - PM - May 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  | 2014/05/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  | 2013/12/09 |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  | 2014/01/31 | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  |  | 2013/12/16 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
VWR - SO11215 - 350 seats of OWFM SKY | Project Kick Off | Project Closure |  | 50786 | 50786 | Philip Haskings | 33 | 16759.38 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Planning & Design | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Hardware / Software Procurement | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Readiness Validation | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 |  | Philip Haskings | [7 empty] | False | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Product Installation | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/01/24 |  | Philip Haskings | [7 empty] | False | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Product Integration | Project Closure |  | 50786 | 50786 | Philip Haskings | 33 | 16759.38 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/03 | 2014/02/27 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Training | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/02/07 | 2014/02/07 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Consulting & Technical Reviews | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 | 2014/03/06 |  | 2014/03/06 | 2014/03/07 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Support Turnover | Project Closure |  | 50786 | 50786 | Philip Haskings | 34 | 17267.24 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/12 | 2014/03/12 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Project Closure | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/14 | 2014/03/13 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
CMS Medicare Phase II - Cluster 3 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  | 2014/01/03 | 2014/01/15 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2014/01/13 | 2014/01/23 | 2014/01/03 | 2014/01/03 | 2014/01/23 | 2014/01/31 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  | 2014/02/18 | 2014/02/27 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  | 2013/11/27 | 2013/11/25 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
BBVA - SO11207 - Remote License Adds | Project Kick Off | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/02 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Planning & Design | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Product Integration | Project Closure |  | 4200 | 0 | Philip Haskings | 100 | 4200 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  | 2014/01/31 | 2013/12/12 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Project Closure | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/16 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Project Kick Off | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Planning & Design | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Hardware / Software Procurement | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Readiness Validation | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Product Installation | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Product Integration | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/04 | 2013/12/06 | Tim Johnson | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Training | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Consulting & Technical Reviews | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/04 | 2013/12/09 | 2013/12/06 | 2013/12/18 | Tim Johnson | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Support Turnover | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Project Closure | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 100 | 5400 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/06 | 2013/12/10 | 2013/12/10 | 2013/12/11 | Kent Pylant | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Project Kick Off | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2013/12/16 | 2013/12/17 | 2013/12/16 | 2013/12/17 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Planning & Design | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/06 | 2014/01/06 | 2014/01/06 | 2014/01/24 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Hardware / Software Procurement | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/13 | 2014/01/14 | 2014/01/13 | 2014/01/14 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Readiness Validation | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/20 | 2014/01/21 | 2014/01/20 | 2014/01/22 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Product Installation | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/20 | 2014/01/20 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Product Integration | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 100 | 71300 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  | 2014/01/31 | 2014/01/28 | Stewart Futcher | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Training | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/03/24 | 2014/03/24 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Consulting & Technical Reviews | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Support Turnover | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/24 |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Project Closure | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/25 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/01/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/01/14 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  | 2014/04/25 | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Project Kick Off | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Planning & Design | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Hardware / Software Procurement | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Readiness Validation | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Product Installation | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Product Integration | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Training | Project Closure |  | 3600 | 0 | John Randall | 100 | 3600 | 0 | 0 | 2013/12/02 | 2014/02/05 | 2014/02/04 |  | 2014/02/05 | 2014/02/12 | John Randall | [7 empty] | True | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Consulting & Technical Reviews | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Support Turnover | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Project Closure | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 | 2014/02/05 |  | 2014/02/05 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Project Kick Off | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 | 2013/12/10 |  |  | 2013/12/16 | Tim Johnson | [7 empty] | True | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Planning & Design | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Hardware / Software Procurement | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Readiness Validation | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Product Installation | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Product Integration | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 100 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  | 2014/02/28 |  | Charlene Dennis | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Training | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Support Turnover | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Project Closure | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Project Kick Off | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Planning & Design | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 25 | 30505 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/02/21 | 2014/02/25 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Hardware / Software Procurement | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/03/14 | 2014/03/14 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Readiness Validation | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/03/28 | 2014/03/28 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Product Installation | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/03/31 | 2014/03/31 | 2014/04/04 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Product Integration | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 50 | 61010 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Training | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/04/28 |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Consulting & Technical Reviews | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/06/11 |  | 2014/06/11 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Support Turnover | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 25 | 30505 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/06/16 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Project Closure | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/06/20 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Project Kick Off | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2013/12/04 |  | 2013/12/11 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Planning & Design | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2013/12/16 | 2013/12/23 | 2013/12/30 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Product Installation | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/01/24 |  | 2014/02/27 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Product Integration | Project Closure |  | 6400 | 0 | Charlene Dennis | 100 | 6400 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/01/27 | 2014/02/28 | 2014/01/27 | Charlene Dennis | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Project Closure | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/02/24 |  | 2014/02/24 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Project Kick Off | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Planning & Design | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Hardware / Software Procurement | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/07 |  | 2013/10/10 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Product Integration | Project Closure |  | 3700 | 3700 | Philip Haskings | 100 | 3700 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/11 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Project Closure | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Project Kick Off | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Planning & Design | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Hardware / Software Procurement | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Product Integration | Project Closure |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/11 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Project Closure | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
CDW - Laureate - SO10850 - AIM Configuration | Project Kick Off | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Planning & Design | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Hardware / Software Procurement | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Readiness Validation | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Product Installation | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Product Integration | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Training | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Consulting & Technical Reviews | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Support Turnover | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Project Closure | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 100 | 8000 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/30 | Stewart Futcher | [7 empty] | True |  | 10850 | 00003-0000016265 | 2013/09/27 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Project Kick Off | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Planning & Design | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Hardware / Software Procurement | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Readiness Validation | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Product Installation | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/05/12 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Product Integration | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 100 | 25500 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/06/30 |  | 2014/06/30 |  | John Randall | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Training | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/03/31 |  | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Consulting & Technical Reviews | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Support Turnover | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/28 |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Project Closure | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/28 |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Project Kick Off | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 | 2013/10/24 | 2013/10/24 | 2013/10/24 | 2013/10/24 | Tim Johnson | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Planning & Design | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 30 | 26649 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Hardware / Software Procurement | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2013/11/29 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Readiness Validation | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2013/12/03 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Product Installation | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 20 | 17766 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Product Integration | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 30 | 26649 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Training | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Consulting & Technical Reviews | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/24 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Support Turnover | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 20 | 17766 | 0 | 0 | 2013/09/30 | 2014/01/31 | 2014/04/30 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Project Closure | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/02/03 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Project Kick Off | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Planning & Design | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Hardware / Software Procurement | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/15 | 2013/10/15 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Readiness Validation | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/15 | 2013/10/15 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Product Installation | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/15 | 2013/10/15 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Product Integration | Project Closure |  | 4000 | 4000 | Stewart Futcher | 100 | 4000 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Training | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/15 | 2013/10/15 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Consulting & Technical Reviews | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/16 | 2013/10/17 | 2013/10/17 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Support Turnover | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/18 | 2013/10/18 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Project Closure | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 |  |  |  |  | Tim Johnson | [7 empty] | False | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Project Kick Off | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Planning & Design | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Hardware / Software Procurement | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Readiness Validation | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Product Installation | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Product Integration | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Training | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Consulting & Technical Reviews | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Support Turnover | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Project Closure | Project Closure |  | 3200 | 5700 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2013/09/30 | 2013/10/31 | 2013/10/07 | 2013/10/07 | 2013/10/31 | 2013/10/31 | Stewart Futcher | [7 empty] | True | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Project Kick Off | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 |  |  |  | 2013/10/03 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Planning & Design | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 |  |  | 2013/10/11 | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Product Installation | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 | 2013/11/15 |  | 2013/11/18 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Project Closure | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2013/10/30 |  | 2013/11/14 | 2013/11/15 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Product Installation | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2013/11/18 |  | 2013/11/22 | 2013/11/19 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Product Integration | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 100 | 21069 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Training | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/03/31 |  | 2014/04/04 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/04/11 |  | 2014/04/11 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/04/18 |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Project Closure | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA -SO10893 - Services_HUB Recovery Project | Project Kick Off | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 |  |  | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Planning & Design | Project Closure |  | 8700 | 8700 | Philip Haskings | 100 | 8700 | 0 | 0 | 2013/10/01 | 2013/10/14 |  |  | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Consulting & Technical Reviews | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Project Closure | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
HSBC PM - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Planning & Design | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Product Installation | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Product Integration | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Training | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Support Turnover | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Project Closure | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 100 | 20160 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  | 2013/08/31 | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - PM - September 2013 | Project Kick Off | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Planning & Design | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Readiness Validation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Product Installation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Product Integration | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Training | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Support Turnover | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Project Closure | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 100 | 19200 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Planning & Design | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Product Installation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Product Integration | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Training | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Support Turnover | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Project Closure | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 100 | 19200 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - November 2013 | Project Kick Off | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Planning & Design | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Readiness Validation | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Product Installation | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Product Integration | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Training | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Support Turnover | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Project Closure | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 100 | 13440 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  | 2013/11/29 | 2013/11/27 | Matt Hogan | [7 empty] | True |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - December 2013 | Project Kick Off | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Planning & Design | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Readiness Validation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Product Installation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Product Integration | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Training | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Support Turnover | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Project Closure | Project Closure |  | 17280 | 0 | Matt Hogan | 100 | 17280 | 0 | 0 | 2013/12/01 | 2013/12/31 | 2013/12/01 | 2013/12/01 | 2013/12/31 | 2013/12/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - September 2013 | Project Kick Off | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Planning & Design | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Readiness Validation | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Product Installation | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Product Integration | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Training | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Support Turnover | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Project Closure | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 100 | 20672 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Planning & Design | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Product Installation | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Product Integration | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Training | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Support Turnover | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Project Closure | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 100 | 23936 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  | 2013/08/31 | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Flagstar - SO10909 - Health Check and SSL services | Project Kick Off | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  |  | 2013/10/01 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Planning & Design | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/10/23 | 2013/10/23 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Hardware / Software Procurement | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/01 | 2014/02/28 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Product Installation | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/04 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Product Integration | Project Closure |  | 12800 | 12800 | Philip Haskings | 100 | 12800 | 0 | 0 | 2013/10/04 | 2014/03/28 | 2014/03/10 |  | 2014/03/14 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Project Closure | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/11 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
HSBC - Admin - October 2013 | Project Kick Off | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Planning & Design | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Hardware / Software Procurement | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Readiness Validation | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Product Installation | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Product Integration | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Training | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Consulting & Technical Reviews | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Support Turnover | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Project Closure | Project Closure |  | 23392 | 0 | Tim Johnson | 100 | 23392 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - November 2013 | Project Kick Off | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Planning & Design | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Hardware / Software Procurement | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Readiness Validation | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Product Installation | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Product Integration | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Training | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Consulting & Technical Reviews | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Support Turnover | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Project Closure | Project Closure |  | 20672 | 0 | Tim Johnson | 100 | 20672 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/27 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - December 2013 | Project Kick Off | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Planning & Design | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Hardware / Software Procurement | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Readiness Validation | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Product Installation | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Product Integration | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Training | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Consulting & Technical Reviews | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Support Turnover | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Project Closure | Project Closure |  | 17680 | 0 | Tim Johnson | 100 | 17680 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Project Kick Off | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/09/16 | 2013/09/16 | 2013/09/16 | 2013/09/16 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Planning & Design | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/07 | 2013/10/07 | 2013/10/11 | 2013/10/11 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Hardware / Software Procurement | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/14 | 2013/10/14 | 2013/10/14 | 2013/10/15 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Readiness Validation | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/08 | 2013/10/08 | 2013/10/09 | 2013/10/09 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Product Installation | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/21 | 2013/10/21 | 2013/11/08 | 2013/11/08 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Product Integration | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/21 | 2013/10/21 | 2013/11/29 | 2013/11/19 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Training | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/20 |  | Stewart Futcher | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Consulting & Technical Reviews | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/23 |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Support Turnover | Project Closure |  | 71000 | 79000 | Stewart Futcher | 100 | 71000 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/23 | 2013/12/20 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Project Closure | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2014/01/03 |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Laureate/Adviceline | Project Kick Off | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Planning & Design | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Readiness Validation | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Product Installation | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Product Integration | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Training | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Support Turnover | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Project Closure | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
NGS | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Product Installation | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Product Integration | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Training | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Project Closure | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Project Kick Off | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2013/12/20 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Planning & Design | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2013/12/24 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Hardware / Software Procurement | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Product Installation | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 | 2014/01/20 |  | 2014/01/21 | 2014/02/26 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Product Integration | 7 - Training |  | 4700 | 4700 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Project Closure | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  | 2014/01/31 |  | Philip Haskings | [7 empty] | False | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
MolDev - SO10939 - Research 10 - Europe | Project Kick Off | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Planning & Design | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Hardware / Software Procurement | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Product Installation | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 | 2013/12/12 |  | 2013/12/13 | 2013/12/12 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Project Closure | Project Closure |  | 3175 | 3295 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
Xerox - SO10936 - Wellness Check | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  |  | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
Xerox - SO10936 - Wellness Check | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
Xerox - SO10936 - Wellness Check | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/22 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Project Kick Off | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/08/24 | 2012/08/24 | 2012/08/24 | 2012/08/29 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Planning & Design | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/08/27 | 2012/08/27 | 2012/09/21 | 2012/09/28 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Hardware / Software Procurement | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/10/01 | 2012/10/05 | 2012/11/02 | 2012/11/26 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Readiness Validation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/12/10 | 2012/12/10 | 2012/12/12 | 2012/12/17 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Product Installation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/12/17 | 2012/12/17 | 2012/12/21 | 2012/12/21 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Product Integration | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2013/01/07 | 2013/01/07 | 2013/01/11 | 2013/01/14 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Training | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Consulting & Technical Reviews | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Support Turnover | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  | 2013/02/11 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Project Closure | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | QM v11 Implementation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 100 | 7410 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2013/01/07 | 2013/01/07 | 2013/01/11 | 2013/01/11 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Project Kick Off | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/10/09 | 2012/10/09 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Planning & Design | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Hardware / Software Procurement | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Readiness Validation | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/13 | 2012/11/13 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Product Installation | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Product Integration | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 100 | 17400 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/19 | 2012/11/19 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Training | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Consulting & Technical Reviews | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Support Turnover | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Project Closure | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/26 | 2012/11/27 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/08/09 | 2012/08/09 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/08/16 | 2012/08/24 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/18 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/31 |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Project Kick Off | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Planning & Design | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/26 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Hardware / Software Procurement | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/25 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Readiness Validation | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/11/15 | 2012/11/15 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Product Installation | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/29 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Product Integration | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 100 | 4700 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/11/27 | 2012/11/27 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Training | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Consulting & Technical Reviews | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/31 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Support Turnover | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Project Closure | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/31 | 2012/11/29 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
CDW - State Auto Insurance - SO8515 | State Auto v11 WFO | Project Closure |  | 26000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/09/21 |  |  | 2012/09/11 | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 8515 | 00003-0000011329
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/24 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/31 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/09 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Nike - SO9425 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/26 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Project Kick Off | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 50 | 3900 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/29 | 2012/10/16 | Stewart Futcher | [7 empty] | True |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Planning & Design | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Hardware / Software Procurement | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Readiness Validation | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Product Installation | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Product Integration | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Training | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Consulting & Technical Reviews | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Support Turnover | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Project Closure | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 100 | 7800 | 0 | 0 | 2012/10/24 | 2012/11/30 | 2012/11/12 | 2012/11/13 | 2012/11/16 | 2012/11/26 | Stewart Futcher | [7 empty] | True |  | 9424 | #
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Project Kick Off | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/07 | 2013/01/07 | 2013/01/07 | 2013/01/07 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Planning & Design | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/14 | 2013/01/14 | 2013/01/25 | 2013/01/31 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Hardware / Software Procurement | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/31 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Readiness Validation | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/21 | 2012/10/18 | 2012/10/18 | 2012/10/18 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Product Installation | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 38.5 | 77385 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/28 | 2013/01/21 | 2013/02/15 | 2013/02/15 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Product Integration | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/28 | 2013/01/21 | 2013/02/15 | 2013/02/15 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Training | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/07/08 | 2013/07/08 | 2013/07/19 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Consulting & Technical Reviews | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/07/08 | 2013/07/08 | 2013/08/23 | 2013/08/23 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Support Turnover | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/08/30 |  | 2013/08/30 |  | Stewart Futcher | [7 empty] | False | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Project Closure | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 69.26 | 139212.6 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/09/13 |  | 2013/09/30 | 2013/09/30 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Bluewater - Webster Bank - SO8981 v11 w/AET | Webster Bank - SO8981 | Project Closure |  | 28800 | 0 | Stewart Futcher | 100 | 28800 | 0 | 0 | 2012/08/14 | 2012/09/28 | 2012/12/10 | 2012/12/10 | 2012/12/21 | 2013/01/30 | Stewart Futcher | [7 empty] | True |  | SO 8981 | 129705
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - Planning SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 100 | 10000 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/24 | 2012/08/28 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/02 | 2012/07/02 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/16 | 2012/07/13 | Stewart Futcher | [7 empty] | True |  |  | 770023005
CDW - Mondial - Services SO7955 | Allianz - SO7955 | 9 - Support Turnover |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/01/03 |  |  |  | 2012/06/29 | 2012/07/20 | Kent Pylant | [7 empty] | True | Matt Holbrook | CDW - SO007955 | 00003-0000010042
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/20 | 2012/07/18 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/08/10 | 2012/08/06 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/08/27 | 2012/08/27 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/09/14 | 2012/09/07 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/09/28 | 2012/09/28 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/01 | 2012/10/05 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/15 | 2012/10/22 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/22 | 2012/10/25 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/09/24 | 2012/09/24 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/10/05 | 2012/10/05 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/10/08 | 2012/10/08 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  | 2012/10/22 | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 | 2013/03/04 | 2013/05/17 | 2013/03/29 | 2013/05/17 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/06/18 | 2012/06/18 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/06/25 | 2012/06/29 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/07/30 | 2012/08/03 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/13 | 2012/08/14 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/20 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/27 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/09/05 | 2012/09/07 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/27 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/24 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 100 | 20000 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/22 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/07/25 | 2012/07/27 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/07/27 | 2012/08/06 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/06/25 | 2012/06/26 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 100 | 500 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/06/22 | 2012/06/22 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/10/10 | 2012/10/10 | Philip Haskings | [7 empty] | True |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/10/31 |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/11/30 |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/12/07 | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
APAC - SO9058 Remote Dialogic Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
APAC - SO9058 Remote Dialogic Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/11/09 | 2013/01/25 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/11/08 | 2012/10/10 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/10/09 | 2012/10/09 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/10/11 | 2012/10/11 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/11/16 | 2013/07/16 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 100 | 1400 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/07/16 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2012/10/24 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2012/11/09 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 100 | 77385 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2013/09/06 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2013/05/02 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/06 | 2012/09/07 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/04 | 2012/09/04 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/08/09 | 2012/08/09 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/08/16 | 2012/08/24 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
CDW - State Auto - SO8846 Training Credits (No Services) | State Auto - SO8846 | 7 - Training |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/05 | 2012/07/27 |  |  | 2012/09/10 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | 8846 | JLQ7504
HSBC - SO8623 Verona Data Split |  | Project Closure |  | 18800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/09/11 | 2012/09/28 |  |  | 2012/07/31 | 2012/07/31 | Kent Pylant | [7 empty] | True |  | 8623 | PEET 8367 |  | True
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 100 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/10 | 2012/08/17 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/31 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/07/10 | 2012/07/10 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/02 | 2012/08/03 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Unused Resource - SO99999 10/18/12 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Ally Financial - SO65577 10/19/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 | 2012/12/04 | 2012/12/05 | 2012/12/04 | 2012/12/05 | Philip Haskings | [7 empty] | True |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/31 | 2012/11/09 | 2012/12/05 | 2012/12/10 | 2012/12/06 | 2012/12/19 | Philip Haskings | [7 empty] | True |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Brady | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  | 2013/02/28 | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | ACS SO9447 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Project Kick Off | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Planning & Design | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Hardware / Software Procurement | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Readiness Validation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Product Installation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Product Integration | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Training | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Consulting & Technical Reviews | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Support Turnover | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Project Closure | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Project Kick Off | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Planning & Design | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Hardware / Software Procurement | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Readiness Validation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Product Installation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Product Integration | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Training | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Consulting & Technical Reviews | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Support Turnover | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Project Closure | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
Ally Financial - SO65577 10/22/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
HSBC - SO9454 - PM October - Matt Hogan | Project Kick Off | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Planning & Design | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Readiness Validation | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Product Installation | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Product Integration | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Training | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Support Turnover | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Project Closure | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  | 2012/10/31 | Kent Pylant | [7 empty] | True | Todd Folkes | 9454 | PEET 7511
HSBC - SO9455 October Admin | Project Kick Off | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Planning & Design | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Hardware / Software Procurement | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Readiness Validation | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Product Installation | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Product Integration | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Training | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Consulting & Technical Reviews | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Support Turnover | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Project Closure | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  | 2012/10/31 | 2012/10/31 | Kent Pylant | [7 empty] | True | Todd Folkes | 9455 | PEET 7154
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Project Kick Off | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Planning & Design | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Hardware / Software Procurement | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Readiness Validation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Product Installation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Product Integration | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Training | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Consulting & Technical Reviews | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Support Turnover | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Project Closure | Project Closure |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
Baptist Hospital - SO9500 Remote Config | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/04 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/11 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/04 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2013/01/09 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
BBVA Compass Bank - SO9502 Global Monitor Trial | Project Kick Off | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/01/09 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Planning & Design | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Readiness Validation | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Product Installation | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Product Integration | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Project Closure | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9515 SIP Trunk Change | Project Kick Off | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2012/11/29 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Planning & Design | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/01/03 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Consulting & Technical Reviews | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/03/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Project Closure | Project Closure |  | 2150 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/03/27 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
CDW - Brady Corp - SO9518 Remote License Addition | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Project Kick Off | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  | 2012/11/26 | 2012/11/27 | Kent Pylant | [7 empty] | True |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Planning & Design | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Hardware / Software Procurement | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Readiness Validation | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Product Installation | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Product Integration | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Training | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Consulting & Technical Reviews | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  | 2012/12/03 | 2012/12/21 | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Support Turnover | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Project Closure | Project Closure |  | 40000 | 0 | Kent Pylant | 100 | 40000 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  | 2013/01/29 | Kent Pylant | [7 empty] | True |  | 9528 | Lary Burke
Greater Toronto Airport Authority - SO9545 Card Install | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/01/26 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2012/11/26 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2012/12/03 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Readiness Validation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Product Integration | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Training | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Consulting & Technical Reviews | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Support Turnover | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/04/04 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Pearson Education - SO9553 Voice Card Consolidation | Project Kick Off | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/03 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Planning & Design | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Hardware / Software Procurement | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Readiness Validation | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Product Installation | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/08 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Product Integration | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/08 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Training | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Consulting & Technical Reviews | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Support Turnover | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Project Closure | Project Closure |  | 2000 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
HSBC - SO9601 - November PM - Matt Hogan | Project Kick Off | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Planning & Design | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Readiness Validation | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Product Installation | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Product Integration | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Training | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Support Turnover | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Project Closure | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Project Kick Off | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Planning & Design | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Hardware / Software Procurement | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Readiness Validation | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Product Installation | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Product Integration | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Training | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Consulting & Technical Reviews | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Support Turnover | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Project Closure | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
Medtronic - SO1198187 10/29/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 100 | 700 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  | 2012/10/29 | 2012/10/29 | Kent Pylant | [7 empty] | True | Tim Prince |  | 1198187
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Medtronic - SO1197187 11/02/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Project Kick Off | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Planning & Design | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Readiness Validation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Product Installation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Product Integration | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Training | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Support Turnover | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Project Closure | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Medtronic - SO1197187 11/05/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
HSBC - SO9619 v11 TDM Upgrades | Project Kick Off | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  | 2013/01/08 | 2013/02/05 | Philip Haskings | [7 empty] | True | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Planning & Design | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Hardware / Software Procurement | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Readiness Validation | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Product Installation | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Product Integration | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Training | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Consulting & Technical Reviews | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Support Turnover | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Project Closure | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 100 | 36000 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  | 2014/07/31 |  | John Randall | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades |  | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Planning & Design | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Product Installation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Product Integration | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Training | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Support Turnover | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Project Closure | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
APAC - SO9641 Dialogic Card Install - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/12 |  | 2012/12/28 | 2012/12/20 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2012/12/20 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/25 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
HSBC - SO8991 Onshore/Offshore Screen Recorder Services |  | 1 - Project Kick Off |  | 0 | 0 | Scott Montgomery | 100 | 0 | 0 | 0 | 2012/08/03 | 2012/09/28 | 2012/12/03 | 2012/12/05 | 2012/12/03 | 2012/12/06 | Kent Pylant | [7 empty] | True | Todd Folkes | 8991 | PEET 9183
VistaCom - SO9654 - License Upgrade - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/11 |  | 2012/12/12 | 2013/01/04 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/11 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/14 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/14 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/20 |  | 2012/12/21 | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/17 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
CDW - AFNI SO9677 Global Monitor Planning & Design | Project Kick Off | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Planning & Design | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Hardware / Software Procurement | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Readiness Validation | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Product Installation | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Product Integration | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Training | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Consulting & Technical Reviews | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Support Turnover | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Project Closure | Project Closure |  | 6400 | 0 | Tim Johnson | 100 | 6400 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  | 2013/05/01 | Kent Pylant | [7 empty] | True | Matt Brush | 9677 | 00003-0000013737 |  | True
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Planning & Design | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Product Installation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Product Integration | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Training | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Support Turnover | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Project Closure | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Project Kick Off | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Planning & Design | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Readiness Validation | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Product Installation | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Product Integration | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Training | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Support Turnover | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Project Closure | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
TOS - Region of Waterloo - SO9735 V11 WFO | Project Kick Off | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/02/28 | 2013/02/28 | 2013/02/28 | 2013/02/28 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Planning & Design | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/03/04 | 2013/03/04 | 2013/03/22 | 2013/03/22 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Hardware / Software Procurement | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/02/25 | 2013/02/25 | 2013/02/28 | 2013/02/28 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Readiness Validation | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/04/08 | 2013/04/09 | 2013/04/10 | 2013/04/10 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Product Installation | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/05/20 | 2013/05/20 | 2013/05/31 | 2013/05/31 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Product Integration | Project Closure |  | 63700 | 0 | Stewart Futcher | 90 | 57330 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/05/20 | 2013/05/20 | 2013/05/31 | 2013/05/31 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Training | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/06/17 | 2013/06/17 | 2013/07/05 | 2013/07/05 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Consulting & Technical Reviews | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/07/01 | 2013/07/01 | 2013/07/12 | 2013/07/12 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Support Turnover | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/08/26 | 2013/09/18 | 2013/08/26 | 2013/09/18 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Project Closure | Project Closure |  | 63700 | 0 | Stewart Futcher | 10 | 6370 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/08/30 |  | 2014/01/31 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
Seimens _ Medstar SO9740 QM Supervisor Training | Project Kick Off | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Planning & Design | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Hardware / Software Procurement | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Readiness Validation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Product Installation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Product Integration | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Training | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Consulting & Technical Reviews | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Support Turnover | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Project Closure | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
CDW - Vectren Energy SO10032 Op QM | Project Kick Off | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/01/10 | 2013/01/10 | 2013/01/18 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Planning & Design | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/03/11 | 2013/03/11 | 2013/03/29 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Hardware / Software Procurement | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/04/15 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Readiness Validation | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/29 | 2013/05/01 | 2013/04/29 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Product Installation | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/05/03 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Product Integration | Project Closure |  | 11815 | 0 | Stewart Futcher | 100 | 11815 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/05/31 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Training | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/09/12 |  | 2013/09/13 |  | Stewart Futcher | [7 empty] | False |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Consulting & Technical Reviews | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/05/20 | 2013/05/20 | 2013/05/24 | 2013/05/30 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Support Turnover | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/08/26 | 2013/09/27 | 2013/08/26 | 2013/09/27 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Project Closure | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/09/06 | 2013/09/24 | 2013/09/06 | 2013/09/24 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 100 | 1575 | 0 | 0 | 2013/01/07 | 2013/01/28 | 2013/01/08 | 2013/01/08 | 2013/01/08 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  | 2013/01/10 | 2013/01/15 | 2013/01/15 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 | 2013/01/25 | 2013/01/28 | 2013/01/25 | 2013/01/28 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2013/01/07 | 2013/01/31 | 2013/03/04 | 2013/05/17 | 2013/03/29 | 2013/05/17 | Stewart Futcher | [7 empty] | True |  | 9772 | 7700237080 |  | True | 2013/05/23
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Project Kick Off | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Planning & Design | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Hardware / Software Procurement | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Readiness Validation | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Product Installation | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Product Integration | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Training | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Consulting & Technical Reviews | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Support Turnover | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Project Closure | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
FabriCut, Inc. - SO9367 v11 Install | Project Kick Off | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2012/11/27 | 2012/10/29 | 2012/11/27 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Planning & Design | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2012/11/27 | 2012/11/27 | 2013/01/22 | 2013/03/12 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2012/11/27 | 2013/01/15 | 2013/01/22 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Readiness Validation | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/01/15 | 2013/01/22 | 2013/01/17 | 2013/01/23 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Product Installation | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/02/18 | 2013/03/14 | 2013/02/28 | 2013/03/18 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Product Integration | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 100 | 16800 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/02/19 | 2013/03/12 | 2013/02/25 | 2013/03/22 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Training | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/04/02 | 2013/04/01 | 2013/04/05 | 2013/04/19 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2013/03/29 | 2013/02/22 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Support Turnover | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/04/23 |  | 2013/04/23 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Project Closure | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2013/04/30 | 2013/03/07 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Project Kick Off | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Planning & Design | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Hardware / Software Procurement | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Readiness Validation | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Product Installation | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Product Integration | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Training | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Consulting & Technical Reviews | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Support Turnover | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Project Closure | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
Verizon - SO9291 Hardware Upgrade | Project Kick Off | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Planning & Design | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Hardware / Software Procurement | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Readiness Validation | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Product Installation | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Product Integration | Project Closure |  | 2400 | 0 | Philip Haskings | 100 | 2400 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/12 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Training | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Consulting & Technical Reviews | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Support Turnover | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Project Closure | Project Closure |  | 2400 | 0 | Philip Haskings | 100 | 2400 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/12 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Project Kick Off | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/06 | 2012/09/07 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Planning & Design | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Readiness Validation | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Product Installation | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Product Integration | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/27 | 2012/09/27 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Training | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  | 2012/09/27 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Support Turnover | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Project Closure | Project Closure |  | 3125 | 0 | Kent Pylant | 100 | 3125 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Covidien - SO1203233 09/26/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Project Kick Off | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Planning & Design | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Readiness Validation | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Product Installation | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Product Integration | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Training | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Support Turnover | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Project Closure | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
Knology - SO9038 Trunk Tap Remote | COS signed | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 500 | 0 | 0 | 2012/08/15 | 2012/09/14 |  |  | 2012/09/21 | 2012/09/25 | Kent Pylant | [7 empty] | True |  | 9038 | 414-126621
TBL Networks - VA Department of Taxation SO8518 WFO | Installation | Project Closure |  | 66889 | 0 | Stewart Futcher | 100 | 66889 | 0 | 0 | 2012/04/30 | 2012/10/10 | 2013/02/04 | 2013/02/04 | 2013/02/15 | 2013/02/22 | Kent Pylant | [7 empty] | True |  | 8518 | 2475 | 2012/09/21 | True
APAC - SO9058 Remote Dialogic Config | APAC - SO9058 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/02 | 2012/10/07 | Kent Pylant | [7 empty] | True |  | 9058 | APAC-TUCE-66902
APAC - SO9058 Remote Dialogic Config | APAC - SO9058 | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/05 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
TBL Networks - VA Department of Taxation SO8518 WFO | VA Dept of Tax - SO8518 | Project Closure |  | 66889 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/10/10 | 2013/01/25 | 2013/01/25 | 2013/01/28 | 2013/01/28 | Stewart Futcher | [7 empty] | True |  | 8518 | 2475 | 2012/09/21 | True
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/31 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/02 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/05 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite | Worldcom - BCBS MA | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  | 2012/10/05 | 2012/10/05 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/04 | Philip Haskings | [7 empty] | True |  |  | 18562
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Siemens - H E B Grocery SO9320 Op QM Install | Project Kick Off | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/16 | 2012/11/16 | 2012/11/16 | 2013/01/08 | Stewart Futcher | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Planning & Design | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/10 | 2012/12/10 | 2013/01/04 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Hardware / Software Procurement | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/10 | 2012/12/10 | 2013/01/02 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Readiness Validation | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Product Installation | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  | 2012/12/10 | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Product Integration | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  | 2012/12/21 | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Training | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Consulting & Technical Reviews | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Support Turnover | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Project Closure | Project Closure |  | 19200 | 0 | Stewart Futcher | 100 | 19200 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/28 | 2013/01/28 | 2013/03/08 | 2013/03/22 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/24 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
CDW - TMG - SO8721 WFO Consulting |  | Project Closure |  | 7550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/06/07 | 2012/07/06 |  |  |  |  | Stewart Futcher | [7 empty] | False |  |  | 00003-0000011680
CDW - TMG - SO8721 WFO Consulting | CDW - TMG SO8721 | Project Closure |  | 7550 | 0 | Stewart Futcher | 100 | 7550 | 0 | 0 | 2012/06/07 | 2012/07/06 |  |  | 2012/07/13 | 2012/07/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011680
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Planning & Design | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/03 | 2012/12/04 | 2013/01/07 | 2013/01/11 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Hardware / Software Procurement | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/26 | 2012/11/26 | 2013/01/04 | 2013/01/07 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Readiness Validation | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/04 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Product Installation | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/02/18 | 2013/02/18 | 2013/02/18 | 2013/03/01 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Product Integration | Project Closure |  | 19100 | 0 | Stewart Futcher | 100 | 19100 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/02/18 | 2013/02/18 | 2013/02/18 | 2013/03/01 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Training | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/03/04 | 2013/03/04 | 2013/03/04 | 2013/03/08 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Consulting & Technical Reviews | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/03/11 | 2013/03/11 | 2013/03/22 | 2013/03/22 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Support Turnover | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/09/26 | 2013/09/26 | 2013/09/26 | 2013/09/26 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Project Closure | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/08/26 | 2013/09/26 | 2013/08/30 | 2013/09/26 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Utah Retirement Systems - SO9292 | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/15 | 2012/11/15 | 2012/11/15 | 2012/11/15 | Stewart Futcher | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Project Kick Off | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Planning & Design | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/08 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Readiness Validation | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/15 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Product Installation | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/19 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Product Integration | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/19 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Training | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/20 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/21 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Support Turnover | Project Closure |  | 2800 | 0 | Philip Haskings | 100 | 2800 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/21 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Project Closure | Project Closure |  | 2800 | 0 | Philip Haskings | 100 | 2800 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/23 | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9325 | 002 2012
Siemens - Peoples Natural Gas SO9328 License Update Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/08 | Philip Haskings | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  | 2012/10/12 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/09/28 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 100 | 36775 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/09/28 | 2012/10/25 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 100 | 36775 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/10/26 | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/11/09 |  | Stewart Futcher | [7 empty] | False |  | 9016 | 00003-0000012388
CDW - Allianz SO9330 Telephone Playback Server | Project Kick Off | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Planning & Design | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Hardware / Software Procurement | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Readiness Validation | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Product Installation | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  | 2012/11/14 |  | 2012/11/15 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Product Integration | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Training | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Consulting & Technical Reviews | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  | 2012/11/30 |  | 2013/01/21 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Support Turnover | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Project Closure | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 | 2012/11/20 | 2013/01/15 | 2012/11/27 | 2013/01/28 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Siemens - Medstar - SO9280 3rd site Op QM | Project Kick Off | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Planning & Design | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Readiness Validation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Product Installation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Product Integration | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Training | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Support Turnover | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Project Closure | Project Closure |  | 3200 | 0 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2012/10/09 | 2013/01/25 | 2012/11/05 | 2012/11/05 | 2012/11/16 | 2012/11/16 | Kent Pylant | [7 empty] | True |  | 9280 | 7700234792 |  | True
CDW - TMG Health - SO9372 Additional Training | Project Kick Off | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Planning & Design | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Readiness Validation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Product Installation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Product Integration | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Training | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Support Turnover | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Project Closure | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 | 2012/10/22 | 2012/10/19 | 2012/10/19 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9372 | Adtech
CDW - State Auto Insurance - SO8515 |  | Project Closure |  | 26000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/09/21 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | False |  | 8515 | 00003-0000011329
Ronco Communications - SO9092 Remote NGX Configuration | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  |  | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/02/08 | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Presidio - Lab Corp - SO8874 Remote Support | Lab Corp | Project Closure |  | 3500 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/08/31 | 2012/09/21 | Kent Pylant | [7 empty] | True |  | 8874 | 36207989-01
Presidio - Lab Corp - SO8874 Remote Support |  | Project Closure |  | 3500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 8874 | 36207989-01
Presidio - Lab Corp - SO8874 Remote Support | Lab Corp - SO8874 | Project Closure |  | 3500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/08/31 | 2012/08/31 | Stewart Futcher | [7 empty] | False |  | 8874 | 36207989-01
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Project Kick Off | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  | 2012/08/31 |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Planning & Design | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Hardware / Software Procurement | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Readiness Validation | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Product Installation | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Product Integration | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Training | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Consulting & Technical Reviews | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Support Turnover | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Project Closure | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
HSBC - SO9101 - August PM Resource - M Hogan | Project Kick Off | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Planning & Design | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Hardware / Software Procurement | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Readiness Validation | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Product Installation | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Product Integration | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Training | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Consulting & Technical Reviews | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Support Turnover | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Project Closure | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9100 - August Admin Support Resources | Project Kick Off | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Planning & Design | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Hardware / Software Procurement | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Readiness Validation | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Product Installation | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Product Integration | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Training | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Consulting & Technical Reviews | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Support Turnover | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Project Closure | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
Ericsson, Inc. - SO9111 Level 3 Support | Project Kick Off | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Planning & Design | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Readiness Validation | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Product Installation | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Product Integration | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Training | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Support Turnover | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Project Closure | Project Closure |  | 3200 | 0 | Philip Haskings | 100 | 3200 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/28 | 2012/09/28 | Philip Haskings | [7 empty] | True |  | 9111 | 4506966796
R J Reynolds - SO9109 - v11 Compliance | Project Kick Off | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/09/06 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Planning & Design | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Hardware / Software Procurement | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/09/12 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Readiness Validation | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Product Installation | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Product Integration | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/10/02 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Training | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Consulting & Technical Reviews | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Support Turnover | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Project Closure | Project Closure |  | 12300 | 0 | Stewart Futcher | 100 | 12300 | 0 | 0 | 2012/09/05 | 2012/12/21 | 2012/12/03 | 2012/12/03 | 2012/12/07 | 2012/12/07 | Stewart Futcher | [7 empty] | True |  | 9109 | 4534690692
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Project Kick Off | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Planning & Design | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Readiness Validation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Product Installation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Product Integration | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Training | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Support Turnover | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Project Closure | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
Unused Resource - SO99999 08/03/12 Fred Jurs | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Unused Resource - SO99999 08/16/12 Chris McGuire | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Unused Resource - SO99999 Michael Taylor | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
Telus Communications - Prospera SO9205 WFM Move | Project Kick Off | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  | 2012/09/20 |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Planning & Design | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Hardware / Software Procurement | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Readiness Validation | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Product Installation | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Product Integration | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Training | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Consulting & Technical Reviews | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Support Turnover | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Project Closure | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Siemens - Capital City Bank - SO9240 eQM License Update | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/10 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/11 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/17 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/18 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/08 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/08 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/03 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Affiliated Computer Services - SO8353 NGX Cards and Server |  | Project Closure |  | 4700 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/10 | 2012/09/25 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Knology - SO9038 Trunk Tap Remote |  | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/08/15 | 2012/09/14 |  |  | 2012/09/21 | 2012/09/21 | Kent Pylant | [7 empty] | True |  | 9038 | 414-126621
Siemens - Dematic Corp. - SO9847 | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/02/08 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/03/07 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Nissan North America - SO9777 On Site Services | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Readiness Validation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Product Integration | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Training | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Consulting & Technical Reviews | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Support Turnover | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
CDW - TMG - SO9856 - Additional Recorders | Project Kick Off | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 | 2012/10/22 | 2012/10/22 | 2012/10/26 | 2012/10/26 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Planning & Design | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 | 2012/10/22 | 2012/10/22 | 2012/10/26 | 2012/10/26 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Readiness Validation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Product Installation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Product Integration | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Training | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Support Turnover | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Project Closure | Project Closure |  | 3200 | 0 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  | 2013/02/14 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
APAC - SO9862 Tucson - Dialogic Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367

## Executor
pj Title | ms Stage | pj current Milestone | pj Type | pj Services Revenue | pj Booked Services Revenue | pj rec Owner | ms % Earned Revenue | ms Earned Revenue | ms % Invoiced Revenue | ms Invoiced Revenue | pj Start Date | pj Est Completion Date | ms Target Start Date | ms Actual Start Date | ms Target Completion Date | ms Actual Completion Date | ms rec Owner | tm Name | tm Type | tm Start Date | tm End Date | tm Num Hours | tm Executor | tm rec Owner | ms Completed | Primary Contact | Sales Order | Customer PO | Customer PO Received Date | COS Received | COS Received Date
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Planning & Design | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Hardware / Software Procurement | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Product Installation | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Product Integration | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
Molecular Devices - SO10073 - Univ Cal Davis - Services for SO9996 | Project Closure | Project Closure | MolDev-Screen 10 | 5270 | 0 | Philip Haskings | 100 | 5270 | 0 | 0 | 2013/04/03 | 2013/04/10 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10073 | 40315301 | 2013/04/15 | True | 2013/07/10
BBVA Compass Bank - SO9870 License Update | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Support Turnover | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BBVA Compass Bank - SO9870 License Update | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/03/25 | 2013/04/05 |  |  |  | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9870 | 99219 |  | True
BMW - SO10979 - Onsite Installation Services | Project Kick Off | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Planning & Design | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Hardware / Software Procurement | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Product Installation | Project Closure |  | 7050 | 14100 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 | 2013/10/31 |  | 2013/10/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10979 - Onsite Installation Services | Project Closure | Project Closure |  | 7050 | 14100 | Philip Haskings | 100 | 7050 | 0 | 0 | 2013/10/14 | 2013/12/12 | 2013/11/01 |  | 2013/12/12 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10979 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Project Kick Off | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Planning & Design | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Hardware / Software Procurement | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Product Installation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  | 2013/11/18 | 2013/11/18 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
BMW - SO10982 - Onsite Installation Services | Project Closure | Project Closure |  | 7050 | 0 | Philip Haskings | 100 | 7050 | 0 | 0 | 2013/10/14 | 2013/12/12 |  |  | 2013/12/12 | 2013/12/20 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10982 | 4500268389 | 2013/10/14 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  | 2013/10/15 |  | 2013/10/16 | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  | 2013/10/15 |  | 2013/10/17 | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Readiness Validation | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Product Installation | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/10/21 |  | 2013/10/25 |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Product Integration | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 50 | 165000 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/10/28 |  | 2013/10/31 | 2013/10/31 | John Randall | [7 empty] | True | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Training | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/11/18 |  | 2013/11/26 |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Mary King | 10996 | 16423 | 2013/10/15 | False
CMS Medicare - SO10996 - eWFO Professional Services - Phase 1 ¦ 4,000 seats | Project Closure | 8 - Consulting & Technical Reviews |  | 330000 | 330000 | John Randall | 50 | 165000 | 0 | 0 | 2013/10/10 | 2013/11/27 | 2013/11/27 |  | 2013/11/27 | 2013/11/29 | John Randall | [7 empty] | True | Mary King | 10996 | 16423 | 2013/10/15 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Project Kick Off | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Planning & Design | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/18 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/10/31 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Product Installation | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  |  | 2013/12/19 | Philip Haskings | [7 empty] | True | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Product Integration | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 100 | 750 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
Nissan - SO11007 - Dialogic Expansion Chassis | Project Closure | 8 - Consulting & Technical Reviews |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/18 | 2014/04/30 |  |  | 2013/12/31 |  | Philip Haskings | [7 empty] | False | Diane Damer | 11007 | 7400067036 | 2013/10/17 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Project Kick Off | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Planning & Design | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Hardware / Software Procurement | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Product Installation | Project Closure |  | 3580 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 | 2013/12/08 |  | 2013/12/11 | 2013/12/13 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10777 - 2 Days of Installation | Project Closure | Project Closure |  | 3580 | 0 | Philip Haskings | 100 | 3580 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10777 | 40909303 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Project Kick Off | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Planning & Design | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Hardware / Software Procurement | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/06 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Product Installation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/17 | 2013/12/31 | 2013/12/08 |  | 2013/12/11 | 2013/12/13 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
MolDev - IGR (France) - SO10595 - Screen 10 + Storage - 1 Day Installation | Project Closure | Project Closure |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/10/17 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10595 | 40702302 | 2013/09/24 | False
HSBC - PM - March 2014 | Project Kick Off | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Planning & Design | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Readiness Validation | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Product Installation | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Product Integration | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Training | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Support Turnover | Project Closure |  | 17280 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - March 2014 | Project Closure | Project Closure |  | 17280 | 0 | Tim Johnson | 100 | 17280 | 0 | 0 | 2014/03/01 | 2014/03/30 |  |  | 2014/03/31 | 2014/03/24 | Matt Hogan | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/03/01 | False
HSBC - PM - January 2014 | Project Kick Off | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Planning & Design | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Hardware / Software Procurement | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Readiness Validation | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Product Installation | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Product Integration | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Training | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Consulting & Technical Reviews | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Support Turnover | Project Closure |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - January 2014 | Project Closure | Project Closure |  | 20160 | 0 | Tim Johnson | 100 | 20160 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/01/01 | False
HSBC - PM - February 2014 | Project Kick Off | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Planning & Design | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Readiness Validation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Product Installation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Product Integration | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Training | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Support Turnover | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
HSBC - PM - February 2014 | Project Closure | Project Closure |  | 17280 | 0 | Matt Hogan | 100 | 17280 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2014/02/01 | False
Windstream - Bausch and Lomb - SO11042 | Project Kick Off | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Planning & Design | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  | 2013/10/30 | 2013/10/31 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Consulting & Technical Reviews | Project Closure |  | 5600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/23 | 2013/11/08 | 2013/11/01 |  | 2013/11/03 | 2013/11/02 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
Windstream - Bausch and Lomb - SO11042 | Project Closure | Project Closure |  | 5600 | 0 | Philip Haskings | 100 | 5600 | 0 | 0 | 2013/10/23 | 2013/11/08 |  |  | 2013/12/09 | 2013/12/16 | Philip Haskings | [7 empty] | True | Mern Reeves | 11042 | 1114507 | 2013/10/23 | False
BMW - SO11055 - GM installation on 9 servers | Project Kick Off | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  | 2014/01/08 | Philip Haskings | [7 empty] | True | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Planning & Design | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Product Integration | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Support Turnover | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
BMW - SO11055 - GM installation on 9 servers | Project Closure | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/28 | 2014/03/31 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 11055 | 4500268851 | 2013/10/24 | False
Verint PMO Revenue - January 2014 | Project Kick Off | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Planning & Design | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Readiness Validation | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Product Installation | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Product Integration | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Training | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Support Turnover | Project Closure |  | 10200 | 10200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/01 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint PMO Revenue - January 2014 | Project Closure | Project Closure |  | 10200 | 10200 | Kent Pylant | 100 | 10200 | 0 | 0 | 2014/01/01 | 2014/01/31 | 2014/01/01 | 2014/01/01 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/01 | False
Verint RRI Revenue - January 2014 | Project Kick Off | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Planning & Design | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Readiness Validation | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Product Installation | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Product Integration | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Training | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Support Turnover | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/02/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - January 2014 | Project Closure | Project Closure |  | 12906.25 | 10000 | Kent Pylant | 100 | 12906.25 | 0 | 0 | 2014/01/02 | 2014/02/04 | 2014/01/02 | 2014/01/02 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - January 2014 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/01/02 | 2014/01/31 | 2014/01/01 | 2014/01/02 | 2014/01/31 | 2014/01/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - February 2014 | Project Kick Off | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Planning & Design | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Readiness Validation | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Product Installation | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Product Integration | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Training | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Support Turnover | Project Closure |  | 0 | 7000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - February 2014 | Project Closure | Project Closure |  | 0 | 7000 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 | 2014/02/01 | 2014/02/01 | 2014/02/28 | 2014/02/28 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Project Kick Off | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Planning & Design | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Readiness Validation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Product Installation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Product Integration | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Training | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Support Turnover | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - February 2014 | Project Closure | Project Closure |  | 0 | 1400 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/02/01 | 2014/02/28 | 2014/02/01 | 2014/02/03 | 2014/02/28 | 2014/02/28 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Project Kick Off | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Planning & Design | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Readiness Validation | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Product Installation | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Product Integration | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Training | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Support Turnover | Project Closure |  | 0 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint PMO Revenue - March 2014 | Project Closure | Project Closure |  | 0 | 3500 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 | 2014/03/01 | 2014/03/03 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | False | Matt Webb | 99999 | 99999 | 2014/01/31 | False
Verint MAC Revenue - March 2014 | Project Closure | Project Closure |  | 0 | 1400 | Kent Pylant | 100 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 | 2014/03/01 | 2014/03/03 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2014/02/03 | False
APAC - SO9872 - Dialogic Install | Project Kick Off | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Planning & Design | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Hardware / Software Procurement | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Readiness Validation | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Product Installation | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Product Integration | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Training | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Consulting & Technical Reviews | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Support Turnover | Project Closure |  | 1300 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
APAC - SO9872 - Dialogic Install | Project Closure | Project Closure |  | 1300 | 0 | Philip Haskings | 100 | 1300 | 0 | 0 | 2013/02/01 | 2013/02/08 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9872 | 68410
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/28/13 - 02/01/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchon Eyewear - SO1190348 01/28/13 - 01/31/13 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Medco - SO1208699 02/01/13 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 02/01/13 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/01 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Planning & Design | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Product Installation | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Product Integration | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Training | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Support Turnover | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO1200249 01/28/13 - 02/01/13 Remote - Aziz H | Project Closure | Project Closure |  | 1200249 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
Rogers Group - SO1174399 01/28/13 - 02/01/13 Robb D | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174399
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/26/12 - 12/28/12 Remote - Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/26 | 2012/12/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Cardinal Health - SO1200319 01/22/13 - 01/25/13 Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200319
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Planning & Design | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Product Installation | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Product Integration | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Training | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Support Turnover | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco health - SO1208699 01/22/13 - 01/25/13 Remote - Fred J | Project Closure | Project Closure |  | 2450 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO 1197187 01/25/13 Remote - Fred J | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/25 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
AIG - SO 1200249 01/22/13 - 01/25/13 Remote Aziz H | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/22 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200249
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/07/13 - 01/09/13 Remote - Aziz | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO 1200238 01/07/13 - 01/11/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Unused Resource - SO99999 01/07/13 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 01/07/13 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/08/13 - 01/11/13 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/08 | 2013/01/11 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Wells Fargo - SO1213216 01/14/13 - 01/18/13 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213216
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused - SO99999 01/14/13 - 01/16/13 Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Medco - SO1208699 01/17/13 - 01/18/13 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/17 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208699
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Planning & Design | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Product Installation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Product Integration | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Training | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Support Turnover | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Domininion Bank - SO1207437 01/14/13 - 01/18/13 Remote - Aziz H | Project Closure | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/14 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
Coca Cola - SO 1205169 01/18/13 Remote - Aziz H | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/18 | 2013/01/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205169
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 01/02/13 - 01/04/13 Remote Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Intact - SO 1213063 01/02/13 Remote - Robb D | Project Kick Off | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Planning & Design | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Readiness Validation | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Product Installation | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Product Integration | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Training | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Support Turnover | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Intact - SO 1213063 01/02/13 Remote - Robb D | Project Closure | Project Closure |  | 175 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1213063
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Project Kick Off | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Planning & Design | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Hardware / Software Procurement | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Readiness Validation | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Product Installation | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Product Integration | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Training | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Consulting & Technical Reviews | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Support Turnover | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Toronto Dominion Bank - SO1207437 01/02/13 - 01/04/13 Remote - Robb B | Project Closure | Project Closure |  | 1925 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1207437
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
Keystone Mercy Health - SO64388 01/02/13 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64388
McKesson - SO1202191 01/02/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
McKesson - SO1202191 01/02/13 Remote - Aziz H | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202191
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Project Kick Off | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Planning & Design | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Readiness Validation | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Product Installation | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Product Integration | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Training | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Support Turnover | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
Bank of America - SO 1204875 01/02/13 - 01/04/13 Remote - Aziz H | Project Closure | Project Closure |  | 525 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/02 | 2013/01/04 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204875
APAC - SO9888 Remote Services | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
APAC - SO9888 Remote Services | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/08 | 2013/02/15 |  |  |  | 2013/02/11 | Philip Haskings | [7 empty] | True |  | 9888 | 68447
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | False |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Mizuho Corporate Bank - SO9897 Remote License Upgrade | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/12 | 2013/02/15 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9897 | 27011
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Project Kick Off | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Planning & Design | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Hardware / Software Procurement | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Readiness Validation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Product Installation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Product Integration | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Training | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Consulting & Technical Reviews | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Support Turnover | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 9740 | 7700237041
Siemens - Medstar Georgetown Univ. Hospital - SO9740 - Training | Project Closure | Project Closure |  | 1800 | 0 | Stewart Futcher | 100 | 1800 | 0 | 0 | [5 empty] | 2013/04/05 | Tim Johnson | [7 empty] | True |  | 9740 | 7700237041
Apple Inc - Onsite v11 Server Installation - SO10129 | Project Kick Off | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Planning & Design | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Hardware / Software Procurement | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/09 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Readiness Validation | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Product Installation | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Product Integration | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Consulting & Technical Reviews | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Support Turnover | Project Closure |  | 13500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
Apple Inc - Onsite v11 Server Installation - SO10129 | Project Closure | Project Closure |  | 13500 | 0 | Philip Haskings | 100 | 13500 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10129 | 6000046400 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Project Kick Off | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Planning & Design | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Training | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Support Turnover | Project Closure |  | 1600 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
NACR - CoBank - SO10144 - Server Rebuild and eQM Training | Project Closure | Project Closure |  | 1600 | 0 | Philip Haskings | 100 | 1600 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10144 | PO00174909 |  | True
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Project Kick Off | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Planning & Design | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Hardware / Software Procurement | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Readiness Validation | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/04/30 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Product Installation | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Product Integration | Project Closure |  | 45000 | 0 | Philip Haskings | 90 | 40500 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Training | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Consulting & Technical Reviews | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Support Turnover | Project Closure |  | 45000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  | 2014/02/28 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Implementation Remote and Onsite | Project Closure | Project Closure |  | 45000 | 0 | Philip Haskings | 10 | 4500 | 0 | 0 |  | 2014/02/28 |  |  | 2014/02/28 | 2014/02/26 | Philip Haskings | [7 empty] | True | Orlando Suero | 9297 | 2120930-01 | 2012/09/30 | True | 2013/06/18
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Training | Training | Project Closure |  | 25000 | 0 | Philip Haskings | 50 | 12500 | 0 | 0 | 2013/01/01 | 2013/09/30 |  |  | 2013/10/31 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 9297 | 2120930-01 | 2013/01/01 | True | 2013/10/15
CNP - Miami Int Airport - SO9297 - SteelBox - Pro Services Training | Project Closure | Project Closure |  | 25000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/30 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 9297 | 2120930-01 | 2013/01/01 | True | 2013/10/15
Verint - Amway Services - SO10138 - John R | Project Kick Off | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Planning & Design | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Hardware / Software Procurement | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Readiness Validation | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Product Installation | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Product Integration | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Training | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Consulting & Technical Reviews | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Support Turnover | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
Verint - Amway Services - SO10138 - John R | Project Closure | Project Closure | Verint-oRec | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/26 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10138 | 822741 OS | 2013/02/22 | True | 2013/03/01
NACR - CoBank - SO10165 - After Hours Support | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/18 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
NACR - CoBank - SO10165 - After Hours Support | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/04/17 | 2013/04/22 |  |  |  | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10165 | PO00175167 |  | True
Verint - California Casualty - SO10162 Onsite Services | Project Kick Off | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Planning & Design | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Hardware / Software Procurement | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Readiness Validation | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Product Installation | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Product Integration | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Training | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Consulting & Technical Reviews | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Support Turnover | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services | Project Closure | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services |  | 7 - Training |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/17 | 2013/04/19 | 2013/04/16 | 2013/04/16 | 2013/04/16 | 2013/04/16 | Kent Pylant | [7 empty] | True |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Verint - California Casualty - SO10162 Onsite Services |  | 7 - Training |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2013/04/17 | 2013/04/19 | 2013/04/17 | 2013/04/17 | 2013/04/19 | 2013/04/19 | Kent Pylant | [7 empty] | True |  | 10162 | P13-5864 | 2013/04/17 | True | 2013/04/25
Molecular Devices - SO10125- Germany - Research 10 | Project Kick Off | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Planning & Design | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Product Installation | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Product Integration | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
Molecular Devices - SO10125- Germany - Research 10 | Project Closure | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/04/18 | 2013/04/25 |  |  |  | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10125 | 40404301 | 2013/06/12 | True | 2013/06/27
NACR - CoBank - SO10177 - Remote License Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
NACR - CoBank - SO10177 - Remote License Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10177 | PO00174906 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Project Kick Off | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/19 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Planning & Design | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Product Installation | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Product Integration | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Support Turnover | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
Arrow S3 - Summit Medical - SO10183 - eWFO 24 Seats - Remote Install | Project Closure | Project Closure |  | 1000 | 0 | Philip Haskings | 100 | 1000 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10183 | PTRK01206537 |  | True
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Planning & Design | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Product Installation | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/03 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Product Integration | Project Closure |  | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/03 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
CDW - AFNI - SO10198 - Addition of 3 Recorders - Remote Installation | Project Closure | Project Closure |  | 7200 | 0 | Philip Haskings | 100 | 7200 | 0 | 0 | [5 empty] | 2013/07/08 | Philip Haskings | [7 empty] | True | David Eyre | 10198 | 000030000014843 | 2013/04/23 | True | 2013/07/23
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Project Kick Off | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/13 | 2013/05/13 | 2013/05/13 | 2013/05/13 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Planning & Design | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/20 | 2013/05/20 | 2013/05/20 | 2013/05/24 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/15 | 2013/05/15 | 2013/05/15 | 2013/05/15 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Readiness Validation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/03 | 2013/06/03 | 2013/06/03 | 2013/06/04 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Product Installation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Product Integration | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Training | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/09/16 |  | 2013/09/20 |  | Tim Johnson | [7 empty] | False |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/05 | 2013/08/05 | 2013/08/23 | 2013/08/23 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Support Turnover | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/26 |  | 2013/08/26 |  | Tim Johnson | [7 empty] | False |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - Santa Cruz - SO10192 - 60 Seat upgrade from Express to v11.1 | Project Closure | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 22400 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/19 |  | 2013/08/30 | 2013/08/30 | Tim Johnson | [7 empty] | True |  | 10192 | 7700239483 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Project Kick Off | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/06 | 2013/05/06 | 2013/05/06 | 2013/05/06 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Planning & Design | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/13 | 2013/05/13 | 2013/05/13 | 2013/05/24 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/05/03 | 2013/05/03 | 2013/05/03 | 2013/05/10 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Readiness Validation | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/03 | 2013/06/03 | 2013/06/03 | 2013/06/04 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Product Installation | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Product Integration | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 95 | 29735 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/06/10 | 2013/06/10 | 2013/06/21 | 2013/06/21 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Training | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2014/01/20 |  | 2014/01/31 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/05 | 2013/08/05 | 2013/08/16 | 2013/08/19 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Support Turnover | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/08/26 | 2013/08/27 | 2013/08/26 | 2013/08/27 | Tim Johnson | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Siemens - County of Santa Cruz - SO10193 - v11.1 OpWFM, Adv Scorecard, OpQM | Project Closure | 8 - Consulting & Technical Reviews |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/06 | 2013/09/27 | 2013/09/27 |  | 2013/09/27 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Larry Caylor | 10193 | 7700239409 | 2013/05/06 | True | 2013/06/26
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Project Kick Off | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Planning & Design | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Hardware / Software Procurement | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Readiness Validation | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Product Installation | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Product Integration | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Training | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Consulting & Technical Reviews | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Support Turnover | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
Verint - WellPoint - SO10206 - HD Repair - Aziz H | Project Closure | 6 - Product Integration |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/04/24 | 2013/04/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10206 | P13-6573 | 2013/04/23 | True | 2013/04/25
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
RJ Reynolds - SO10209 - Ai-Logix PCIe Onsite Install | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 |  |  | 2013/05/28 | 2013/05/28 | 2013/05/31 | 2013/05/31 | Tim Johnson | [7 empty] | True |  | 10209 | 4534726762 | 2013/05/15 | True | 2013/06/17
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
BBVA - Compass Bank - SO10256 - U10 License Expansion for 7 Seats | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/05/28 | Philip Haskings | [7 empty] | True |  | 10256 | PO118125 |  | True
Molecular Devices - SO10170 - MedImmune HCS Solution | Project Kick Off | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Planning & Design | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Hardware / Software Procurement | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Product Installation | Project Closure |  | 5270 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Molecular Devices - SO10170 - MedImmune HCS Solution | Project Closure | Project Closure |  | 5270 | 0 | Philip Haskings | 100 | 5270 | 0 | 0 | [5 empty] | 2013/06/28 | Philip Haskings | [7 empty] | True |  | 10170 | 40416305 | 2013/05/07 | True | 2013/07/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/10/10 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/08 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
Progressive Casualty - SO10291 - PCIE 48 Remote Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/10/31 |  |  |  | 2013/09/27 | Philip Haskings | [7 empty] | True | Walter Lazusky | 10291 | 651657 | 2013/05/07 | True | 2013/10/10
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Training | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ePlus - County of Sussex - SO10290 - v11.1 OpQM 136 seats | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  | 10290 | 651657 |  | False
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Project Kick Off | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/16 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Planning & Design | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Hardware / Software Procurement | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/21 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Readiness Validation | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/22 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Product Installation | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/24 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Product Integration | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Consulting & Technical Reviews | Project Closure |  | 5500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
ADVANtel - City of Alameda - SO10299 - v11 PCI Encryption | Project Closure | Project Closure |  | 5500 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10299 | 5007930 |  | True
Charter Communications - SO10307 Hard Drive Solution Services | Project Kick Off | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Planning & Design | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Product Installation | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/06/20 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Charter Communications - SO10307 Hard Drive Solution Services | Project Closure | Project Closure | Hardware Install / Config | 14100 | 0 | Philip Haskings | 100 | 14100 | 0 | 0 | 2013/05/14 | 2013/05/17 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10307 | 1705292 000 OW | 2013/05/13 | True | 2013/07/01
Johnson & Johnson - SO10313 On Site Card Install | Project Kick Off | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Planning & Design | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Hardware / Software Procurement | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Product Installation | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
Johnson & Johnson - SO10313 On Site Card Install | Project Closure | Project Closure |  | 4000 | 0 | Philip Haskings | 100 | 4000 | 0 | 0 | 2013/05/16 | 2013/05/17 |  |  |  | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10313 | 993172154 | 2013/05/14 | True | 2013/08/01
ACS Technologies - SO10315 - Dell Server Remote Services | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/05/20 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - SO10315 - Dell Server Remote Services | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/20 | 2013/08/14 |  |  |  | 2013/08/14 | Philip Haskings | [7 empty] | True |  | 10315 | 838567 | 2013/05/15 | True | 2013/08/30
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/05/29 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
ACS Technologies - Cheyenne - SO10329 Remote Hardware Services | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/05/22 | 2013/05/24 |  |  |  | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10329 | AC199849 | 2013/05/22 | True | 2013/08/09
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Project Kick Off | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Planning & Design | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Hardware / Software Procurement | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Readiness Validation | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Product Installation | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Product Integration | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Training | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Consulting & Technical Reviews | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Support Turnover | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
Alticor, Inc. Amway - SO10370 - Op QM v11 Install | Project Closure | Project Closure | Verint-oQM | 31600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/05/29 | 2013/07/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10370 | 834104 OS | 2013/05/31 | True | 2013/07/26
CDW - Comerica SO9679 License Update | Project Kick Off | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Planning & Design | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Readiness Validation | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Product Installation | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Product Integration | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Training | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Support Turnover | Project Closure |  | 500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/05/28 | 2013/05/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9679 | KAU6719 |  | True
CDW - Comerica SO9679 License Update | Project Closure | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 500 | 0 | 0 | 2013/05/28 | 2013/05/29 |  | 2013/05/20 |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9679 | KAU6719 |  | True
Siemens - Peoples Natural Gas SO10359 v11 WFO | Project Kick Off | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/06/17 | 2013/06/17 | 2013/06/17 | 2013/06/17 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Planning & Design | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/03 | 2013/07/03 | 2013/07/12 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Hardware / Software Procurement | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/08 | 2013/07/08 | 2013/07/08 | 2013/07/10 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Readiness Validation | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/09 | 2013/07/11 | 2013/07/09 | 2013/07/11 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Product Installation | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/15 | 2013/07/15 | 2013/07/19 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Product Integration | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/07/22 | 2013/07/22 | 2013/07/26 | 2013/07/26 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Training | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/12 | 2013/08/12 | 2013/08/16 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Consulting & Technical Reviews | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/12 | 2013/08/12 | 2013/08/19 | 2013/08/19 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Support Turnover | Project Closure |  | 48800 | 0 | Stewart Futcher | 100 | 48800 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/08/26 | 2013/08/19 | 2013/08/26 | 2013/08/30 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Siemens - Peoples Natural Gas SO10359 v11 WFO | Project Closure | Project Closure |  | 48800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/05/30 | 2013/09/25 | 2013/09/20 | 2013/09/24 | 2013/09/20 | 2013/09/24 | Stewart Futcher | [7 empty] | True | Mark Steve | 10359 | 7700240086 | 2013/04/29 | True | 2013/08/26
Coventry Management Services - SO10373 - PCIE Remote Install | Project Kick Off | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/05/31 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Planning & Design | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/15 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/15 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Product Installation | Project Closure |  | 1000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/25 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Coventry Management Services - SO10373 - PCIE Remote Install | Project Closure | Project Closure |  | 1000 | 0 | Philip Haskings | 100 | 1000 | 0 | 0 | [5 empty] | 2013/07/26 | Philip Haskings | [7 empty] | True |  | 10373 | 108000000016130 | 2013/05/31 | True | 2013/07/31
Verint - AAA NC SO10402 Card Issues - John R | Project Kick Off | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Planning & Design | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Hardware / Software Procurement | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Readiness Validation | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Product Installation | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Product Integration | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Training | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Consulting & Technical Reviews | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Support Turnover | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Verint - AAA NC SO10402 Card Issues - John R | Project Closure | Project Closure |  | 7200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/06/03 | 2013/06/07 |  |  |  |  | John Randall | [7 empty] | False |  | 10402 | P13-10297 | 2013/05/31 | True | 2013/06/24
Siemens - Medstar Health - SO10404 License Addition | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/06/10 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
Siemens - Medstar Health - SO10404 License Addition | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/06/07 | 2013/06/12 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10404 | 7700240166 | 2013/06/07 | True | 2013/08/28
CDW - Comerica - SO10300 Training | Project Kick Off | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Planning & Design | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Hardware / Software Procurement | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Readiness Validation | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Product Installation | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Product Integration | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Training | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Consulting & Technical Reviews | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Support Turnover | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10300 | 10184-2 | 2013/06/07 | False
CDW - Comerica - SO10300 Training | Project Closure | Project Closure | Verint-oQM | 0 | 0 | Tim Johnson | 100 | 0 | 0 | 0 | 2013/06/07 | 2013/06/14 |  |  |  | 2013/06/28 | Tim Johnson | [7 empty] | True |  | 10300 | 10184-2 | 2013/06/07 | False
City of Chicago - SO11678 - SSL Enablement | Project Kick Off | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  | 2014/03/20 | Tim Johnson | [7 empty] | True | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Planning & Design | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 50 | 5175 | 0 | 0 | 2014/03/25 | 2014/05/30 |  | 2014/03/20 | 2014/04/11 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Hardware / Software Procurement | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Readiness Validation | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Product Installation | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Product Integration | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 50 | 5175 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/03/31 |  | 2014/05/16 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Training | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Consulting & Technical Reviews | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Support Turnover | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
City of Chicago - SO11678 - SSL Enablement | Project Closure | 2 - Planning & Design |  | 10350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/21 |  | 2014/04/30 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11678 | 4521717439 | 2014/03/24 | False
Avista - SO11661 - Cutover Support | Support Turnover | 8 - Consulting & Technical Reviews |  | 3800 | 0 | Stewart Futcher | 100 | 3800 | 0 | 0 | 2014/03/26 | 2014/04/04 |  |  | 2014/04/04 |  | Stewart Futcher | [7 empty] | False | Susan Anderson | 11661 | 213614 | 2014/03/20 | False
Avista - SO11661 - Cutover Support | Project Closure | 8 - Consulting & Technical Reviews |  | 3800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/26 | 2014/04/04 |  |  |  |  | Tim Johnson | [7 empty] | False | Susan Anderson | 11661 | 213614 | 2014/03/20 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Project Kick Off | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/22 |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Planning & Design | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 25 | 1287.5 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/04/22 |  | 2014/04/25 |  | Rebecca Chaussinand | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Hardware / Software Procurement | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Readiness Validation | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/01 |  | 2014/05/02 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Product Installation | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/05 |  | 2014/05/06 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Training | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 75 | 3862.5 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/28 |  | 2014/05/30 |  | Rebecca Chaussinand | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Futuredontics - SO11685 - Upgrade 10.0.6 and delta training | Project Closure | 1 - Project Kick Off |  | 5150 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 | 2014/05/30 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | Mike Windler | 11685 | Signed SOW | 2014/03/25 | False
Google Lab Implementation - Jon Sant | Project Kick Off | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Planning & Design | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 25 | 11200 | 0 | 0 |  |  |  |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Hardware / Software Procurement | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Readiness Validation | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Product Installation | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Product Integration | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 50 | 11200 | 0 | 0 |  |  |  |  | 2014/05/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Training | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Consulting & Technical Reviews | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Support Turnover | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 25 | 11200 | 0 | 0 |  |  |  |  | 2014/06/28 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Google Lab Implementation - Jon Sant | Project Closure | 1 - Project Kick Off |  | 11200 | 11200 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Project Kick Off | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/09 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Planning & Design | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Hardware / Software Procurement | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Product Integration | Project Closure |  | 500 | 500 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  | 2014/01/31 | 2014/01/30 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
SCANA - SO11255 - PCIe 120/96 Digi Remote Install | Project Closure | Project Closure |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/01/31 |  |  |  | 2014/01/30 | Philip Haskings | [7 empty] | True | ALAN BOONE | 11255 | SC-1100014054 | 2013/12/06 | False
Bluegreen - SO11254 - GM Installation | Project Kick Off | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Planning & Design | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Hardware / Software Procurement | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Readiness Validation | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Product Installation | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Product Integration | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Training | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Support Turnover | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Bluegreen - SO11254 - GM Installation | Project Closure | 2 - Planning & Design |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/09 | 2014/05/30 |  |  | 2014/05/31 |  | Tim Johnson | [7 empty] | False | Justin Reynolds | SO11254 | 69594 | 2013/12/05 | False
Memphis Light, Gas and Water - SO11247 | Project Kick Off | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/04 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Planning & Design | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Product Integration | Project Closure |  | 3500 | 0 | Philip Haskings | 100 | 3500 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
Memphis Light, Gas and Water - SO11247 | Project Closure | Project Closure |  | 3500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Jon Barlow | 11247 | APP1323718 | 2013/12/04 | False
AtlantiCare - SO11277 - Onsite Installation | Project Kick Off | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Planning & Design | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Hardware / Software Procurement | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Product Installation | Project Closure |  | 4000 | 4000 | Philip Haskings | 100 | 4000 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
AtlantiCare - SO11277 - Onsite Installation | Project Closure | Project Closure |  | 4000 | 4000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | Dawn Collins | 11277 | 3487474 | 2013/12/09 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Project Kick Off | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Planning & Design | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Hardware / Software Procurement | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Readiness Validation | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Product Installation | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Product Integration | Project Closure |  | 18000 | 18000 | John Randall | 100 | 18000 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/21 | John Randall | [7 empty] | True | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Training | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Consulting & Technical Reviews | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Support Turnover | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
HSBC - SO11285 - Canada TOR-VAN TopLayer_Shormicro 1G-Copper | Project Closure | Project Closure |  | 18000 | 18000 | John Randall | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Elton Zhou | 11285 | D07071730 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Project Kick Off | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/01/09 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Planning & Design | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Hardware / Software Procurement | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Readiness Validation | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Product Installation | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  |  | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Product Integration | Project Closure |  | 14500 | 14500 | Philip Haskings | 100 | 14500 | 0 | 0 | 2013/12/11 | 2014/03/14 |  |  | 2014/03/07 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Consulting & Technical Reviews | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 | 2014/03/03 |  | 2014/03/03 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Nissan NMAC - SO11290 - Onsite QM v7.8 Lab Install | Project Closure | Project Closure |  | 14500 | 14500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/14 | 2014/03/14 |  | 2014/03/14 | 2014/02/27 | Philip Haskings | [7 empty] | True | Paula Sterling | 11290 | 7700244461 | 2013/12/10 | False
Amway - SO11094 - GM Installation | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Support Turnover | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  |  | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Amway - SO11094 - GM Installation | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/26 | Philip Haskings | [7 empty] | True | Ron Neihoff | 11094 | 871037 | 2013/11/01 | False
Medstar - SO11299 - 12 Additional Licenses | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  |  | 2014/03/25 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/27 | 2014/03/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Medstar - SO11299 - 12 Additional Licenses | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | Philip Haskings | [7 empty] | True | Charlie Jung | 11299 | 7700244582 | 2013/12/11 | False
Level One - SO9944 QM Training - Verint Services | Project Kick Off | Project Closure |  | 3100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Level One - SO9944 QM Training - Verint Services | Training | Project Closure |  | 3100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Level One - SO9944 QM Training - Verint Services | Project Closure | Project Closure |  | 3100 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/02/22 | 2013/02/27 |  |  |  | 2013/03/27 | Philip Haskings | [7 empty] | True |  | 9944 | NC130027
Medical Mutual - SO9946 Remote Config | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9946 | MMO65691
Medical Mutual - SO9946 Remote Config | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/02/22 | 2013/02/01 |  |  |  | 2013/03/29 | Philip Haskings | [7 empty] | True |  | 9946 | MMO65691
MolDev - SO9595 - Russia HCS Quest 64 | Project Kick Off | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Planning & Design | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Hardware / Software Procurement | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Product Installation | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Product Integration | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Support Turnover | Project Closure |  | 4995 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9595 - Russia HCS Quest 64 | Project Closure | Project Closure |  | 4995 | 0 | Philip Haskings | 100 | 4995 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9595 | 41128204 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Project Kick Off | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Planning & Design | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Hardware / Software Procurement | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Product Installation | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Product Integration | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Support Turnover | Project Closure |  | 9990 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
MolDev - SO9762 - Russia HCS Quest 64 plus Screen 10 (2 Servers) | Project Closure | Project Closure |  | 9990 | 0 | Philip Haskings | 100 | 9990 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9762 | 40103202 |  | True
Nissan North America - SO9975 Irving TX Onsite | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/02 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Nissan North America - SO9975 Irving TX Onsite | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/03/04 | 2013/03/08 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9975 | 7400060096 | 2013/04/03 | True | 2013/07/08
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Project Kick Off | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Planning & Design | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Hardware / Software Procurement | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Readiness Validation | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Product Installation | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Product Integration | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Training | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Consulting & Technical Reviews | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Support Turnover | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Morgan & Morgan - SO11446 - 50 x V7.8 oWFO Licenses | Project Closure | 1 - Project Kick Off |  | 7600 | 7600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | David McKeon | 11446 | 36400477-01 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Project Kick Off | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/24 |  | 2014/01/24 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Planning & Design | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/24 |  | 2014/01/24 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Product Integration | Project Closure |  | 700 | 700 | Philip Haskings | 100 | 700 | 0 | 0 | 2014/01/23 | 2014/01/31 |  | 2014/01/25 | 2014/02/03 | 2014/01/25 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Pittsburgh Glass Works - SO11443 - Remote services - Assist moving and mapping DP6409 cards | Project Closure | Project Closure |  | 700 | 700 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/01/31 |  |  |  | 2014/02/03 | Philip Haskings | [7 empty] | True | Shonda Riley | 11443 | AGSIR06908 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Project Kick Off | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Planning & Design | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Hardware / Software Procurement | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Product Integration | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 100 | 6600 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/03/18 |  | Philip Haskings | [7 empty] | False | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Charter - SO11445 -Bridgeton MO-Voice Screen Recorders - Onsite Install | Project Closure | 6 - Product Integration |  | 6600 | 6600 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Drew Stelling | 11445 | 1775784 | 2014/01/22 | False
Google - SO11457 | Project Kick Off | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Planning & Design | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Hardware / Software Procurement | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Readiness Validation | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Product Installation | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Product Integration | Project Closure |  | 4800 | 0 | Stewart Futcher | 100 | 4800 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  | 2014/02/28 | 2014/02/25 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Training | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Consulting & Technical Reviews | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Support Turnover | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
Google - SO11457 | Project Closure | Project Closure |  | 4800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 11457 | 5010540 | 2014/01/23 | False
United BioSource a divisio of Express Scripts l OEM | Project Kick Off | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Planning & Design | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Readiness Validation | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Product Installation | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Product Integration | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Training | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Support Turnover | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
United BioSource a divisio of Express Scripts l OEM | Project Closure | 1 - Project Kick Off |  | 0 | 18400 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Project Kick Off | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Planning & Design | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Readiness Validation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Product Installation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Product Integration | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 100 | 6700 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Training | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Support Turnover | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11504 - Overland Park - E1/T1 Tap Panel/Server - Onsite, Weekend Installation | Project Closure | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/13 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11504 | OH 4000606 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Project Kick Off | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Planning & Design | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Readiness Validation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Product Installation | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Product Integration | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 100 | 6700 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Training | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Support Turnover | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
UBC - SO11505 - Kansas City - T1/E1 Panel/Server Onsite, Weekend Installation | Project Closure | 1 - Project Kick Off |  | 6700 | 13400 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dan Koehn | 11505 | OH 4000604 | 2014/02/07 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Project Kick Off | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Planning & Design | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Hardware / Software Procurement | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Product Installation | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  |  | 2014/03/08 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Product Integration | Project Closure |  | 750 | 750 | Philip Haskings | 100 | 750 | 0 | 0 | 2014/02/04 | 2014/03/31 | 2014/03/19 |  | 2014/03/20 | 2014/03/20 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Henry Ford Health System - SO 11422 Remote Dialogic | Project Closure | Project Closure |  | 750 | 750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/03/31 |  |  | 2014/03/28 | 2014/03/31 | Philip Haskings | [7 empty] | True | Mike Chisholm | 11422 | 0011550972 | 2014/02/03 | False
Questar - SO11489 - DPA | Project Kick Off | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Planning & Design | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Hardware / Software Procurement | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Readiness Validation | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Product Installation | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Product Integration | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 100 | 30600 | 0 | 0 | 2014/02/03 | 2014/02/07 | 2014/04/07 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Training | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Consulting & Technical Reviews | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Support Turnover | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Questar - SO11489 - DPA | Project Closure | 1 - Project Kick Off |  | 30600 | 30600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/03 | 2014/02/07 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matthew Goodman | 11489 | 23085 | 2014/02/03 | False
Weber Stephen Products - SO11468 - oWFM | Project Kick Off | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Planning & Design | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Hardware / Software Procurement | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Readiness Validation | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Product Installation | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Product Integration | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Training | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Support Turnover | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Weber Stephen Products - SO11468 - oWFM | Project Closure | 1 - Project Kick Off |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Glen Sowa | 11468 | PTRK01314500 | 2014/01/27 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Project Kick Off | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  | 2014/02/20 |  | 2014/02/20 | Tim Johnson | [7 empty] | True | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Planning & Design | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Hardware / Software Procurement | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Readiness Validation | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Product Installation | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Product Integration | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Training | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Consulting & Technical Reviews | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Support Turnover | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 100 | 44420 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  | 2014/06/20 |  | Charlene Dennis | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Verizon - SO11477 - oRec v7.8 + Import Manager | Project Closure | 2 - Planning & Design |  | 44420 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/10 | 2014/06/06 |  |  |  |  | Tim Johnson | [7 empty] | False | Patricia White | 11477 | LLD2963 | 2014/01/30 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Project Kick Off | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Planning & Design | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 25 | 5850 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/04/11 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Hardware / Software Procurement | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Readiness Validation | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Product Installation | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Product Integration | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 50 | 11700 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/05/09 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Training | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Consulting & Technical Reviews | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Support Turnover | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 25 | 5850 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  | 2014/06/06 |  | Stewart Futcher | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Roanoke Gas - SO11510 - oRec- 40 seats + Adtech server | Project Closure | 1 - Project Kick Off |  | 23400 | 28000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dale Harless | 11510 | 220237 | 2014/02/10 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Project Kick Off | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Planning & Design | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Hardware / Software Procurement | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Readiness Validation | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Product Installation | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Product Integration | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  | 2014/04/01 |  | Philip Haskings | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Training | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Consulting & Technical Reviews | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Support Turnover | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Healthgrades - SO11471 - Add 7 seats for oWFM + TOM | Project Closure | 6 - Product Integration |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/12 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | John Klein | 11471 | LMG0307 | 2014/02/11 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Project Kick Off | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/14 | 2014/03/14 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Planning & Design | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 25 | 3600 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/12 | 2014/03/12 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Hardware / Software Procurement | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/10 | 2014/03/05 | 2014/03/14 | 2014/03/14 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Readiness Validation | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/14 |  | 2014/03/17 | 2014/03/21 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Product Installation | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/24 |  | 2014/03/28 | 2014/03/26 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Product Integration | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 50 | 7200 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/03/24 |  | 2014/03/28 | 2014/03/28 | Rebecca Chaussinand | [7 empty] | True | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Training | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/21 |  | 2014/04/25 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Consulting & Technical Reviews | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/21 |  |  |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Support Turnover | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 25 | 3600 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/28 |  | 2014/04/30 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
Chesapeake Bank -SO11523 - oREC 12 Seats | Project Closure | 7 - Training |  | 14400 | 14528 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/06/20 | 2014/04/30 |  | 2014/04/30 |  | Rebecca Chaussinand | [7 empty] | False | Toni Harrison | 11523 | 3210 | 2014/02/14 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Project Kick Off | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  |  | 2014/02/27 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Planning & Design | 5 - Product Installation |  | 220000 | 0 | John Randall | 50 | 110000 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  | 2014/02/28 | 2014/02/28 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Hardware / Software Procurement | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  |  | 2014/04/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Readiness Validation | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/04/07 | 2014/04/10 | 2014/04/07 | 2014/04/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Product Installation | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/04/10 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Product Integration | 5 - Product Installation |  | 220000 | 0 | John Randall | 50 | 110000 | 0 | 0 | 2014/02/20 | 2014/05/30 |  |  | 2014/05/30 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Training | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/05/12 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Consulting & Technical Reviews | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Support Turnover | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 1: Speech | Project Closure | 5 - Product Installation |  | 220000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/05/30 | 2014/06/09 |  | 2014/06/09 |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
Charter - SO11502 - F5 Implementation | Project Kick Off | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  | 2014/02/21 |  | 2014/02/21 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Planning & Design | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  | 2014/02/21 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/21 | 2014/02/21 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Readiness Validation | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/24 | 2014/02/24 | 2014/02/24 | 2014/02/24 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Product Installation | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/25 | 2014/02/25 | 2014/02/26 | 2014/02/25 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Product Integration | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/26 | 2014/02/25 | 2014/02/26 | 2014/02/25 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Training | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 | 2014/02/26 | 2014/02/26 | 2014/02/26 | 2014/02/26 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/02/26 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Support Turnover | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/03/12 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Charter - SO11502 - F5 Implementation | Project Closure | Project Closure |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/02/18 | 2014/03/14 |  |  |  | 2014/03/12 | Tim Johnson | [7 empty] | True | Douglas Rose | 11502 | 10260 | 2014/02/12 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Project Kick Off | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Planning & Design | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Training | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 100 | 1150 | 0 | 0 | 2014/02/19 | 2014/04/30 | 2014/04/21 |  | 2014/04/21 |  | Philip Haskings | [7 empty] | False | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Citizens Bank - SO11524 - Remote training for v9.3 Express | Project Closure | 3 - Hardware / Software Procurement |  | 1150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/19 | 2014/04/30 |  |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Dorann Morris | 11524 | Credit Card | 2014/02/14 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Project Kick Off | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  | 2014/02/17 | Philip Haskings | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Planning & Design | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Product Integration | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 100 | 16750 | 0 | 0 | 2014/02/20 | 2014/03/31 | 2014/03/23 |  | 2014/03/27 |  | Philip Haskings | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
Express Scripts -SO11540 - Services - Onsite Weekend - Tampa | Project Closure | 3 - Hardware / Software Procurement |  | 16750 | 16750 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Laura Stern | 11540 | 1011025 | 2014/02/19 | False
HSBC - PM - July 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
HSBC - PM - July 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/07/01 | 2014/07/31 |  |  | 2014/07/31 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/07/01 | False
Nissan - SO11528 - Remote Services | Project Kick Off | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Planning & Design | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Hardware / Software Procurement | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Product Integration | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
Nissan - SO11528 - Remote Services | Project Closure | 4 - Readiness Validation |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/04/30 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Bonnie Lord | 11528 | 740006930 | 2014/02/14 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Project Kick Off | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Planning & Design | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 50 | 106000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/02/28 | 2014/02/28 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Readiness Validation | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Product Installation | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Product Integration | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 50 | 106000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/05/16 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Training | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Support Turnover | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 2: DPA | Project Closure | 3 - Hardware / Software Procurement |  | 212000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Project Kick Off | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Planning & Design | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 50 | 90000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/03/31 | 2014/03/24 | John Randall | [7 empty] | True | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Readiness Validation | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Product Installation | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Product Integration | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 50 | 90000 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  | 2014/06/20 |  | John Randall | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Training | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Support Turnover | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
CMS Medicare - SO11536 - Analytics Part 3: Adv. Scorecards | Project Closure | 3 - Hardware / Software Procurement |  | 180000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/02/20 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11536 | 0000016423 | 2014/02/20 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Project Kick Off | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/11 | 2014/03/11 | 2014/03/11 | 2014/03/11 | Stewart Futcher | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Planning & Design | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 50 | 44675 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/24 | 2014/03/24 | 2014/03/28 | 2014/03/31 | Stewart Futcher | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Hardware / Software Procurement | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/17 | 2014/03/17 | 2014/03/17 | 2014/03/18 | Tim Johnson | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Readiness Validation | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/03/31 | 2014/04/01 | 2014/03/31 | 2014/04/07 | Tim Johnson | [7 empty] | True | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Product Installation | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/04/08 | 2014/04/08 | 2014/04/18 |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Product Integration | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 50 | 44675 | 0 | 0 | 2014/03/03 | 2014/06/30 | 2014/04/08 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Training | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Consulting & Technical Reviews | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Support Turnover | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
SWBC - SO11576 - Avaya v12 oWFM + AIM 1400 total seats, 650-seat Expansion | Project Closure | 5 - Product Installation |  | 89350 | 92825 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Kroner | 11576 | 161871 | 2014/02/26 | False
McKesson - SOxxxx - Radware Implementation | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Training | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
McKesson - SOxxxx - Radware Implementation | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Donna Edwards |  | 123456 | 2014/04/30 | False
Verint PMO Revenue - June 2014 | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - June 2014 | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Project Kick Off | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Planning & Design | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Readiness Validation | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Product Installation | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Product Integration | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Training | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Consulting & Technical Reviews | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Support Turnover | Project Closure |  | 1000 | 1000 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - June 2014 | Project Closure | Project Closure |  | 1000 | 1000 | Kent Pylant | 100 | 1000 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Pleasant Holidays - SO11617 - ODBC Drivers | Product Integration | Project Closure |  | 1000 | 0 | Rebecca Chaussinand | 100 | 1000 | 0 | 0 | 2014/03/06 | 2014/03/14 |  | 2014/03/07 | 2014/03/21 | 2014/03/07 | Rebecca Chaussinand | [7 empty] | True | Heather Gault | 11617 | 159029 | 2014/03/06 | False
Pleasant Holidays - SO11617 - ODBC Drivers | Project Closure | Project Closure |  | 1000 | 0 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/06 | 2014/03/14 |  |  |  | 2014/03/19 | Rebecca Chaussinand | [7 empty] | True | Heather Gault | 11617 | 159029 | 2014/03/06 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Project Kick Off | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 34 | 7480 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/21 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Planning & Design | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Hardware / Software Procurement | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Readiness Validation | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Product Installation | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 33 | 7260 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/24 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Product Integration | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Consulting & Technical Reviews | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 33 | 7260 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/03/31 | 2014/03/31 | Philip Haskings | [7 empty] | True | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
Flagstar Bank - SO11630 - PCI Encryption and QM addition - 581 seats | Project Closure | 9 - Support Turnover |  | 22000 | 21900 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/11 | 2014/03/28 |  |  | 2014/06/20 |  | Philip Haskings | [7 empty] | False | Andy Langlois | 11630 | 000030000018210 | 2014/03/11 | False
NMAC - SO11637 - Remote Services | Project Kick Off | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Planning & Design | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Hardware / Software Procurement | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Product Integration | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 100 | 375 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
NMAC - SO11637 - Remote Services | Project Closure | 4 - Readiness Validation |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/12 | 2014/04/30 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Paula Sterling | 11637 | 7400067036 | 2014/03/12 | False
Iron Mountain - SO11645 - WFO Onsite Training | Project Kick Off | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/05/30 |  |  |  | 2014/03/25 | Tim Johnson | [7 empty] | True | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Iron Mountain - SO11645 - WFO Onsite Training | Training | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 100 | 6200 | 0 | 0 | 2014/03/18 | 2014/05/30 | 2014/04/01 |  | 2014/04/03 |  | Rebecca Chaussinand | [7 empty] | False | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Iron Mountain - SO11645 - WFO Onsite Training | Project Closure | 2 - Planning & Design |  | 6200 | 6200 | Rebecca Chaussinand | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/05/30 |  |  | 2014/04/30 |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11645 | P16947 | 2014/03/14 | False
Nissan North America - SO11605 - Change Order | Project Kick Off | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Planning & Design | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  | 2014/03/27 | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Hardware / Software Procurement | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/20 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Product Integration | Project Closure |  | 4000 | 0 | Philip Haskings | 100 | 4000 | 0 | 0 | 2014/03/18 | 2014/04/30 | 2014/03/20 | 2014/03/20 | 2014/03/21 | 2014/03/31 | Philip Haskings | [7 empty] | True | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Nissan North America - SO11605 - Change Order | Project Closure | Project Closure |  | 4000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/18 | 2014/04/30 |  |  |  | 2014/03/31 | Philip Haskings | [7 empty] | False | Paula Sterling | 11605 | 7700246584 | 2014/03/05 | False
Wide Open West SO11652 - Avaya QM Services | Project Kick Off | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Planning & Design | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 25 | 2321.25 | 0 | 0 |  |  |  |  | 2014/04/18 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Hardware / Software Procurement | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Readiness Validation | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Product Installation | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Product Integration | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 50 | 4642.5 | 0 | 0 |  |  |  |  | 2014/04/30 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Training | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Consulting & Technical Reviews | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Support Turnover | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 25 | 2321.25 | 0 | 0 |  |  |  |  | 2014/06/18 |  | Kent Pylant | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Wide Open West SO11652 - Avaya QM Services | Project Closure | 1 - Project Kick Off |  | 9285 | 9285 | Kent Pylant | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False | Tracy Fleming | 11652 | 4521716813 | 2014/03/17 | False
Texas Guarantee - SO11646 - Avaya oQM services | Project Kick Off | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Planning & Design | 7 - Training |  | 137682 | 137682 | Kent Pylant | 25 | 34420.5 | 0 | 0 | 2014/03/10 | 2014/03/31 |  | 2014/02/24 | 2014/03/28 | 2014/03/06 | Kent Pylant | [7 empty] | True | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Hardware / Software Procurement | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Readiness Validation | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Product Installation | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Product Integration | 7 - Training |  | 137682 | 137682 | Kent Pylant | 50 | 68841 | 0 | 0 | 2014/03/10 | 2014/03/31 |  | 2014/03/08 | 2014/03/31 | 2014/03/31 | Kent Pylant | [7 empty] | True | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Training | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Consulting & Technical Reviews | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Support Turnover | 7 - Training |  | 137682 | 137682 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/10 | 2014/03/31 |  |  | 2014/06/18 |  | Kent Pylant | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
Texas Guarantee - SO11646 - Avaya oQM services | Project Closure | 7 - Training |  | 137682 | 137682 | Kent Pylant | 25 | 34420.5 | 0 | 0 | 2014/03/10 | 2014/03/31 | 2014/05/01 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | V.K. Bhandari | 11646 | 452171661 | 2014/03/14 | False
QT11141 Nissan Smyrna | Project Kick Off | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Planning & Design | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 25 | 750 | 0 | 0 |  |  |  |  | 2014/04/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Hardware / Software Procurement | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Readiness Validation | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Product Installation | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Product Integration | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 50 | 750 | 0 | 0 |  |  |  |  | 2014/05/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Training | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Consulting & Technical Reviews | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Support Turnover | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 25 | 750 | 0 | 0 |  |  |  |  | 2014/06/18 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11141 Nissan Smyrna | Project Closure | 1 - Project Kick Off |  | 750 | 750 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
MedImpact - SO11659 - Additional Recorder and PCI | Project Kick Off | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Planning & Design | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 25 | 2750 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/04/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Hardware / Software Procurement | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Readiness Validation | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Product Installation | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Product Integration | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 50 | 5500 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/05/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Training | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Consulting & Technical Reviews | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Support Turnover | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 25 | 2750 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Philip Haskings | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
MedImpact - SO11659 - Additional Recorder and PCI | Project Closure | 1 - Project Kick Off |  | 11000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11659 | 291842 | 2014/03/19 | False
Charter - GM as part of Platinum Support | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 25 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 50 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/05/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Training | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 25 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  | 2014/06/24 |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
Charter - GM as part of Platinum Support | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/03/25 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chris Schmoker | 12345 | 12345 | 2013/10/01 | False
The Jay Group - SO9980 - Troubleshooting CT Connect | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/04 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
The Jay Group - SO9980 - Troubleshooting CT Connect | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | [5 empty] | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9980 | 980001 |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Project Kick Off | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Planning & Design | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/06 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Hardware / Software Procurement | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Readiness Validation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Product Installation | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Product Integration | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Support Turnover | Project Closure |  | 7050 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Amway - SO9984 - DP6409 E1/T1 Tap Panel - Onsite | Project Closure | Project Closure |  | 7050 | 0 | Philip Haskings | 100 | 7050 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 9984 | 814528OC |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/03/18 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/03 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
Progressive Casualty Insurance - SO10009 Dialogic Install Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/03/11 | 2013/03/14 |  |  |  | 2013/05/22 | Philip Haskings | [7 empty] | True |  | 10009 | 639011 |  | True
CDW - AFNI - SO9988 Server Builds (Bobby D) | Project Kick Off | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Planning & Design | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Hardware / Software Procurement | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Product Installation | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Product Integration | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Support Turnover | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 4800 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
CDW - AFNI - SO9988 Server Builds (Bobby D) | Project Closure | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/03/01 | 2013/03/11 |  |  |  | 2013/03/27 | Kent Pylant | [7 empty] | True |  | 9988 | 00003-0000014388
Siemens - Academy Sports - SO9893 - Remote License Install | Project Kick Off | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Planning & Design | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/15 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Product Installation | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Product Integration | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Support Turnover | Project Closure |  | 350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
Siemens - Academy Sports - SO9893 - Remote License Install | Project Closure | Project Closure |  | 350 | 0 | Philip Haskings | 100 | 350 | 0 | 0 | [5 empty] | 2013/04/10 | Philip Haskings | [7 empty] | True | Mike Kinard | 9893 | 7700238025 |  | True
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Project Kick Off | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Planning & Design | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Hardware / Software Procurement | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Readiness Validation | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Product Installation | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Product Integration | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Training | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Consulting & Technical Reviews | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Support Turnover | Project Closure |  | 1600 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10041 | KIJ7575 |  | True | 2013/06/03
CDW - Brady Corp. SO10041 - v7.8.3 Upgrade | Project Closure | Project Closure |  | 1600 | 0 | Stewart Futcher | 100 | 1600 | 0 | 0 | 2013/03/19 | 2013/03/22 |  |  |  | 2013/06/03 | Stewart Futcher | [7 empty] | True |  | 10041 | KIJ7575 |  | True | 2013/06/03
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/20 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
APAC - SO10050 PCI Exp D480 Onsite Install |  | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 10050 | 4500000074 |  | True
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/03/20 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10047 Ft. Worth - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/29 | Philip Haskings | [7 empty] | True | Switchboard | 10047 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/03/20 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/29 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Express Scripts - SO10048 Franklin Lakes - HW Move |  | Project Closure | Hardware Install / Config | 6700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/11/30 |  |  |  | 2013/12/09 | Philip Haskings | [7 empty] | True | Switchboard | 10048 | PPR000000049465 | 2013/03/18 | False
Nissan North America - SO10063 analog hardware - Atlanta | Project Kick Off | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/03/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Planning & Design | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/03/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Hardware / Software Procurement | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Product Installation | Project Closure |  | 2350 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/19 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Nissan North America - SO10063 analog hardware - Atlanta | Project Closure | Project Closure |  | 2350 | 0 | Philip Haskings | 100 | 2350 | 0 | 0 | 2013/03/25 | 2013/04/29 |  |  |  | 2013/07/22 | Philip Haskings | [7 empty] | True |  | 10063 | 7400060287 | 2013/03/25 | True | 2013/07/30
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Project Kick Off | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Planning & Design | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/03/26 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Product Integration | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Support Turnover | Project Closure |  | 700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/04/30 | Philip Haskings | [7 empty] | True |  | 100066 | 4500252087 |  | True
Hydro One Networks - SO10066 - D480 Remote After Hours Install | Project Closure | Project Closure |  | 700 | 0 | Philip Haskings | 100 | 700 | 0 | 0 | [5 empty] | 2013/05/01 | Tim Johnson | [7 empty] | True |  | 100066 | 4500252087 |  | True
Healthgrades - SO11115 - Addition of 20 Licenses | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
Healthgrades - SO11115 - Addition of 20 Licenses | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
Healthgrades - SO11115 - Addition of 20 Licenses | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/03/31 |  |  |  | 2014/03/13 | Philip Haskings | [7 empty] | True | John Klein | 11115 | LEH2519 | 2013/11/06 | False
HEB Grocery - SO11127 - oQM | Project Kick Off | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 | 2013/11/20 |  | 2013/11/22 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Planning & Design | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Hardware / Software Procurement | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Readiness Validation | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Product Installation | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2013/12/23 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Product Integration | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 100 | 25600 | 0 | 0 | 2013/11/08 | 2014/01/31 | 2014/03/17 | 2014/03/18 | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Training | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Consulting & Technical Reviews | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Support Turnover | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
HEB Grocery - SO11127 - oQM | Project Closure | 6 - Product Integration |  | 25600 | 25600 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/08 | 2014/01/31 |  |  | 2014/01/10 |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11127 | 7700243930 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Project Kick Off | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  | 2013/11/15 |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Planning & Design | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Hardware / Software Procurement | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Product Integration | Project Closure |  | 6700 | 6700 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11109 Memphis - Installation of DP 6409 After Hours | Project Closure | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Laura Stern | 11109 | 1005602 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Project Kick Off | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Planning & Design | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Hardware / Software Procurement | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Product Integration | Project Closure |  | 6700 | 6700 | Philip Haskings | 100 | 6700 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Express Scripts - SO11106 Ft Worth - Installation of DP6409 After Hours | Project Closure | Project Closure |  | 6700 | 6700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2013/12/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Laura Stern | 11106 | 1005601 | 2013/11/07 | False
Wellpoint - SO11131 - D480 Replacement | Project Kick Off | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/11/13 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Hardware / Software Procurement | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Product Integration | Project Closure |  | 6500 | 6500 | Philip Haskings | 100 | 6500 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Wellpoint - SO11131 - D480 Replacement | Project Closure | Project Closure |  | 6500 | 6500 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/11 | 2014/01/31 |  |  |  | 2013/12/31 | Philip Haskings | [7 empty] | True | Tim Lindy | 11131 | 0005015409 | 2013/11/08 | False
Verint MAC Revenue - March 2014 | Project Kick Off | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Planning & Design | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Hardware / Software Procurement | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Readiness Validation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Product Installation | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Product Integration | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Training | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Consulting & Technical Reviews | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - March 2014 | Support Turnover | Project Closure |  | 0 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/03 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Project Kick Off | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Planning & Design | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Hardware / Software Procurement | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Readiness Validation | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Product Installation | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Product Integration | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Training | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Consulting & Technical Reviews | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Support Turnover | Project Closure |  | 7000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint PMO Revenue - April 2014 | Project Closure | Project Closure |  | 7000 | 0 | Kent Pylant | 100 | 7000 | 0 | 0 | 2014/04/01 | 2014/04/30 | 2014/04/01 | 2014/04/01 | 2014/04/30 | 2014/04/30 | Kent Pylant | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
Verint MAC Revenue - April 2014 | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/04/01 | 2014/04/30 | 2014/04/01 | 2014/04/01 | 2014/04/30 | 2014/04/30 | Kent Pylant | [7 empty] | False | Tim Prince | 99999 | 99999 | 2014/02/03 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Project Kick Off | Project Closure |  | 17875 | 0 | Philip Haskings | 25 | 4468.75 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2013/12/31 | 2013/12/11 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Planning & Design | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/12 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Hardware / Software Procurement | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/14 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Readiness Validation | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/15 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Product Installation | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  |  | 2013/11/22 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Product Integration | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2013/12/13 | 2014/02/27 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Training | Project Closure |  | 17875 | 0 | Philip Haskings | 50 | 8937.5 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/14 | 2014/02/27 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Consulting & Technical Reviews | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/07 |  | Philip Haskings | [7 empty] | False | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Support Turnover | Project Closure |  | 17875 | 0 | Philip Haskings | 25 | 4468.75 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/14 | 2014/04/07 | Philip Haskings | [7 empty] | True | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
PCNA - SO11153 - Verint v11.1 oRec/Compliance | Project Closure | Project Closure |  | 17875 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/12 | 2014/02/28 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Scott Miller | 11153 | LEY2470 | 2013/11/13 | False
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Project Kick Off | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Planning & Design | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Hardware / Software Procurement | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Readiness Validation | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Product Installation | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Product Integration | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Training | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Consulting & Technical Reviews | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Support Turnover | Project Closure |  | 6333 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9930 | 7700238024 |  | True
Siemens - FL Dept of Juvenile Justice - SO9930 Exp QM v9.3 | Project Closure | Project Closure |  | 6333 | 0 | Stewart Futcher | 100 | 6333 | 0 | 0 | 2013/02/20 | 2013/03/01 |  |  |  | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 9930 | 7700238024 |  | True
CDW - Comerica - SO7206 v7.8 Op QM | Project Kick Off | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  | 2013/01/01 |  | 2013/01/15 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Planning & Design | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Hardware / Software Procurement | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Readiness Validation | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Product Installation | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Product Integration | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Training | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Consulting & Technical Reviews | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Support Turnover | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  |  | 2013/09/18 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
CDW - Comerica - SO7206 v7.8 Op QM | Project Closure | Project Closure | Verint-oQM | 91892 | 0 | Tim Johnson | 100 | 91892 | 0 | 0 | 2013/01/01 | 2013/09/13 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 7206 | 8163 | 2012/01/01 | True | 2013/09/30
Region of York - SO11390 - Addtional Licenses | Project Kick Off | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 | 2014/01/10 | 2014/01/10 | 2014/01/10 | 2014/01/10 | Tim Johnson | [7 empty] | True | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Planning & Design | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Hardware / Software Procurement | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Readiness Validation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Product Installation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Product Integration | Project Closure |  | 500 | 500 | John Randall | 100 | 500 | 0 | 0 | 2014/01/09 | 2014/01/31 |  | 2014/01/29 | 2014/01/31 | 2014/01/31 | John Randall | [7 empty] | True | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Training | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Consulting & Technical Reviews | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Support Turnover | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
Region of York - SO11390 - Addtional Licenses | Project Closure | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/01/09 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Foster | 11390 | JMF090120141125 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Project Kick Off | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Planning & Design | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Hardware / Software Procurement | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Readiness Validation | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Product Installation | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Product Integration | Project Closure |  | 1600 | 7200 | Kent Pylant | 100 | 1600 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  | 2014/03/21 | 2014/03/31 | Kent Pylant | [7 empty] | True | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Training | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Consulting & Technical Reviews | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Support Turnover | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
HEB Grocery - SO11389 - Onsite Support | Project Closure | Project Closure |  | 1600 | 7200 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Geronimo Jorge | 11389 | 7700245155 | 2014/01/09 | False
Toyota - SO11393 - Training Credits | Project Kick Off | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  |  | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Planning & Design | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  |  | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Hardware / Software Procurement | Project Closure |  | 0 | 3128 | Philip Haskings | 100 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  | 2014/02/03 | 2014/01/23 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Toyota - SO11393 - Training Credits | Project Closure | Project Closure |  | 0 | 3128 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/02/07 |  |  | 2014/02/17 | 2014/02/26 | Philip Haskings | [7 empty] | True | Savio Correia | 11393 | 20007983 | 2014/01/10 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Project Kick Off | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/29 | 2014/01/29 | 2014/01/29 | 2014/01/29 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Planning & Design | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/29 | 2014/01/29 | 2014/01/29 | 2014/01/29 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Hardware / Software Procurement | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/01/30 |  | 2014/01/30 |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Readiness Validation | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Product Installation | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Product Integration | Project Closure |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/15 | 2014/03/31 |  | 2014/03/04 | 2014/03/07 | 2014/03/28 | John Randall | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Training | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Consulting & Technical Reviews | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Support Turnover | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Capital One - SO11405 - MDC CoreroLoadBalancer | Project Closure | Project Closure |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/15 | 2014/03/31 | 2014/02/07 |  | 2014/02/07 | 2014/03/28 | Tim Johnson | [7 empty] | True | Jim Vowell | 11405 | EPUS10000242800 | 2014/01/14 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Project Kick Off | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  | 2014/01/28 | 2014/02/03 | 2014/01/28 | Tim Johnson | [7 empty] | True | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Planning & Design | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Hardware / Software Procurement | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Readiness Validation | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Product Installation | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Product Integration | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Training | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Consulting & Technical Reviews | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Support Turnover | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 100 | 6400 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  | 2014/05/16 |  | Charlene Dennis | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Medstar - SO11442 - oQM UMH GCOA - 35 seats | Project Closure | 2 - Planning & Design |  | 6400 | 8400 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/23 | 2014/05/09 |  |  |  |  | Tim Johnson | [7 empty] | False | John Valentine | 11442 | 7700245329 | 2014/01/22 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Project Kick Off | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/01/28 |  | 2014/01/28 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Planning & Design | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 25 | 8775 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/17 | 2014/02/07 | 2014/02/17 | Charlene Dennis | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Hardware / Software Procurement | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/18 |  | 2014/02/18 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Readiness Validation | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 |  | 2014/02/21 |  | 2014/02/21 | Tim Johnson | [7 empty] | True | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Product Installation | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/02/24 | 2014/02/24 | 2014/03/27 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Product Integration | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 50 | 17550 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/03/17 |  | 2014/03/31 |  | Charlene Dennis | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Training | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/03/26 |  | 2014/03/31 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Consulting & Technical Reviews | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/01 |  | 2014/04/03 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Support Turnover | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 25 | 8775 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/30 |  | 2014/04/30 |  | Charlene Dennis | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
Bristol Meyers Squibb - SO11435 - oQM Install Services | Project Closure | 5 - Product Installation |  | 35100 | 35000 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/27 | 2014/05/30 | 2014/04/30 |  | 2014/04/30 |  | Tim Johnson | [7 empty] | False | Laura Prendergast | 11435 | 87710033795 | 2014/01/21 | False
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Project Kick Off | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Planning & Design | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/07/10 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Product Installation | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
BT Americas - SO10412 - Remote After-hour support - PCIe, Dual, 64 SPAN | Project Closure | Project Closure | Hardware Install / Config | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/09 | 2013/10/31 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10412 | 87710030555 | 2013/07/09 | True | 2013/10/08
Sunturn - NuSkin SO10547 - Server Move - Provo | Project Kick Off | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 | 2013/07/11 |  | 2013/07/12 |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Planning & Design | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Hardware / Software Procurement | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Readiness Validation | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Product Installation | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 | 2013/07/19 |  | 2013/07/22 |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Product Integration | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Training | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Consulting & Technical Reviews | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Support Turnover | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
Sunturn - NuSkin SO10547 - Server Move - Provo | Project Closure | Project Closure | Verint-oQM | 4800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/22 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10547 | S6698 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Project Kick Off | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Planning & Design | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Readiness Validation | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Product Installation | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Product Integration | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Training | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Support Turnover | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
SCANA - SO10457 - Aiken - Remote Card Install | Project Closure | Project Closure | Hardware Install / Config | 700 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/10 | 2013/07/11 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10457 | SC-1100012170 | 2013/07/10 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Project Kick Off | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/13 |  | 2013/08/19 | 2013/08/20 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Planning & Design | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/21 | 2013/08/21 | 2013/08/26 | 2013/09/10 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Hardware / Software Procurement | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/08/27 | 2013/08/27 | 2013/08/29 | 2013/09/02 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Readiness Validation | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/02 | 2013/09/10 | 2013/09/04 | 2013/09/19 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Product Installation | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/04 | 2013/09/19 | 2013/09/05 | 2013/09/19 | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Product Integration | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 50 | 15100 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/09/06 | 2013/09/30 | 2013/10/11 | 2013/10/28 | John Randall | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Training | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/11/04 | 2013/11/04 | 2013/11/15 | 2013/11/15 | Tim Johnson | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2013/11/04 |  | 2013/12/13 | 2014/03/25 | Tim Johnson | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Support Turnover | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 50 | 15100 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2014/02/27 |  | 2014/03/21 | 2014/03/31 | John Randall | [7 empty] | True | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
Healthgrades - SO10554 - WFM + TOM 60 Seats | Project Closure | Project Closure | Verint-oWFM | 30200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/19 | 2014/02/28 | 2014/02/07 |  | 2014/02/07 |  | Tim Johnson | [7 empty] | False | Bill Spilman | 10554 | 000030000015451 | 2013/08/05 | False
State of Oregon - SO10565 - DP6409 Onsite Install | Project Kick Off | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/07/31 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Planning & Design | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/12 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Hardware / Software Procurement | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Product Installation | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/17 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Product Integration | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  |  | 2013/09/17 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
State of Oregon - SO10565 - DP6409 Onsite Install | Project Closure | 7 - Training | Hardware Install / Config | 7200 | 0 | Philip Haskings | 100 | 7200 | 0 | 0 | 2013/07/31 | 2013/10/31 |  |  | 2013/09/30 | 2013/09/19 | Philip Haskings | [7 empty] | True | Robert siegel | 10565 | 4500117067 | 2013/07/17 | True | 2013/09/19
AFNI - SO10571 - GM Install and Config | Project Kick Off | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  | 2013/07/29 | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Planning & Design | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Hardware / Software Procurement | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Readiness Validation | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Product Installation | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Consulting & Technical Reviews | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Support Turnover | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  |  |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
AFNI - SO10571 - GM Install and Config | Project Closure | 2 - Planning & Design |  | 8500 | 0 | Philip Haskings | 100 | 8500 | 0 | 0 | 2013/07/29 | 2014/07/31 |  |  | 2014/07/31 |  | Philip Haskings | [7 empty] | False | Mike Schwermin | 10571 | 000030000015513 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Project Kick Off | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Planning & Design | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Hardware / Software Procurement | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/07/23 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Readiness Validation | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Product Installation | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Product Integration | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
CDW - AFNI - SO10572 - Install of 6 Recorders | Project Closure | Project Closure | Verint-oRec | 19200 | 0 | Philip Haskings | 100 | 19200 | 0 | 0 | 2013/07/23 | 2013/11/29 |  |  | 2013/11/29 | 2013/12/03 | Philip Haskings | [7 empty] | True | Mike Schwermin | 10572 | 000030000015511 | 2013/07/18 | False
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Project Kick Off | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 |  | 2013/08/02 |  | 2013/08/02 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Planning & Design | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/05 |  | 2013/08/09 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Hardware / Software Procurement | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Readiness Validation | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/09 |  | 2013/08/15 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Product Installation | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/19 |  | 2013/08/21 | 2013/09/15 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Product Integration | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 100 | 25500 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2013/08/21 |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Training | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/13 | 2014/02/03 | 2014/01/24 | 2014/02/21 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Consulting & Technical Reviews | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/13 |  | 2014/01/24 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Support Turnover | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/28 | 2014/02/28 | 2014/01/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Intuitive - Pizza Hut- SO10506- SaaS oWFM | Project Closure | Project Closure | Verint-SaaS-oQM | 25500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/31 | 2014/02/28 | 2014/01/28 | 2014/02/28 | 2014/01/28 | 2014/02/28 | Tim Johnson | [7 empty] | True | Keith Donaldson | 10506 | 2809 | 2013/07/23 | True | 2013/09/18
Stevens Communications - Kohls - SO10601 - Radware | Project Kick Off | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Planning & Design | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Readiness Validation | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Product Installation | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Product Integration | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Training | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Support Turnover | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
Stevens Communications - Kohls - SO10601 - Radware | Project Closure | Project Closure | Hardware Install / Config | 9400 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/29 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10601 | 10815 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Project Kick Off | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Planning & Design | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  | 2013/07/26 |  | 2013/07/26 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Hardware / Software Procurement | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Readiness Validation | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Product Installation | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Product Integration | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Training | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Consulting & Technical Reviews | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 100 | 1600 | 0 | 0 | 2013/07/26 | 2013/07/29 | 2013/07/29 | 2013/07/29 | 2013/07/29 | 2013/07/31 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Support Turnover | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 10599 | 151271 | 2013/07/25 | False
NACR - Pleasant Holidays - SO10599 - Avaya WFM Health Check | Project Closure | 9 - Support Turnover | Verint-oWFM | 1600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/07/26 | 2013/07/29 |  | 2013/07/29 |  | 2013/08/01 | Kent Pylant | [7 empty] | True |  | 10599 | 151271 | 2013/07/25 | False
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Project Kick Off | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/02/01 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Planning & Design | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Readiness Validation | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  | 2013/07/15 |  | 2013/07/26 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Product Installation | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  | 2013/07/09 |  | 2013/02/15 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Product Integration | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Training | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 |  |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Support Turnover | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/06 | 2013/08/13 | 2013/08/13 |  | 2013/08/13 |  | Tim Johnson | [7 empty] | False |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
HSBC - SO 7947 Phase 1 - On Site Jersey City TopLayer | Project Closure | Project Closure | Hardware Install / Config | 6450 | 0 | John Randall | 100 | 6450 | 0 | 0 | 2013/08/06 | 2013/08/13 | 2013/08/13 |  | 2013/08/13 | 2013/08/13 | Tim Johnson | [7 empty] | True |  | 7947 | PT-006107 | 2012/01/01 | True | 2013/08/13
CDW - CBeyond - SO10615 - oWFM | Project Kick Off | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 |  |  |  | 2013/08/29 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Planning & Design | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/16 |  | 2013/09/16 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Hardware / Software Procurement | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/16 |  | 2013/09/20 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Readiness Validation | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/20 |  | 2013/09/20 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Product Installation | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/23 | 2013/09/23 | 2013/09/27 | 2013/09/27 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Product Integration | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 75 | 17707.5 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/09/30 |  | 2013/10/31 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Training | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/10/21 | 2013/10/15 | 2013/10/23 | 2013/10/23 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/10/28 |  | 2013/11/01 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Support Turnover | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 25 | 5902.5 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/11/04 |  | 2013/11/04 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
CDW - CBeyond - SO10615 - oWFM | Project Closure | Project Closure | Verint-oWFM | 23610 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/29 | 2013/10/31 | 2013/11/05 |  | 2013/11/11 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10615 | 00030000015570 | 2013/07/29 | False
MolDev - Methodist Hospital - SO10614 - Quest | Project Kick Off | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/08/26 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Planning & Design | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Hardware / Software Procurement | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Product Installation | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  |  | 2013/09/12 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
MolDev - Methodist Hospital - SO10614 - Quest | Project Closure | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/08/30 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10614 | 40729301 | 2013/07/29 | True | 2013/09/25
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Project Kick Off | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/19 | 2013/08/19 | 2013/08/19 | 2013/08/19 | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Planning & Design | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/22 | 2013/08/22 | 2013/08/26 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Hardware / Software Procurement | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/09 | 2013/08/09 | 2013/08/12 | 2013/08/13 | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Readiness Validation | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/08/27 | 2013/08/27 | 2013/08/27 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Product Installation | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/09 |  | 2013/09/27 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Product Integration | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 50 | 64775 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/09 |  | 2013/09/27 | 2013/09/27 | Tim Johnson | [7 empty] | True | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Training | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/07 |  | 2013/10/25 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Consulting & Technical Reviews | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/09/23 |  | 2013/09/30 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Support Turnover | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 50 | 64775 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/25 |  | 2013/10/25 | 2013/10/31 | Stewart Futcher | [7 empty] | True | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
Carousel - Contra Costa County - SO10625 - oWFO (WFM v7 to v11 Migration) | Project Closure | Project Closure | Verint-oWFO | 129550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/08/19 | 2013/10/31 | 2013/10/31 |  | 2013/10/31 |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10625 | 264481 | 2013/07/31 | True | 2013/09/30
MolDev - PepsiCo (California) - SO10561 - Quest | Project Kick Off | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Planning & Design | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Hardware / Software Procurement | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Product Installation | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
MolDev - PepsiCo (California) - SO10561 - Quest | Project Closure | Project Closure | MolDev -Quest | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10561 | 40712304 | 2013/08/02 | True | 2013/09/03
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Project Kick Off | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Planning & Design | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Hardware / Software Procurement | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Readiness Validation | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  | 2013/08/02 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Product Installation | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 | 2013/08/12 |  | 2013/08/16 |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Product Integration | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 | 2013/08/12 |  | 2013/08/16 | 2013/08/26 | Tim Johnson | [7 empty] | True |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Training | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Support Turnover | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
NACR - Pleasant Holidays - SO10633 - Avaya WFM | Project Closure | Project Closure | Verint-oWFM | 12000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/08/12 | 2013/08/26 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10633 | 151701 | 2013/08/02 | True | 2013/08/26
Telus Comm - Access - SO10632 - WFM Training | Project Kick Off | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 |  |  |  | 2013/08/09 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Planning & Design | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 |  |  |  | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Training | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 100 | 2500 | 0 | 0 | 2013/08/09 | 2013/10/28 | 2013/10/28 |  | 2013/10/28 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
Telus Comm - Access - SO10632 - WFM Training | Project Closure | Project Closure | Verint-oWFM | 2500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/09 | 2013/10/28 | 2013/10/28 |  | 2013/10/28 | 2013/10/30 | Philip Haskings | [7 empty] | True |  | 10632 | T429893 | 2013/08/02 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Project Kick Off | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/03 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Planning & Design | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Product Installation | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  |  | 2013/10/24 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
MolDev - Bayer (France) - SO10655 - Research 10 | Project Closure | Project Closure | MolDev-Research 10 | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/09/02 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/31 | Philip Haskings | [7 empty] | True |  | 10655 | 40724302 | 2013/08/08 | False
BBVA - SO10677 - Health Check | Project Kick Off | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/14 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Planning & Design | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Product Integration | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - SO10677 - Health Check | Project Closure | Project Closure | Hardware Install / Config | 9000 | 0 | Philip Haskings | 100 | 9000 | 0 | 0 | 2013/08/22 | 2013/08/28 |  |  |  | 2013/08/28 | Philip Haskings | [7 empty] | True | James Reedy | 10677 | 135272 | 2013/08/13 | True | 2013/08/31
BBVA - Intl Weatlh Mgmt - SO10737 | Project Kick Off | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Planning & Design | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Hardware / Software Procurement | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  |  | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Product Integration | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  | 2013/10/31 | 2013/09/17 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
BBVA - Intl Weatlh Mgmt - SO10737 | Project Closure | Project Closure | Verint-oQM | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2013/09/13 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/25 | Philip Haskings | [7 empty] | True |  | 10737 | 133321 | 2013/08/16 | True | 2013/09/30
Charter - SO10692 - Recorders at Multiple Sites | Project Kick Off | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/09/10 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Planning & Design | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/10/16 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Hardware / Software Procurement | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  |  | 2013/10/01 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Readiness Validation | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/11/29 | 2013/11/29 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Product Installation | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/13 | 2013/12/03 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Product Integration | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/13 | 2013/12/03 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
Charter - SO10692 - Recorders at Multiple Sites | Project Closure | Project Closure | Verint-oRec | 56100 | 0 | Philip Haskings | 100 | 56100 | 0 | 0 | 2013/09/30 | 2013/12/16 |  |  | 2013/12/16 | 2013/12/31 | Philip Haskings | [7 empty] | True | Zolna, Jake | 10692 | 1733634 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Project Kick Off | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/08/26 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Planning & Design | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/02 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Hardware / Software Procurement | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/02 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Product Installation | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  |  | 2013/09/09 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Product Integration | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 100 | 7800 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/20 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
NACR - Texas Tech - SO10698 - Encryption | Project Closure | Project Closure | Verint-oRec | 7800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/26 | 2013/12/31 |  |  | 2013/11/29 | 2013/12/20 | Philip Haskings | [7 empty] | True | Jan Cummings | 10698 | 152081 | 2013/08/19 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Project Kick Off | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/25 | 2013/09/25 | 2013/09/25 | 2013/09/25 | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Planning & Design | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/26 | 2013/09/26 | 2013/12/09 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Hardware / Software Procurement | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/09/26 | 2013/09/26 | 2013/12/09 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Readiness Validation | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/12/06 |  | 2013/12/06 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Product Installation | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2013/12/16 |  | 2013/12/16 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Product Integration | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 75 | 25638.75 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/01/27 |  | 2014/02/14 | 2014/02/26 | John Randall | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Training | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/02/17 |  | 2014/02/28 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/03 |  | 2014/03/14 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Support Turnover | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 25 | 8546.25 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/17 |  | 2014/03/17 | 2014/03/28 | John Randall | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
National Flood - SO10744 - oWFM + Shift Bid + Pop-up Alerts | Project Closure | Project Closure | Verint-oWFM | 34185 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/20 | 2014/01/31 | 2014/03/17 |  | 2014/03/17 | 2014/03/28 | Tim Johnson | [7 empty] | True | Helene Thompson | 10744 | 210267 | 2013/08/20 | False
ACS - Xerox - SO10700 Health Check for Support Renewal | Project Kick Off | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Planning & Design | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  | 2013/09/24 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Product Installation | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 | 2013/09/27 |  | 2013/09/27 | 2013/09/27 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal | Project Closure | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
ACS - Xerox - SO10700 Health Check for Support Renewal |  | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/30 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 10700 | AC212426 | 2013/08/21 | True | 2013/10/01
Verint PMO Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Training | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 45500 | 0 | Tim Johnson | 100 | 45500 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - September 2013 | Project Kick Off | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Planning & Design | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Readiness Validation | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Product Installation | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Product Integration | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Training | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Support Turnover | Project Closure |  | 20300 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - September 2013 | Project Closure | Project Closure |  | 20300 | 0 | Kent Pylant | 100 | 20300 | 0 | 0 | 2013/09/01 | 2013/09/30 |  | 2013/09/02 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint PMO Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Training | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/01 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint PMO Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 21700 | 0 | Tim Johnson | 100 | 21700 | 0 | 0 | 2013/10/01 | 2013/10/01 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Training | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint RRI Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 27912.5 | 0 | Kent Pylant | 100 | 27912.5 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Planning & Design | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Product Installation | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Product Integration | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Training | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Support Turnover | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint MAC Revenue - August 2013 | Project Closure | 1 - Project Kick Off |  | 3150 | 0 | Kent Pylant | 100 | 3150 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Verint PMO Revenue - November 2013 | Project Kick Off | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Planning & Design | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Readiness Validation | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Product Installation | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Product Integration | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Training | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Support Turnover | Project Closure |  | 16100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - November 2013 | Project Closure | Project Closure |  | 16100 | 0 | Kent Pylant | 100 | 16100 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/10/28 | 2013/11/30 | 2013/11/30 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint PMO Revenue - December 2013 | Project Kick Off | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Planning & Design | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Readiness Validation | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Product Installation | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Product Integration | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Training | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Support Turnover | Project Closure |  | 9100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint PMO Revenue - December 2013 | Project Closure | Project Closure |  | 9100 | 0 | Kent Pylant | 100 | 9100 | 0 | 0 | 2013/12/01 | 2013/12/31 |  | 2013/12/02 | 2013/12/31 | 2013/12/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - September 2013 | Project Kick Off | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Planning & Design | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Readiness Validation | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Product Installation | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Product Integration | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Training | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Support Turnover | Project Closure |  | 21393.75 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - September 2013 | Project Closure | Project Closure |  | 21393.75 | 0 | Kent Pylant | 100 | 21393.75 | 0 | 0 | 2013/09/01 | 2013/09/30 |  | 2013/09/02 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint RRI Revenue - November 2013 | Project Kick Off | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Planning & Design | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Readiness Validation | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Product Installation | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Product Integration | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Training | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Support Turnover | Project Closure |  | 41606.25 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - November 2013 | Project Closure | Project Closure |  | 41606.25 | 0 | Kent Pylant | 100 | 41606.25 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/11/01 | 2013/11/30 | 2013/11/29 | Kent Pylant | [7 empty] | True | Matt Webb | 99999 | 99999 | 2013/11/01 | False
Verint RRI Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Training | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 31150 | 0 | Kent Pylant | 100 | 31150 | 0 | 0 | 2013/10/01 | 2013/10/31 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint RRI Revenue - December 2013 | Project Kick Off | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Planning & Design | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Readiness Validation | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Product Installation | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Product Integration | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Training | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Support Turnover | Project Closure |  | 23362.5 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint RRI Revenue - December 2013 | Project Closure | Project Closure |  | 23362.5 | 0 | Kent Pylant | 100 | 23362.5 | 0 | 0 | 2013/12/01 | 2013/12/31 |  | 2013/12/02 | 2013/12/31 | 2013/12/31 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Project Kick Off | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2013/10/08 | 2013/10/08 | 2013/10/08 | 2013/10/08 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Planning & Design | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/03/07 | 2014/03/07 | 2014/03/10 | 2014/03/10 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Hardware / Software Procurement | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/02/17 | 2014/02/17 | 2014/02/21 | 2014/02/21 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Readiness Validation | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/03/24 | 2014/03/24 | 2014/03/27 | 2014/03/27 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Product Installation | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/01 | 2014/04/01 | 2014/04/04 | 2014/04/04 | Tim Johnson | [7 empty] | True | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Product Integration | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 75 | 70897.5 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/01 | 2014/04/01 | 2014/04/11 |  | Stewart Futcher | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Training | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/21 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Consulting & Technical Reviews | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/04/30 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Support Turnover | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 25 | 23632.5 | 0 | 0 | 2013/09/03 | 2013/11/29 | 2014/05/30 |  | 2014/05/30 |  | Stewart Futcher | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Delta Dental - SO10732 - oWFO + WFM v7-v11 Migration | Project Closure | 6 - Product Integration | Verint-oWFO | 94530 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/03 | 2013/11/29 |  |  | 2014/03/07 |  | Tim Johnson | [7 empty] | False | Federico Victoria III | 10732 | 81781 | 2013/08/28 | False
Verint MAC Revenue - September 2013 | Project Kick Off | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Planning & Design | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Hardware / Software Procurement | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Readiness Validation | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Product Installation | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Product Integration | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Training | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Consulting & Technical Reviews | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Support Turnover | Project Closure |  | 900 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - September 2013 | Project Closure | Project Closure |  | 900 | 0 | Kent Pylant | 100 | 900 | 0 | 0 | 2013/09/30 | 2013/09/30 |  | 2013/09/30 | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
Verint MAC Revenue - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Training | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - October 2013 | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  | 2013/10/01 | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
Verint MAC Revenue - November 2013 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - November 2013 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  | 2013/10/28 | 2013/11/30 | 2013/12/02 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/11/01 | False
Verint MAC Revenue - December 2013 | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince | 99999 | 99999 | 2013/12/01 | False
Verint MAC Revenue - December 2013 | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 | 2013/12/01 | 2013/12/02 | 2013/12/31 | 2013/12/30 | Kent Pylant | [7 empty] | True | Tim Prince | 99999 | 99999 | 2013/12/01 | False
ADVANtel - Consumer Cellular - SO10736 | Project Kick Off | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Planning & Design | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Hardware / Software Procurement | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Readiness Validation | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Product Installation | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Product Integration | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 100 | 3200 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  | 2013/10/03 | 2013/10/07 | Tim Johnson | [7 empty] | True |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Training | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Consulting & Technical Reviews | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Support Turnover | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
ADVANtel - Consumer Cellular - SO10736 | Project Closure | 7 - Training | Verint-oWFM | 3200 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/09/02 | 2013/09/21 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10736 | 5009120 | 2013/08/29 | True | 2013/10/03
Siemens - Medstar - SO10746 | Project Kick Off | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/04 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Planning & Design | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/10 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Hardware / Software Procurement | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 |  |  |  | 2013/09/24 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Product Installation | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/04 | 2013/10/07 | 2013/10/04 |  | 2013/10/04 | 2013/10/15 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Siemens - Medstar - SO10746 | Project Closure | Project Closure | Verint-oQM | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/09/04 | 2013/10/07 | 2013/10/07 |  | 2013/10/07 | 2013/10/15 | Philip Haskings | [7 empty] | True | Gary Goetzinger | 10746 | 7700242294 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Project Kick Off | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/08 |  | 2013/10/08 | 2013/10/09 | Tim Johnson | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Planning & Design | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/09 |  | 2013/10/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Hardware / Software Procurement | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/01 |  | 2013/10/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Readiness Validation | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/10/29 |  | 2013/10/30 | 2013/11/04 | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Product Installation | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/11/11 | 2013/11/11 | 2013/11/11 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Product Integration | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 17.66 | 4503.3 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2013/11/12 | 2013/11/11 | 2013/12/20 | 2013/12/17 | John Randall | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Training | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/03 |  | 2014/03/14 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Consulting & Technical Reviews | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/17 |  | 2014/03/28 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Support Turnover | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 82.34 | 20996.7 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Region of York - SO10747 - oWFM 30 Seats | Project Closure | Project Closure | Verint-oWFM | 25500 | 25500 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 |  | Tim Johnson | [7 empty] | False | Jim Foster | 10747 | JMF260820131046 | 2013/09/04 | False
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Project Kick Off | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Planning & Design | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/11 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Product Integration | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  |  | 2013/09/11 | Philip Haskings | [7 empty] | False |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Black Box - Genentech - SO10751 - Express v9.3 QM VOX reconfigure to CTI AACC v6.2 - After-hour Install | Project Closure | Project Closure | Verint-oQM | 3200 | 3200 | Philip Haskings | 100 | 3200 | 0 | 0 | 2013/09/06 | 2013/09/10 |  |  | 2013/09/13 | 2013/09/13 | Philip Haskings | [7 empty] | True |  | 10751 | NCI0000255496 | 2013/09/05 | True | 2013/10/01
Innovation Group - SO10754 - oWFO | Project Kick Off | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/10/17 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Planning & Design | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/09/30 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Hardware / Software Procurement | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 |  |  |  | 2013/09/20 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Readiness Validation | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/26 | 2013/09/30 | 2013/09/27 | 2013/09/30 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Product Installation | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/25 | 2013/09/30 | 2013/10/21 | 2013/10/20 | Tim Johnson | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Product Integration | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 80 | 46640 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/09/26 | 2013/09/30 | 2013/10/31 | 2013/10/30 | John Randall | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Training | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/11/18 | 2013/11/18 | 2014/02/14 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Consulting & Technical Reviews | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2013/10/28 |  | 2013/11/15 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Support Turnover | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 20 | 11660 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2014/03/31 |  | 2014/03/31 | 2014/03/28 | John Randall | [7 empty] | True | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Innovation Group - SO10754 - oWFO | Project Closure | Project Closure | Verint-oWFO | 58300 | 58300 | John Randall | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/03/28 | 2014/01/06 |  | 2014/01/06 |  | Tim Johnson | [7 empty] | False | Carol Shapleigh | 10754 | 269040 | 2013/09/05 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Project Kick Off | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/16 | 2013/09/16 | 2013/09/17 | 2013/09/17 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Planning & Design | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/23 | 2013/09/24 | 2013/10/04 | 2013/10/04 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Hardware / Software Procurement | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/09/23 | 2013/09/23 | 2013/09/23 | 2013/09/24 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Readiness Validation | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/04 | 2013/10/04 | 2013/10/04 | 2013/10/07 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Product Installation | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/07 | 2013/10/07 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Product Integration | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/07 | 2013/10/07 | 2013/10/25 | 2013/10/25 | Stewart Futcher | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Training | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 100 | 62400 | 0 | 0 | 2013/09/16 | 2013/12/20 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Consulting & Technical Reviews | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/12/20 | 2014/10/30 | Tim Johnson | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Support Turnover | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/11/23 | 2014/02/19 | Stewart Futcher | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Carousel - MedImpact - SO10733 - oQM w/ DC Redundancy | Project Closure | Project Closure | Verint-oQM | 62400 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/12/20 |  |  | 2013/12/30 | 2014/02/19 | Stewart Futcher | [7 empty] | False | Eric Bonnecarre | 10733 | 268326 | 2013/09/06 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Project Kick Off | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Planning & Design | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Hardware / Software Procurement | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/14 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Readiness Validation | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/21 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Product Installation | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  |  | 2014/02/28 | Philip Haskings | [7 empty] | True | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Product Integration | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 75 | 6675 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Training | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Consulting & Technical Reviews | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Support Turnover | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 25 | 2225 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Medstar - SO10779 - oQM + Lesson Mgmt | Project Closure | 6 - Product Integration |  | 8900 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/11 | 2014/06/30 |  |  | 2014/06/30 |  | Philip Haskings | [7 empty] | False | K. Keith Drew | 10779 | 7700242511 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Project Kick Off | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Planning & Design | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Hardware / Software Procurement | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Readiness Validation | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Product Installation | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Product Integration | 7 - Training |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/29 | Stewart Futcher | [7 empty] | True |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Training | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Consulting & Technical Reviews | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Support Turnover | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10703 | 7700241820 | 2013/09/11 | False
Siemens - County of Santa Cruz - SO10703 - Additional 20 QM Licenses | Project Closure | 7 - Training |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/29 | Tim Johnson | [7 empty] | True |  | 10703 | 7700241820 | 2013/09/11 | False
ACCC Insurance Co - SO10741 - oWFM | Project Kick Off | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  | 2014/02/20 | Philip Haskings | [7 empty] | True | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Planning & Design | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Hardware / Software Procurement | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Readiness Validation | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Product Installation | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Product Integration | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 100 | 25500 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  | 2014/05/02 |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Training | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Consulting & Technical Reviews | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Support Turnover | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  |  |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
ACCC Insurance Co - SO10741 - oWFM | Project Closure | 2 - Planning & Design |  | 25500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/05/30 |  |  | 2013/12/31 |  | Philip Haskings | [7 empty] | False | Leah Treille | 10741 | 14387 | 2013/09/12 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Project Kick Off | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Planning & Design | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Readiness Validation | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Product Installation | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Product Integration | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Training | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Support Turnover | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Pittsburgh Glass Works - SOxxxx - DP6409 | Project Closure | 1 - Project Kick Off |  | 0 | 4700 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Adam Ip | [7 empty] | False |  |  | 12345 | 2013/09/13 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/09 | 2013/10/09 | 2013/10/09 | 2013/10/09 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/21 | 2013/10/21 | 2013/10/31 | 2013/11/08 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/10/14 | 2013/10/14 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Readiness Validation | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/06 | 2013/11/08 | 2013/11/08 | 2013/11/12 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Product Installation | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/04 | 2013/11/04 | 2013/11/29 | 2013/11/29 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Product Integration | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 75 | 44400 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2013/11/04 | 2013/11/04 | 2013/12/13 | 2013/12/17 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Training | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/03/03 | 2014/03/03 | 2014/03/07 | 2014/03/07 | Stewart Futcher | [7 empty] | True | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/03/03 | 2014/03/03 | 2014/04/25 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 25 | 14800 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/04/25 |  | 2014/04/25 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Mobile Gas - SO10807 -oWFO + TOM - 21 Seats | Project Closure | 8 - Consulting & Technical Reviews |  | 59200 | 94790 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/17 | 2013/12/31 | 2014/04/28 |  | 2014/04/28 |  | Stewart Futcher | [7 empty] | False | Karen Hoganson | 10807 | 153678 | 2013/09/16 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Project Kick Off | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/01 | 2013/09/19 | 2013/10/01 | 2013/09/19 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Planning & Design | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/09/25 |  | 2013/09/25 | 2013/10/01 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Hardware / Software Procurement | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/01 | 2013/09/19 | 2013/10/01 | 2013/09/20 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Readiness Validation | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/14 | 2013/10/17 | 2013/10/14 | 2013/10/17 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Product Installation | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/21 | 2013/10/18 | 2013/10/25 | 2013/10/22 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Product Integration | Project Closure |  | 46400 | 54740 | Philip Haskings | 66 | 30624 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/10/28 |  | 2013/11/01 | 2013/11/06 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Training | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/11/12 |  | 2013/11/21 | 2014/03/05 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Consulting & Technical Reviews | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/11 |  | 2013/12/11 | 2014/03/05 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Support Turnover | Project Closure |  | 46400 | 54740 | Philip Haskings | 34 | 15776 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/13 |  | 2014/02/07 | 2014/02/21 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
Merrill Assoc - HireRight - SO10808 - aWFM + LM | Project Closure | Project Closure |  | 46400 | 54740 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/17 | 2014/02/28 | 2013/12/16 |  | 2013/12/16 | 2014/03/11 | Philip Haskings | [7 empty] | True | Hiram Romero | 10808 | 12934 | 2013/09/17 | False
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Readiness Validation | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Product Installation | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Training | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Consulting & Technical Reviews | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Support Turnover | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 |  |  |  |  | Adam Ip | [7 empty] | False |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/16 | 2013/09/16 | 2013/09/16 | 2013/09/16 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/17 | 2013/09/17 | 2013/09/17 | 2013/09/17 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
NACR - Intrust Bank - SO10809 - Express Troubleshooting |  | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/16 | 2013/09/17 | 2013/09/18 | 2013/09/18 | 2013/09/18 | 2013/09/18 | Philip Haskings | [7 empty] | True |  | 10809 | 153765 | 2013/09/17 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Planning & Design | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 |  | 2013/09/20 |  | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Project Kick Off | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/10/01 | 2013/09/20 | 2013/10/01 | 2013/09/20 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Product Installation | Project Closure |  | 4700 | 4700 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/09/09 |  | 2013/09/24 | 2013/09/24 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Johnson & Johnson - SO10813 - Voice Card Install | Project Closure | Project Closure |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/18 | 2013/09/25 | 2013/10/31 |  | 2013/10/31 | 2013/09/25 | Philip Haskings | [7 empty] | True |  | 10813 | 993220797 | 2013/09/18 | True | 2013/10/01
Nissan - SO10758 - Remote Services | Project Kick Off | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Planning & Design | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Product Integration | Project Closure |  | 2200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  |  | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Nissan - SO10758 - Remote Services | Project Closure | Project Closure |  | 2200 | 0 | Philip Haskings | 100 | 2200 | 0 | 0 | 2013/08/17 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Philip Haskings | [7 empty] | True |  | 10758 | 7400066031 | 2013/08/17 | True | 2013/09/27
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Project Kick Off | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/10/07 | 2013/10/10 | 2013/10/10 | 2013/10/10 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Planning & Design | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/29 | 2013/11/18 | 2013/11/29 | 2013/11/29 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/25 | 2013/11/25 | 2013/11/25 | 2014/02/28 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Readiness Validation | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/11/04 | 2013/11/06 | 2013/11/15 | 2014/01/01 | Stewart Futcher | Testing by Adam | Billable | 2014/04/23 | 2014/04/23 | 5.2 | Libby Lasseigne | Adam Ip | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Product Installation | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/12/09 | 2013/12/09 | 2013/12/27 | 2013/12/27 | Tim Johnson | [7 empty] | True | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Product Integration | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 40 | 77384 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2013/12/09 | 2013/12/09 | 2014/04/18 |  | Stewart Futcher | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Training | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/02/10 | 2014/02/10 | 2014/02/21 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/02/10 | 2014/02/10 | 2014/02/10 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Support Turnover | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 20 | 38692 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/05/01 |  | 2014/05/30 |  | Stewart Futcher | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Avista - SO10833 - Avaya v12 oWFO + Speech + Data Migration + ADA/AET | Project Closure | 8 - Consulting & Technical Reviews |  | 193460 | 193460 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2014/01/31 | 2014/05/05 |  | 2014/05/05 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 10833 | 210931 | 2013/09/25 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Project Kick Off | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Planning & Design | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 | 2014/03/24 | 2014/03/24 | 2014/04/01 | 2014/04/01 | Kent Pylant | [7 empty] | True | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Hardware / Software Procurement | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Readiness Validation | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Product Installation | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Product Integration | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 100 | 11300 | 0 | 0 | 2014/03/24 | 2014/04/25 | 2014/04/21 |  | 2014/04/25 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Training | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Consulting & Technical Reviews | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Support Turnover | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  | 2014/07/01 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Commonwealth of Kentucky - Avaya QM Training SO11700 | Project Closure | 3 - Hardware / Software Procurement |  | 11300 | 11300 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/03/24 | 2014/04/25 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan |  | 4521718073 | 2014/04/01 | False
Region of York - SO11390 TOM Addition | Project Kick Off | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Planning & Design | Project Closure |  | 500 | 500 | John Randall | 25 | 125 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Hardware / Software Procurement | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Readiness Validation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Product Installation | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Product Integration | Project Closure |  | 500 | 500 | John Randall | 50 | 250 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Training | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Consulting & Technical Reviews | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Support Turnover | Project Closure |  | 500 | 500 | John Randall | 25 | 125 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  | 2014/03/31 | 2014/03/31 | John Randall | [7 empty] | True | Jim Foster |  | 15161 | 2014/03/24 | False
Region of York - SO11390 TOM Addition | Project Closure | Project Closure |  | 500 | 500 | John Randall | 0 | 0 | 0 | 0 | 2014/03/31 | 2014/03/31 |  |  |  |  | John Randall | [7 empty] | False | Jim Foster |  | 15161 | 2014/03/24 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Project Kick Off | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Planning & Design | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 25 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/05/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Hardware / Software Procurement | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Readiness Validation | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Product Installation | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Product Integration | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 50 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/06/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Training | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Consulting & Technical Reviews | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Support Turnover | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 25 | 500 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  | 2014/07/02 |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - CDW - SO 11704 License for seats and TOM | Project Closure | 1 - Project Kick Off |  | 500 | 500 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/03 | 2014/04/10 |  |  |  |  | Philip Haskings | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
QT11192 Pearson Education Support | Project Kick Off | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Planning & Design | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 25 | 1000 | 0 | 0 |  |  |  |  | 2014/05/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Hardware / Software Procurement | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Readiness Validation | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Product Installation | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Product Integration | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 50 | 1000 | 0 | 0 |  |  |  |  | 2014/06/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Training | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Consulting & Technical Reviews | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Support Turnover | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 25 | 1000 | 0 | 0 |  |  |  |  | 2014/07/02 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
QT11192 Pearson Education Support | Project Closure | 1 - Project Kick Off |  | 1000 | 1000 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Project Kick Off | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Hardware / Software Procurement | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Product Integration | 1 - Project Kick Off |  | 250 | 250 | John Randall | 100 | 250 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  | 2014/06/03 |  | John Randall | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Healthgrades - SO11704 - License expansion qty 10 v11.1 | Project Closure | 1 - Project Kick Off |  | 250 | 250 | John Randall | 0 | 0 | 0 | 0 | 2014/04/10 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Bill Spilman | 11704 | LSB0102 | 2014/04/02 | False
Flagstar l PS support l 4 days | Project Kick Off | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Planning & Design | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 25 | 10800 | 0 | 0 |  |  |  |  | 2014/05/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Hardware / Software Procurement | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Readiness Validation | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Product Installation | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Product Integration | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 50 | 10800 | 0 | 0 |  |  |  |  | 2014/06/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Training | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Consulting & Technical Reviews | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Support Turnover | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 25 | 10800 | 0 | 0 |  |  |  |  | 2014/07/03 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Flagstar l PS support l 4 days | Project Closure | 1 - Project Kick Off |  | 10800 | 10800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Project Kick Off | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Planning & Design | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 25 | 9100 | 0 | 0 |  |  |  |  | 2014/05/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Hardware / Software Procurement | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Readiness Validation | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Product Installation | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Product Integration | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 50 | 9100 | 0 | 0 |  |  |  |  | 2014/06/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Training | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Consulting & Technical Reviews | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Support Turnover | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 25 | 9100 | 0 | 0 |  |  |  |  | 2014/07/04 |  | Tim Johnson | [7 empty] | False |  |  |  |  | False
Charter ¦ Voice Screen Recording Servers ¦ Billings MT | Project Closure | 1 - Project Kick Off |  | 9100 | 9100 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  |  |  | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Project Kick Off | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Planning & Design | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  | 2014/05/09 |  | Philip Haskings | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Hardware / Software Procurement | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Product Integration | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  | 2014/06/09 |  | Philip Haskings | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
BioAgilytix Labs - SO11727 - MolDev Research 10 Installation | Project Closure | 1 - Project Kick Off |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/04/09 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Grischa Chandy | 11727 | 40407401 | 2014/04/07 | False
Wells Fargo - SO11619 - Remote Training | Project Kick Off | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Planning & Design | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 50 | 2700 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  | 2014/04/18 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Hardware / Software Procurement | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Readiness Validation | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Training | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 50 | 2700 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  | 2014/05/16 |  | Kent Pylant | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Wells Fargo - SO11619 - Remote Training | Project Closure | 1 - Project Kick Off |  | 5400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Suzanne Jordan | 11619 | 179146 | 2014/03/06 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Project Kick Off | Project Closure |  | 500 | 500 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/19 | 2014/01/31 |  | 2013/12/20 |  | 2013/12/20 | Tim Johnson | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Product Installation | Project Closure |  | 500 | 500 | Charlene Dennis | 100 | 500 | 0 | 0 | 2013/12/19 | 2014/01/31 |  | 2014/01/08 | 2014/01/31 | 2014/01/08 | Charlene Dennis | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Brady Group - SO11327 - Remote installation - 5 seat license | Project Closure | Project Closure |  | 500 | 500 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/19 | 2014/01/31 |  |  |  | 2014/01/10 | Tim Johnson | [7 empty] | True | Greg Goetz | 11327 | LHJ3322 | 2013/12/19 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Project Kick Off | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Planning & Design | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Hardware / Software Procurement | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Readiness Validation | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Product Installation | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Product Integration | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 100 | 8900 | 0 | 0 | 2013/12/17 | 2014/07/31 | 2014/06/16 |  | 2014/07/25 |  | Philip Haskings | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Training | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Consulting & Technical Reviews | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Support Turnover | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Northwest Natural Gas - SO11306 - LDAP Integration | Project Closure | 2 - Planning & Design |  | 8900 | 8900 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2014/07/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Mike Farwick | 11306 | 5010207 | 2013/12/13 | False
Apple - SO11312 - Onsite Services | Project Kick Off | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Hardware / Software Procurement | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Product Installation | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  | 2013/12/20 | 2013/12/19 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Consulting & Technical Reviews | Project Closure |  | 8000 | 8000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  |  | 2013/12/19 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
Apple - SO11312 - Onsite Services | Project Closure | Project Closure |  | 8000 | 8000 | Philip Haskings | 100 | 8000 | 0 | 0 | 2013/12/17 | 2013/12/31 |  |  | 2013/12/27 | 2013/12/31 | Philip Haskings | [7 empty] | True | Brian White | 11312 | 6000085714 | 2013/12/17 | False
USG - SO11375 - SKY oWFO - 130 Seats | Project Kick Off | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/01/14 |  | 2014/01/14 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Planning & Design | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/01/15 |  | 2014/01/31 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Hardware / Software Procurement | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Readiness Validation | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Product Installation | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 |  | 2014/02/10 | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Product Integration | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 100 | 39300 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/02/28 | 2014/02/28 | 2014/04/28 |  | Charlene Dennis | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Training | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/03/10 | 2014/03/10 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Consulting & Technical Reviews | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Support Turnover | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
USG - SO11375 - SKY oWFO - 130 Seats | Project Closure | 5 - Product Installation |  | 39300 | 39300 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/14 | 2014/04/08 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Seth Luxon | 11375 | 915485 | 2014/01/06 | False
HireRight - SO11385 - SSO Implementation | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Product Installation | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Product Integration | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Training | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
HireRight - SO11385 - SSO Implementation | Project Closure | 1 - Project Kick Off |  | 0 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/01/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Carol Richardson | 11385 | 88888 | 2014/01/07 | False
Verint PMO Revenue - May 2014 | Project Kick Off | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Planning & Design | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Hardware / Software Procurement | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Readiness Validation | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Product Installation | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Product Integration | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Training | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Consulting & Technical Reviews | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Support Turnover | Project Closure |  | 3500 | 3500 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint PMO Revenue - May 2014 | Project Closure | Project Closure |  | 3500 | 3500 | Kent Pylant | 100 | 3500 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Project Kick Off | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Planning & Design | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Hardware / Software Procurement | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Readiness Validation | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Product Installation | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Product Integration | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Training | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Consulting & Technical Reviews | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Support Turnover | Project Closure |  | 1400 | 1400 | Kent Pylant | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
Verint MAC Revenue - May 2014 | Project Closure | Project Closure |  | 1400 | 1400 | Kent Pylant | 100 | 1400 | 0 | 0 | 2014/05/01 | 2014/05/30 | 2014/05/01 |  | 2014/05/30 |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999 | 2014/05/01 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Project Kick Off | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/03/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Planning & Design | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Hardware / Software Procurement | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Readiness Validation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Product Installation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Product Integration | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/06 | 2014/04/30 | 2014/05/31 |  | 2014/05/31 |  | John Randall | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Training | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Consulting & Technical Reviews | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Support Turnover | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
HSBC- SO11313 - ECC NL TopLayer_Shoremicro 1G-Copper | Project Closure | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 11313 | D07122887 | 2013/12/17 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Project Kick Off | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/02/18 |  | 2014/02/18 | Tim Johnson | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Planning & Design | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 25 | 6975 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/21 | 2014/03/21 | 2014/03/28 | Charlene Dennis | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Hardware / Software Procurement | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/07 |  | 2014/04/09 | Tim Johnson | [7 empty] | True | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Readiness Validation | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 |  | 2014/04/07 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Product Installation | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/04/14 |  |  |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Product Integration | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 50 | 13950 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/04/28 |  | 2014/04/30 |  | Charlene Dennis | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Training | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/06 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Consulting & Technical Reviews | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/12 |  | 2014/05/16 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Support Turnover | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 25 | 6975 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/26 |  | 2014/05/26 |  | Charlene Dennis | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
Denmat Holdings - SO11465 - SKY Compliance Recording - 93 agents | Project Closure | 4 - Readiness Validation |  | 27900 | 19680 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/02/04 | 2014/05/30 | 2014/05/26 |  | 2014/05/26 |  | Tim Johnson | [7 empty] | False | Thomas Lyon | 11465 | 92705 | 2014/01/27 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Project Kick Off | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/01/14 |  | 2014/01/14 | Charlene Dennis | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Planning & Design | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 25 | 20391.25 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/02/07 | 2014/02/28 | 2014/02/28 | Charlene Dennis | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Hardware / Software Procurement | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/03/04 |  | 2014/03/06 | Tim Johnson | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Readiness Validation | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 |  | 2014/03/07 |  | 2014/03/07 | Tim Johnson | [7 empty] | True | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Product Installation | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/03/17 |  | 2014/05/15 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Product Integration | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 50 | 40782.5 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/03/15 |  | 2014/05/15 |  | Charlene Dennis | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Training | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/04/07 |  | 2014/03/21 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Consulting & Technical Reviews | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/05/23 |  | 2014/05/23 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Support Turnover | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 25 | 20391.25 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/06/04 |  | 2014/07/11 |  | Charlene Dennis | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
AAA Life - SO11336 - Recording/WFM/CF/325 seats/Services portion | Project Closure | 5 - Product Installation |  | 81565 | 81565 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/02 | 2014/04/04 | 2014/06/04 |  | 2014/06/04 |  | Tim Johnson | [7 empty] | False | Ken Drazin | 11336 | 000030000017178 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Project Kick Off | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/01/09 |  | 2014/01/09 | Charlene Dennis | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Planning & Design | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/02/19 |  | 2014/02/19 | Tim Johnson | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Product Integration | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 100 | 4800 | 0 | 0 | 2014/01/10 | 2014/02/28 |  | 2014/02/22 | 2014/02/24 | 2014/02/24 | Charlene Dennis | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11339 - JTAPI Services - After Hours | Project Closure | 7 - Training |  | 4800 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2014/01/10 | 2014/02/28 |  |  |  | 2014/03/05 | Tim Johnson | [7 empty] | True | George Smedley, Jr. | 11339 | 000030000017332 | 2013/12/20 | False
Comerica - SO11350 - Change order for Campaign Changes | Project Kick Off | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Planning & Design | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Hardware / Software Procurement | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Readiness Validation | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Product Installation | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Product Integration | 7 - Training |  | 1800 | 1800 | Tim Johnson | 100 | 1800 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  | 2014/01/07 | 2014/01/07 | Tim Johnson | [7 empty] | True | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Training | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Consulting & Technical Reviews | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Support Turnover | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Comerica - SO11350 - Change order for Campaign Changes | Project Closure | 7 - Training |  | 1800 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/01/08 |  |  |  |  | Tim Johnson | [7 empty] | False | Tracey Vaughan | 11350 | LIF8226 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Project Kick Off | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/02/20 | Philip Haskings | [7 empty] | True | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Planning & Design | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/02/25 | Philip Haskings | [7 empty] | True | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Hardware / Software Procurement | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Readiness Validation | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Product Installation | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Product Integration | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Training | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Consulting & Technical Reviews | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Support Turnover | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 100 | 32400 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  | 2014/05/30 |  | Philip Haskings | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
Credit Union One - SO11363 - oWFM | Project Closure | 4 - Readiness Validation |  | 32400 | 34485 | Philip Haskings | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Dave Breuer | 11363 | 7700244965 | 2013/12/30 | False
HSBC - PM - June 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC - PM - June 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/06/01 | 2014/06/30 |  |  | 2014/06/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/06/01 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Project Kick Off | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  | 2014/03/31 | Tim Johnson | [7 empty] | True | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Planning & Design | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Hardware / Software Procurement | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Readiness Validation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Product Installation | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Product Integration | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 100 | 9000 | 0 | 0 | 2014/01/06 | 2014/04/30 | 2014/05/31 |  | 2014/05/31 |  | John Randall | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Training | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Consulting & Technical Reviews | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Support Turnover | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
HSBC- SO11314 - ECC VH TopLayer_Shoremicro 1G-Copper | Project Closure | 2 - Planning & Design |  | 9000 | 9000 | John Randall | 0 | 0 | 0 | 0 | 2014/01/06 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Todd Folkes | 11314 | D07122996 | 2013/12/17 | False
Vanguard SO11382 - PS custom data | Project Kick Off | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Planning & Design | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Hardware / Software Procurement | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Readiness Validation | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Product Installation | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Product Integration | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Training | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Consulting & Technical Reviews | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Support Turnover | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 0 | 0 | 0 | 0 | 2014/01/20 | 2014/01/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Steven Smith |  | 1 | 2014/01/06 | False
Vanguard SO11382 - PS custom data | Project Closure | 6 - Product Integration |  | 3900 | 3900 | Tim Johnson | 100 | 3900 | 0 | 0 | 2014/01/20 | 2014/01/28 | 2014/01/20 | 2014/01/20 | 2014/01/21 | 2014/01/28 | Tim Johnson | [7 empty] | True | Steven Smith |  | 1 | 2014/01/06 | False
MedImpact - SO11345 - License Adds | Project Kick Off | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Planning & Design | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Hardware / Software Procurement | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Readiness Validation | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Product Installation | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Product Integration | Project Closure |  | 800 | 0 | Stewart Futcher | 100 | 800 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  | 2014/01/31 | 2014/01/28 | Stewart Futcher | [7 empty] | True | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Training | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Consulting & Technical Reviews | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Support Turnover | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
MedImpact - SO11345 - License Adds | Project Closure | Project Closure |  | 800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2014/01/07 | 2014/02/28 |  |  |  | 2014/01/31 | Stewart Futcher | [7 empty] | True | Alberto Otazua | 11345 | 278092 | 2013/12/27 | False
Toyota Canada, Inc. - SO10414 v11 Project | Project Kick Off | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/10 | 2013/06/10 | 2013/06/10 | 2013/06/11 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Planning & Design | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/17 | 2013/06/17 | 2013/06/28 | 2013/06/28 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Hardware / Software Procurement | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/06/14 | 2013/06/14 | 2013/06/17 | 2013/06/17 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Readiness Validation | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/08 | 2013/07/08 | 2013/07/09 | 2013/07/09 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Product Installation | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/15 | 2013/07/15 | 2013/07/26 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Product Integration | Project Closure |  | 31300 | 0 | Stewart Futcher | 100 | 31300 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/07/15 | 2013/07/15 | 2013/08/30 | 2013/08/16 | Stewart Futcher | [7 empty] | True | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Training | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/16 |  | 2013/09/20 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Consulting & Technical Reviews | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/08/19 | 2013/08/19 | 2013/08/26 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Support Turnover | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/17 |  | 2013/09/17 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Toyota Canada, Inc. - SO10414 v11 Project | Project Closure | Project Closure |  | 31300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/06/17 | 2013/08/30 | 2013/09/23 |  | 2013/09/23 |  | Stewart Futcher | [7 empty] | False | Savio Correia | 10414 | 20007349 | 2013/06/11 | True | 2013/08/30
Molecular Devices - SO10201 - Germany - Quest System | Project Kick Off | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Planning & Design | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Hardware / Software Procurement | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/12 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Product Installation | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Product Integration | Project Closure |  | 3175 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Molecular Devices - SO10201 - Germany - Quest System | Project Closure | Project Closure |  | 3175 | 0 | Philip Haskings | 100 | 3175 | 0 | 0 | [5 empty] | 2013/07/19 | Philip Haskings | [7 empty] | True |  | 10201 | 40422301 | 2013/04/22 | True | 2013/07/19
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Project Kick Off | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Planning & Design | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Hardware / Software Procurement | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Readiness Validation | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Product Installation | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Product Integration | Project Closure |  | 6400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10441 -36 Licenses and move SPANs | Project Closure | Project Closure |  | 6400 | 0 | Philip Haskings | 100 | 6400 | 0 | 0 | 2013/06/19 | 2013/08/20 |  |  |  | 2013/08/27 | Philip Haskings | [7 empty] | True |  | 10441 | 7700240515 | 2013/06/17 | True | 2013/08/28
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Project Kick Off | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Planning & Design | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/19 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Hardware / Software Procurement | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/25 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Product Installation | Project Closure |  | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/06/25 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Siemens - Medstar Health - SO10443 - Remote install of new licenses | Project Closure | Project Closure |  | 750 | 0 | Philip Haskings | 100 | 750 | 0 | 0 | [5 empty] | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10443 | 7700240553 | 2013/06/17 | True | 2013/07/12
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Project Kick Off | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/06/24 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Planning & Design | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  | 2013/07/22 |  | 2013/07/03 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Hardware / Software Procurement | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/03 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Product Installation | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
Black Box - Papa Johns - SO10446 - Remote 50 QM/WFM License Addition | Project Closure | Project Closure | Verint-oWFO | 750 | 0 | Philip Haskings | 100 | 750 | 0 | 0 | 2013/06/24 | 2013/08/26 |  |  |  | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 10446 | NCI0000248547 | 2013/06/17 | True | 2013/08/26
CDW - AFNI - SO10447 - License Moves | Project Kick Off | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Planning & Design | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Hardware / Software Procurement | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/07/12 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Product Integration | Project Closure |  | 950 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  |  | 2013/08/21 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
CDW - AFNI - SO10447 - License Moves | Project Closure | Project Closure |  | 950 | 0 | Philip Haskings | 100 | 950 | 0 | 0 | 2013/08/21 | 2013/11/30 |  |  | 2013/09/30 | 2013/08/21 | Philip Haskings | [7 empty] | True | David Eyre | 10447 | 000030000015233 | 2013/06/17 | False
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Project Kick Off | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  |  | 2013/06/21 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Planning & Design | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  |  | 2013/07/31 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Product Installation | Project Closure |  | 4800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/06/21 | 2013/09/06 | 2013/08/22 |  |  | 2013/09/06 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Siemens - HEB Grocery - SO10430 - Adpater Change - SDK Patch | Project Closure | Project Closure |  | 4800 | 0 | Philip Haskings | 100 | 4800 | 0 | 0 | 2013/06/21 | 2013/09/06 |  |  | 2013/09/10 | 2013/09/10 | Philip Haskings | [7 empty] | True | Gail Morace | 10430 | 7700240579 | 2013/06/19 | True | 2013/09/11
Molecular Devices - SO10431 - Research 10 California | Project Kick Off | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Planning & Design | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 |  |  |  | 2013/07/09 |  | 2013/07/12 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Hardware / Software Procurement | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/09 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Product Installation | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Product Integration | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Molecular Devices - SO10431 - Research 10 California | Project Closure | Project Closure | MolDev-Research 10 | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | [5 empty] | 2013/07/11 | Philip Haskings | [7 empty] | True |  | 10431 | 40613301 | 2013/06/24 | True | 2013/07/25
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Project Kick Off | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/13 | 2014/01/13 | 2014/01/14 | 2014/04/08 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Planning & Design | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/20 | 2014/01/20 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Hardware / Software Procurement | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/27 | 2014/01/27 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Readiness Validation | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/01/27 | 2014/01/28 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Product Installation | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/02/17 | 2014/02/17 | 2014/02/21 | 2014/02/21 | Tim Johnson | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Product Integration | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 60 | 53250 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/02/10 | 2014/03/10 | 2014/02/21 | 2014/02/28 | Stewart Futcher | [7 empty] | True | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Training | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 20 | 17750 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/04/28 |  | 2014/05/02 |  | Stewart Futcher | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Consulting & Technical Reviews | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/05/09 |  | 2014/05/09 |  | Tim Johnson | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Support Turnover | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 20 | 17750 | 0 | 0 | 2013/11/18 | 2014/02/28 | 2014/05/02 |  | 2014/05/09 |  | Stewart Futcher | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
Monster Technologies - SO11179 - oQM v11.1 Services + PCI + SSO + ADA/AET | Project Closure | 6 - Product Integration |  | 88750 | 103000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/11/18 | 2014/02/28 |  |  |  |  | Tim Johnson | [7 empty] | False | Rob Bernstein | 11179 | 59309 | 2013/11/15 | False
HSBC - PM - April 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
HSBC - PM - April 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/04/01 | 2014/04/30 |  |  | 2014/04/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/04/01 | False
CMS Medicare Phase II - Cluster 2 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  | 2013/12/17 | 2013/12/23 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 2 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/05 | 2013/12/17 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
HSBC - PM - May 2014 | Project Kick Off | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Planning & Design | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Hardware / Software Procurement | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Readiness Validation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Product Installation | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Product Integration | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Training | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Support Turnover | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
HSBC - PM - May 2014 | Project Closure | 1 - Project Kick Off |  | 17000 | 0 | Matt Hogan | 100 | 17000 | 0 | 0 | 2014/05/01 | 2014/05/30 |  |  | 2014/05/30 |  | Matt Hogan | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2014/05/01 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  | 2013/12/09 |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  | 2014/01/31 | 2013/12/12 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
BBVA - SO11208 - Secondary Mkt Group B-Ham 5 Seats Voice Only | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/01/31 |  |  |  | 2013/12/16 | Philip Haskings | [7 empty] | True | Brian Abston | 11208 | 186191 | 2013/11/26 | False
VWR - SO11215 - 350 seats of OWFM SKY | Project Kick Off | Project Closure |  | 50786 | 50786 | Philip Haskings | 33 | 16759.38 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Planning & Design | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Hardware / Software Procurement | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 | 2013/12/31 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Readiness Validation | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2013/12/13 |  | Philip Haskings | [7 empty] | False | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Product Installation | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/01/24 |  | Philip Haskings | [7 empty] | False | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Product Integration | Project Closure |  | 50786 | 50786 | Philip Haskings | 33 | 16759.38 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/03 | 2014/02/27 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Training | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/02/07 | 2014/02/07 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Consulting & Technical Reviews | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 | 2014/03/06 |  | 2014/03/06 | 2014/03/07 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Support Turnover | Project Closure |  | 50786 | 50786 | Philip Haskings | 34 | 17267.24 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/12 | 2014/03/12 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
VWR - SO11215 - 350 seats of OWFM SKY | Project Closure | Project Closure |  | 50786 | 50786 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/03/14 |  |  | 2014/03/14 | 2014/03/13 | Philip Haskings | [7 empty] | True | Roger Lopez | 11215 | 2478 | 2013/11/25 | False
CMS Medicare Phase II - Cluster 3 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  | 2014/01/03 | 2014/01/15 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 3 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/23 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2014/01/13 | 2014/01/23 | 2014/01/03 | 2014/01/03 | 2014/01/23 | 2014/01/31 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 4 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/13 | 2014/01/23 |  |  |  | 2014/02/10 | Tim Johnson | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  | 2014/02/18 | 2014/02/27 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 5 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2014/01/29 | 2014/02/18 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Project Kick Off | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Planning & Design | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Hardware / Software Procurement | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Readiness Validation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Product Installation | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Product Integration | Project Closure |  | 207857 | 0 | John Randall | 100 | 207857 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  | 2013/11/27 | 2013/11/25 | John Randall | [7 empty] | True | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Training | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Consulting & Technical Reviews | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Support Turnover | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
CMS Medicare Phase II - Cluster 1 | Project Closure | Project Closure |  | 207857 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/21 | 2013/11/27 |  |  |  |  | Tim Johnson | [7 empty] | False | Scott Willis | 11195 | 0000016423 | 2013/11/20 | False
BBVA - SO11207 - Remote License Adds | Project Kick Off | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/02 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Planning & Design | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/06 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Product Integration | Project Closure |  | 4200 | 0 | Philip Haskings | 100 | 4200 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  | 2014/01/31 | 2013/12/12 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
BBVA - SO11207 - Remote License Adds | Project Closure | Project Closure |  | 4200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/11/26 | 2014/01/31 |  |  |  | 2013/12/16 | Philip Haskings | [7 empty] | True | Joshua McCarty | 11207 | 190230 | 2013/11/25 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Project Kick Off | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Planning & Design | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Hardware / Software Procurement | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Readiness Validation | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Product Installation | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Product Integration | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/03 | 2013/12/04 | 2013/12/06 | Tim Johnson | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Training | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Consulting & Technical Reviews | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/04 | 2013/12/09 | 2013/12/06 | 2013/12/18 | Tim Johnson | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Support Turnover | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/12/03 | 2013/12/03 |  |  |  |  | Tim Johnson | [7 empty] | False | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Vanguard - SO11238 - Pro Svcs Mapping Project | Project Closure | 9 - Support Turnover |  | 5400 | 5400 | Kent Pylant | 100 | 5400 | 0 | 0 | 2013/12/03 | 2013/12/03 | 2013/12/06 | 2013/12/10 | 2013/12/10 | 2013/12/11 | Kent Pylant | [7 empty] | True | Michelle Robinson | 11238 | 01000-0000199721 | 2013/11/27 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Project Kick Off | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2013/12/16 | 2013/12/17 | 2013/12/16 | 2013/12/17 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Planning & Design | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/06 | 2014/01/06 | 2014/01/06 | 2014/01/24 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Hardware / Software Procurement | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/13 | 2014/01/14 | 2014/01/13 | 2014/01/14 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Readiness Validation | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/20 | 2014/01/21 | 2014/01/20 | 2014/01/22 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Product Installation | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/01/20 | 2014/01/20 | 2014/01/31 | 2014/01/31 | Tim Johnson | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Product Integration | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 100 | 71300 | 0 | 0 | 2013/12/02 | 2014/02/28 |  |  | 2014/01/31 | 2014/01/28 | Stewart Futcher | [7 empty] | True | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Training | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/03/24 | 2014/03/24 | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Consulting & Technical Reviews | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/21 |  | 2014/04/21 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Support Turnover | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/24 |  | 2014/04/24 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Commonwealth of Mass - SO11219 - Avaya v12 oWFO | Project Closure | 7 - Training |  | 71300 | 72000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 | 2014/04/25 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Charles McCann | 11219 | 279271 | 2013/11/26 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Project Kick Off | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/01/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Planning & Design | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/01/14 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Hardware / Software Procurement | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Product Integration | Project Closure |  | 1000 | 1000 | Philip Haskings | 100 | 1000 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  | 2014/04/25 | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Starwood Hotels and Resorts - SO11230 - D480 Remote Install | Project Closure | Project Closure |  | 1000 | 1000 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/10 | 2014/04/30 |  |  |  | 2014/04/08 | Philip Haskings | [7 empty] | True | Craig Frick | 11230 | 4500079309 | 2013/12/02 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Project Kick Off | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Planning & Design | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Hardware / Software Procurement | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Readiness Validation | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Product Installation | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Product Integration | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Training | Project Closure |  | 3600 | 0 | John Randall | 100 | 3600 | 0 | 0 | 2013/12/02 | 2014/02/05 | 2014/02/04 |  | 2014/02/05 | 2014/02/12 | John Randall | [7 empty] | True | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Consulting & Technical Reviews | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Support Turnover | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 |  |  |  |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Cerium Networks - NFS - SO11202 - 2 day QM Training (Forms Administration & QM End User Training) | Project Closure | Project Closure |  | 3600 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/05 | 2014/02/05 |  | 2014/02/05 |  | Tim Johnson | [7 empty] | False | Helene Thompson | 11202 | 211824 | 2013/11/22 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Project Kick Off | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 | 2013/12/10 |  |  | 2013/12/16 | Tim Johnson | [7 empty] | True | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Planning & Design | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Hardware / Software Procurement | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Readiness Validation | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Product Installation | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Product Integration | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 100 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  | 2014/02/28 |  | Charlene Dennis | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Training | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Consulting & Technical Reviews | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Support Turnover | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Regional Medical Center - SO11239 - Avaya OEM CAM changes and training | Project Closure | 2 - Planning & Design |  | 0 | 4800 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/04 | 2014/01/22 |  |  |  |  | Tim Johnson | [7 empty] | False | Craig Schneider | 11239 | P16564 | 2013/12/02 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Project Kick Off | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  |  | 2014/01/31 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Planning & Design | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 25 | 30505 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/02/21 | 2014/02/25 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Hardware / Software Procurement | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/03/14 | 2014/03/14 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Readiness Validation | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/03/28 | 2014/03/28 | Philip Haskings | [7 empty] | True | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Product Installation | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/03/31 | 2014/03/31 | 2014/04/04 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Product Integration | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 50 | 61010 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/04/25 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Training | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/04/28 |  | 2014/06/06 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Consulting & Technical Reviews | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 | 2014/06/11 |  | 2014/06/11 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Support Turnover | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 25 | 30505 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/06/16 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Bluegreen - SO11253 - Avaya v12 aWFO | Project Closure | 5 - Product Installation |  | 122020 | 122020 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/12/06 | 2014/05/30 |  |  | 2014/06/20 |  | Philip Haskings | [7 empty] | False | Kyle Fahsel | 11253 | 65922 | 2013/12/05 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Project Kick Off | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2013/12/04 |  | 2013/12/11 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Planning & Design | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2013/12/16 | 2013/12/23 | 2013/12/30 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Product Installation | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/01/24 |  | 2014/02/27 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Product Integration | Project Closure |  | 6400 | 0 | Charlene Dennis | 100 | 6400 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/01/27 | 2014/02/28 | 2014/01/27 | Charlene Dennis | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
Mitsubishi - SO11224 - Adding TOM and UST to Avaya oWFO | Project Closure | Project Closure |  | 6400 | 0 | Charlene Dennis | 0 | 0 | 0 | 0 | 2013/12/02 | 2014/02/28 |  | 2014/02/24 |  | 2014/02/24 | Tim Johnson | [7 empty] | True | Hiram Romero | 11224 | 13032 | 2013/11/27 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Project Kick Off | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Planning & Design | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Hardware / Software Procurement | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/07 |  | 2013/10/10 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Product Integration | Project Closure |  | 3700 | 3700 | Philip Haskings | 100 | 3700 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/11 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10837 - Information Security-BROCK 12 Seats | Project Closure | Project Closure |  | 3700 | 3700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/11/11 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10837 | 181389 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Project Kick Off | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Planning & Design | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Hardware / Software Procurement | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Product Integration | Project Closure |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/11 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
BBVA - SO10836 - Information Security-BROCK 19 Seats | Project Closure | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10836 | 181387 | 2013/09/26 | False
CDW - Laureate - SO10850 - AIM Configuration | Project Kick Off | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Planning & Design | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Hardware / Software Procurement | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Readiness Validation | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Product Installation | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Product Integration | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Training | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Consulting & Technical Reviews | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Support Turnover | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 10850 | 00003-0000016265 | 2013/09/27 | False
CDW - Laureate - SO10850 - AIM Configuration | Project Closure | 1 - Project Kick Off |  | 8000 | 8000 | Stewart Futcher | 100 | 8000 | 0 | 0 | 2013/07/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/30 | Stewart Futcher | [7 empty] | True |  | 10850 | 00003-0000016265 | 2013/09/27 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Project Kick Off | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Planning & Design | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Hardware / Software Procurement | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Readiness Validation | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/14 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Product Installation | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/05/12 |  | 2014/05/30 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Product Integration | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 100 | 25500 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/06/30 |  | 2014/06/30 |  | John Randall | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Training | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/03/31 |  | 2014/04/11 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Consulting & Technical Reviews | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/14 |  | 2014/04/25 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Support Turnover | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/28 |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Trulia - SO10853 - SKY aWFM - 60 Seats | Project Closure | 1 - Project Kick Off |  | 25500 | 1 | John Randall | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/02/10 | 2014/04/28 |  | 2014/04/28 |  | Tim Johnson | [7 empty] | False | Keith Donaldson | 10853 | Amendment 1 REF 3089 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Project Kick Off | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 | 2013/10/24 | 2013/10/24 | 2013/10/24 | 2013/10/24 | Tim Johnson | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Planning & Design | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 30 | 26649 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Hardware / Software Procurement | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2013/11/29 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Readiness Validation | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2013/12/03 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Product Installation | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 20 | 17766 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Product Integration | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 30 | 26649 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 | 2014/01/07 | Stewart Futcher | [7 empty] | True | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Training | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/17 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Consulting & Technical Reviews | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/01/24 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Support Turnover | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 20 | 17766 | 0 | 0 | 2013/09/30 | 2014/01/31 | 2014/04/30 |  | 2014/04/30 |  | Stewart Futcher | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Epson - SO10859 - Upgrade to Verint oQM 7.8.2 with DPA - 100 Seats | Project Closure | 7 - Training |  | 88830 | 93000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/01/31 |  |  | 2014/02/03 |  | Tim Johnson | [7 empty] | False | Eileen Woods | 10859 | 4500014458 | 2013/09/26 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Project Kick Off | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Planning & Design | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Hardware / Software Procurement | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/15 | 2013/10/15 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Readiness Validation | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/15 | 2013/10/15 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Product Installation | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/15 | 2013/10/15 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Product Integration | Project Closure |  | 4000 | 4000 | Stewart Futcher | 100 | 4000 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/15 | 2013/10/18 | 2013/10/18 | Stewart Futcher | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Training | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/15 | 2013/10/15 | 2013/10/17 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Consulting & Technical Reviews | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/14 | 2013/10/16 | 2013/10/17 | 2013/10/17 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Support Turnover | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 | 2013/10/18 | 2013/10/18 | 2013/10/18 | 2013/10/18 | Tim Johnson | [7 empty] | True | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Toyota Canada - SO10877 - Services to Install v11 AIM | Project Closure | Project Closure |  | 4000 | 4000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/02 | 2013/11/29 |  |  |  |  | Tim Johnson | [7 empty] | False | Savio Correia | 10877 | 20007657 | 2013/09/30 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Project Kick Off | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Planning & Design | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Hardware / Software Procurement | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Readiness Validation | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Product Installation | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Product Integration | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Training | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Consulting & Technical Reviews | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Support Turnover | Project Closure |  | 3200 | 5700 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/09/30 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
Carousel - Contra Costa County - SO10870 - Change order to existing project | Project Closure | Project Closure |  | 3200 | 5700 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2013/09/30 | 2013/10/31 | 2013/10/07 | 2013/10/07 | 2013/10/31 | 2013/10/31 | Stewart Futcher | [7 empty] | True | David Eisenlohr | 10870 | 271935 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Project Kick Off | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 |  |  |  | 2013/10/03 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Planning & Design | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 |  |  | 2013/10/11 | 2013/10/23 | Philip Haskings | [7 empty] | True | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Product Installation | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 | 2013/11/15 |  | 2013/11/18 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
BMW - SO10862 - GM Installation and Configuration | Project Closure | 3 - Hardware / Software Procurement |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/09/30 | 2014/03/31 | 2014/03/31 |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Wally Wolfe | 10862 | 4600210314 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Project Kick Off | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  |  | 2013/10/25 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Planning & Design | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2013/10/30 |  | 2013/11/14 | 2013/11/15 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Product Installation | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2013/11/18 |  | 2013/11/22 | 2013/11/19 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Product Integration | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 100 | 21069 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  | 2013/12/31 | 2013/12/31 | Philip Haskings | [7 empty] | True | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Training | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/03/31 |  | 2014/04/04 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/04/11 |  | 2014/04/11 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Support Turnover | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 | 2014/04/18 |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
Golfsmith - SO10863 - SKY aWFM - 35 Seats | Project Closure | 8 - Consulting & Technical Reviews |  | 21069 | 21069 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/04/18 |  |  | 2014/04/18 |  | Philip Haskings | [7 empty] | False | Keith Donaldson | 10863 | 2973 | 2013/09/27 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Project Kick Off | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Planning & Design | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/04 | 2013/10/03 | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Product Integration | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/10 | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA - SO10834 - Information Security - BROCK 14 Seats | Project Closure | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10834 | 181386 | 2013/09/26 | False
BBVA -SO10893 - Services_HUB Recovery Project | Project Kick Off | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 |  |  | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Planning & Design | Project Closure |  | 8700 | 8700 | Philip Haskings | 100 | 8700 | 0 | 0 | 2013/10/01 | 2013/10/14 |  |  | 2013/10/04 | 2013/10/03 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Consulting & Technical Reviews | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/07 |  | 2013/10/11 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
BBVA -SO10893 - Services_HUB Recovery Project | Project Closure | Project Closure |  | 8700 | 8700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/14 | 2013/10/14 |  | 2013/10/14 | 2013/10/25 | Philip Haskings | [7 empty] | True |  | 10893 | 138974 | 2013/10/01 | False
HSBC PM - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Planning & Design | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Product Installation | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Product Integration | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Training | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Support Turnover | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC PM - August 2013 | Project Closure | 1 - Project Kick Off |  | 20160 | 0 | Tim Johnson | 100 | 20160 | 0 | 0 | 2013/08/01 | 2013/08/31 |  |  | 2013/08/31 | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - PM - September 2013 | Project Kick Off | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Planning & Design | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Readiness Validation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Product Installation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Product Integration | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Training | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Support Turnover | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - September 2013 | Project Closure | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 100 | 19200 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - PM - October 2013 | Project Kick Off | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Planning & Design | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Readiness Validation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Product Installation | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Product Integration | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Training | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Support Turnover | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - October 2013 | Project Closure | 1 - Project Kick Off |  | 19200 | 0 | Tim Johnson | 100 | 19200 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
HSBC - PM - November 2013 | Project Kick Off | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Planning & Design | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Readiness Validation | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Product Installation | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Product Integration | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Training | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Support Turnover | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - November 2013 | Project Closure | 1 - Project Kick Off |  | 13440 | 0 | Matt Hogan | 100 | 13440 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  | 2013/11/29 | 2013/11/27 | Matt Hogan | [7 empty] | True |  | 99999 | 99999 | 2013/11/01 | False
HSBC - PM - December 2013 | Project Kick Off | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Planning & Design | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Hardware / Software Procurement | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Readiness Validation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Product Installation | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Product Integration | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Training | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Consulting & Technical Reviews | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Support Turnover | Project Closure |  | 17280 | 0 | Matt Hogan | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - PM - December 2013 | Project Closure | Project Closure |  | 17280 | 0 | Matt Hogan | 100 | 17280 | 0 | 0 | 2013/12/01 | 2013/12/31 | 2013/12/01 | 2013/12/01 | 2013/12/31 | 2013/12/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - September 2013 | Project Kick Off | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Planning & Design | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Readiness Validation | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Product Installation | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Product Integration | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Training | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Support Turnover | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - September 2013 | Project Closure | 1 - Project Kick Off |  | 20672 | 0 | Tim Johnson | 100 | 20672 | 0 | 0 | 2013/09/01 | 2013/09/30 |  |  | 2013/09/30 | 2013/09/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/09/01 | True | 2013/09/30
HSBC - Admin - August 2013 | Project Kick Off | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Planning & Design | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Hardware / Software Procurement | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Readiness Validation | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Product Installation | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Product Integration | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Training | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Consulting & Technical Reviews | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Support Turnover | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
HSBC - Admin - August 2013 | Project Closure | 1 - Project Kick Off |  | 23936 | 0 | Tim Johnson | 100 | 23936 | 0 | 0 | 2013/08/01 | 2013/08/30 |  |  | 2013/08/31 | 2013/08/31 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/08/01 | True | 2013/08/31
Flagstar - SO10909 - Health Check and SSL services | Project Kick Off | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  |  | 2013/10/01 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Planning & Design | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/10/23 | 2013/10/23 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Hardware / Software Procurement | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/01 | 2014/02/28 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Product Installation | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/04 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Product Integration | Project Closure |  | 12800 | 12800 | Philip Haskings | 100 | 12800 | 0 | 0 | 2013/10/04 | 2014/03/28 | 2014/03/10 |  | 2014/03/14 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
Flagstar - SO10909 - Health Check and SSL services | Project Closure | Project Closure |  | 12800 | 12800 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/04 | 2014/03/28 |  |  | 2013/11/11 | 2014/03/31 | Philip Haskings | [7 empty] | True | Jeff Schang | 10909 | 00003-0000016390 | 2013/10/03 | False
HSBC - Admin - October 2013 | Project Kick Off | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Planning & Design | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Hardware / Software Procurement | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Readiness Validation | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Product Installation | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Product Integration | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Training | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Consulting & Technical Reviews | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Support Turnover | Project Closure |  | 23392 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  |  |  | Tim Johnson | [7 empty] | False |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - October 2013 | Project Closure | Project Closure |  | 23392 | 0 | Tim Johnson | 100 | 23392 | 0 | 0 | 2013/10/01 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/30 | Tim Johnson | [7 empty] | True |  | 99999 | 99999 | 2013/10/01 | False
HSBC - Admin - November 2013 | Project Kick Off | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Planning & Design | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Hardware / Software Procurement | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Readiness Validation | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Product Installation | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Product Integration | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Training | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Consulting & Technical Reviews | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Support Turnover | Project Closure |  | 20672 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - November 2013 | Project Closure | Project Closure |  | 20672 | 0 | Tim Johnson | 100 | 20672 | 0 | 0 | 2013/11/01 | 2013/11/30 |  |  | 2013/11/30 | 2013/11/27 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/11/01 | False
HSBC - Admin - December 2013 | Project Kick Off | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Planning & Design | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Hardware / Software Procurement | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Readiness Validation | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Product Installation | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Product Integration | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Training | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Consulting & Technical Reviews | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Support Turnover | Project Closure |  | 17680 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  |  |  | Tim Johnson | [7 empty] | False | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
HSBC - Admin - December 2013 | Project Closure | Project Closure |  | 17680 | 0 | Tim Johnson | 100 | 17680 | 0 | 0 | 2013/12/01 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/31 | Tim Johnson | [7 empty] | True | Chad Curnutt | 99999 | 99999 | 2013/12/01 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Project Kick Off | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/09/16 | 2013/09/16 | 2013/09/16 | 2013/09/16 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Planning & Design | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/07 | 2013/10/07 | 2013/10/11 | 2013/10/11 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Hardware / Software Procurement | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/14 | 2013/10/14 | 2013/10/14 | 2013/10/15 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Readiness Validation | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/08 | 2013/10/08 | 2013/10/09 | 2013/10/09 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Product Installation | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/21 | 2013/10/21 | 2013/11/08 | 2013/11/08 | Tim Johnson | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Product Integration | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 | 2013/10/21 | 2013/10/21 | 2013/11/29 | 2013/11/19 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Training | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/20 |  | Stewart Futcher | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Consulting & Technical Reviews | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/23 |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Support Turnover | Project Closure |  | 71000 | 79000 | Stewart Futcher | 100 | 71000 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2013/12/23 | 2013/12/20 | Stewart Futcher | [7 empty] | True | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Google - SO10934 - Avaya oWFM Implementation + BM + SQL Replication | Project Closure | Project Closure |  | 71000 | 79000 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/10/08 | 2014/01/31 |  |  | 2014/01/03 |  | Tim Johnson | [7 empty] | False | Yvonne Nachtigall | 10934 | 5009558 | 2013/10/08 | False
Laureate/Adviceline | Project Kick Off | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Planning & Design | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Readiness Validation | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Product Installation | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Product Integration | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Training | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Support Turnover | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
Laureate/Adviceline | Project Closure | 1 - Project Kick Off |  | 0 | 1800 | Tim Johnson | 0 | 0 | 0 | 0 | [6 empty] | Tim Johnson | [7 empty] | False |  |  | LBQ0013 | 2013/10/09 | False
NGS | Project Kick Off | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Planning & Design | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Hardware / Software Procurement | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Readiness Validation | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Product Installation | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Product Integration | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Training | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Consulting & Technical Reviews | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Support Turnover | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
NGS | Project Closure | 1 - Project Kick Off |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/14 | [5 empty] | Tim Johnson | [7 empty] | False |  |  | 12345 | 2013/10/14 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Project Kick Off | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2013/12/20 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Planning & Design | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2013/12/24 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Hardware / Software Procurement | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  |  | 2014/01/10 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Product Installation | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 | 2014/01/20 |  | 2014/01/21 | 2014/02/26 | Philip Haskings | [7 empty] | True | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Product Integration | 7 - Training |  | 4700 | 4700 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  | 2014/03/31 |  | Philip Haskings | [7 empty] | False | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
Wells Fargo Bank - SO10958 - Onsite Server/EC/Card Installation | Project Closure | 7 - Training |  | 4700 | 4700 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2014/02/28 |  |  | 2014/01/31 |  | Philip Haskings | [7 empty] | False | Brent Lyon | 10958 | 20131010RC | 2013/10/11 | False
MolDev - SO10939 - Research 10 - Europe | Project Kick Off | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/03 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Planning & Design | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Hardware / Software Procurement | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  |  | 2013/12/10 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Product Installation | Project Closure |  | 3175 | 3295 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/11 | 2013/12/31 | 2013/12/12 |  | 2013/12/13 | 2013/12/12 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
MolDev - SO10939 - Research 10 - Europe | Project Closure | Project Closure |  | 3175 | 3295 | Philip Haskings | 100 | 3175 | 0 | 0 | 2013/10/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/12/16 | Philip Haskings | [7 empty] | True | Guillaume Frugier | 10939 | 41009301 | 2013/10/09 | False
Xerox - SO10936 - Wellness Check | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  |  | 2013/10/11 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
Xerox - SO10936 - Wellness Check | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  |  | 2013/10/15 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
Xerox - SO10936 - Wellness Check | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/10/10 | 2013/10/31 |  |  | 2013/10/31 | 2013/10/22 | Philip Haskings | [7 empty] | True |  | 10936 | AC218851 | 2013/10/08 | False
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Project Kick Off | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/08/24 | 2012/08/24 | 2012/08/24 | 2012/08/29 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Planning & Design | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/08/27 | 2012/08/27 | 2012/09/21 | 2012/09/28 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Hardware / Software Procurement | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/10/01 | 2012/10/05 | 2012/11/02 | 2012/11/26 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Readiness Validation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/12/10 | 2012/12/10 | 2012/12/12 | 2012/12/17 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Product Installation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2012/12/17 | 2012/12/17 | 2012/12/21 | 2012/12/21 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Product Integration | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2013/01/07 | 2013/01/07 | 2013/01/11 | 2013/01/14 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Training | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Consulting & Technical Reviews | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Support Turnover | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  | 2013/02/11 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | Project Closure | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False | Matt Brush | 9403 | 00003-0000012976
CDW - Federal Mogul Corporation - SO9403 Op QM v11 Implementation | QM v11 Implementation | 6 - Product Integration |  | 7410 | 0 | Stewart Futcher | 100 | 7410 | 0 | 0 | 2012/10/22 | 2013/01/31 | 2013/01/07 | 2013/01/07 | 2013/01/11 | 2013/01/11 | Stewart Futcher | [7 empty] | True | Matt Brush | 9403 | 00003-0000012976
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Project Kick Off | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/10/09 | 2012/10/09 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Planning & Design | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Hardware / Software Procurement | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Readiness Validation | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/13 | 2012/11/13 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Product Installation | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Product Integration | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 100 | 17400 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/19 | 2012/11/19 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Training | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Consulting & Technical Reviews | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Support Turnover | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Laura Stern | 9415 | 3717
Liberty Healthcare - SO9415 Port St. Lucie Weekend Server Move | Project Closure | 2 - Planning & Design |  | 17400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/19 |  |  | 2012/11/26 | 2012/11/27 | Kent Pylant | [7 empty] | True | Laura Stern | 9415 | 3717
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Project Kick Off | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/08/09 | 2012/08/09 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Planning & Design | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/08/16 | 2012/08/24 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Readiness Validation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Product Installation | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Product Integration | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/18 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Training | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Support Turnover | Project Closure |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Affiliated Computer Services - SO9412 Chassis Move (Aziz H) | Project Closure | Project Closure |  | 0 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/10/18 | 2012/10/19 |  |  | 2012/10/31 |  | Kent Pylant | [7 empty] | False |  | 9412 | Tarik
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Project Kick Off | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/16 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Planning & Design | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/26 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Hardware / Software Procurement | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/25 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Readiness Validation | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/11/15 | 2012/11/15 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Product Installation | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/29 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Product Integration | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 100 | 4700 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/11/27 | 2012/11/27 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Training | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Consulting & Technical Reviews | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/31 |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Support Turnover | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9422 | 38119
Express Scripts, INc. - SO9422 Trunk Tapping Hardware - Ft. Worth, TX - D Sabo | Project Closure | 6 - Product Integration |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/27 |  |  | 2012/10/31 | 2012/11/29 | Kent Pylant | [7 empty] | True |  | 9422 | 38119
CDW - State Auto Insurance - SO8515 | State Auto v11 WFO | Project Closure |  | 26000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/09/21 |  |  | 2012/09/11 | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 8515 | 00003-0000011329
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/24 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/31 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/02 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/11/09 | 2012/11/29 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
Nike, Inc. c/o ACS, Inc. - SO9425 Remote Install - D Sabo | Nike - SO9425 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/26 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 9425 | 5600243639
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Project Kick Off | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 50 | 3900 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  | 2012/10/29 | 2012/10/16 | Stewart Futcher | [7 empty] | True |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Planning & Design | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Hardware / Software Procurement | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Readiness Validation | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Product Installation | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Product Integration | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Training | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Consulting & Technical Reviews | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Support Turnover | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/24 | 2012/11/30 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9424 | #
TOS, Ltd. - Chrysler Canada - SO9424 PBX Change | Project Closure | 2 - Planning & Design |  | 7800 | 0 | Stewart Futcher | 100 | 7800 | 0 | 0 | 2012/10/24 | 2012/11/30 | 2012/11/12 | 2012/11/13 | 2012/11/16 | 2012/11/26 | Stewart Futcher | [7 empty] | True |  | 9424 | #
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Project Kick Off | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/07 | 2013/01/07 | 2013/01/07 | 2013/01/07 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Planning & Design | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/14 | 2013/01/14 | 2013/01/25 | 2013/01/31 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Hardware / Software Procurement | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/31 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Readiness Validation | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/21 | 2012/10/18 | 2012/10/18 | 2012/10/18 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Product Installation | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 38.5 | 77385 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/28 | 2013/01/21 | 2013/02/15 | 2013/02/15 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Product Integration | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/01/28 | 2013/01/21 | 2013/02/15 | 2013/02/15 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Training | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/07/08 | 2013/07/08 | 2013/07/19 | 2013/07/19 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Consulting & Technical Reviews | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/07/08 | 2013/07/08 | 2013/08/23 | 2013/08/23 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Support Turnover | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/08/30 |  | 2013/08/30 |  | Stewart Futcher | [7 empty] | False | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Laureate Education SO9428 v11 WFO 10/22/12 - 11/20/12 | Project Closure | 9 - Support Turnover |  | 201000 | 0 | Stewart Futcher | 69.26 | 139212.6 | 0 | 0 | 2012/10/22 | 2012/11/21 | 2013/09/13 |  | 2013/09/30 | 2013/09/30 | Stewart Futcher | [7 empty] | True | Gene Kelly | 9428 | 00003-0000013174 | 2012/07/09 | False
Bluewater - Webster Bank - SO8981 v11 w/AET | Webster Bank - SO8981 | Project Closure |  | 28800 | 0 | Stewart Futcher | 100 | 28800 | 0 | 0 | 2012/08/14 | 2012/09/28 | 2012/12/10 | 2012/12/10 | 2012/12/21 | 2013/01/30 | Stewart Futcher | [7 empty] | True |  | SO 8981 | 129705
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - Planning SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 100 | 10000 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/24 | 2012/08/28 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/02 | 2012/07/02 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/16 | 2012/07/13 | Stewart Futcher | [7 empty] | True |  |  | 770023005
CDW - Mondial - Services SO7955 | Allianz - SO7955 | 9 - Support Turnover |  | 0 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/01/03 |  |  |  | 2012/06/29 | 2012/07/20 | Kent Pylant | [7 empty] | True | Matt Holbrook | CDW - SO007955 | 00003-0000010042
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/07/20 | 2012/07/18 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/08/10 | 2012/08/06 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/08/27 | 2012/08/27 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/09/14 | 2012/09/07 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/09/28 | 2012/09/28 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/01 | 2012/10/05 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/15 | 2012/10/22 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Intuition - SO8344 v11 Upgrade | Siemens - Intuition Systems / SO8344 | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/03/29 | 2012/08/31 |  |  | 2012/10/22 | 2012/10/25 | Stewart Futcher | [7 empty] | True |  |  | 770023005
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/09/24 | 2012/09/24 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/10/05 | 2012/10/05 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  | 2012/10/08 | 2012/10/08 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  | 2012/10/22 | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/08 | 2012/08/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9014 | 7700233331 |  | True
Siemens - Watson Clinic - SO9014 eQM License Update | Siemens - Watson Clinic / SO9014 | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/08/08 | 2012/08/31 | 2013/03/04 | 2013/05/17 | 2013/03/29 | 2013/05/17 | Stewart Futcher | [7 empty] | True |  | 9014 | 7700233331 |  | True
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/06/18 | 2012/06/18 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/06/25 | 2012/06/29 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/07/30 | 2012/08/03 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/13 | 2012/08/14 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/20 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/27 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/09/05 | 2012/09/07 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/27 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/24 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
CDW - Laureate Education SO8512 LAB Site Install | CDW - Laureate Education SO8512 LAB Site Install | Project Closure |  | 20000 | 0 | Stewart Futcher | 100 | 20000 | 0 | 0 | 2012/04/30 | 2012/07/27 |  |  | 2012/08/22 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011318
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/07/25 | 2012/07/27 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/07/27 | 2012/08/06 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/06/25 | 2012/06/26 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Fairmont Hotels - SO8751 - Remote Services | Fairmount - SO8751 | Project Closure |  | 500 | 0 | John Randall | 100 | 500 | 0 | 0 | 2012/06/22 | 2012/07/25 |  |  | 2012/06/22 | 2012/06/22 | Kent Pylant | [7 empty] | True |  | SO8751 | GRC-06-3190-12
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/10/10 | 2012/10/10 | Philip Haskings | [7 empty] | True |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/10/31 |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/11/30 |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 100 | 1500 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  | 2012/12/07 | 2013/05/01 | Philip Haskings | [7 empty] | True |  | 9022 | 90000577315 |  | True
Agilent - SO9022 NGX Card Install (Colorado Springs) |  | Project Closure |  | 1500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/10 | 2012/09/28 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9022 | 90000577315 |  | True
APAC - SO9058 Remote Dialogic Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
APAC - SO9058 Remote Dialogic Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/11/09 | 2013/01/25 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/09/30 | 2012/09/30 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
JEA - SO8978 NMS Config |  | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/06 | 2012/08/31 |  |  | 2012/11/08 | 2012/10/10 | Philip Haskings | [7 empty] | True |  | 8978 | 122555
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/10/09 | 2012/10/09 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/10/11 | 2012/10/11 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2012/11/16 | 2013/07/16 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Vanguard - SO8748 Direct Hardware Configuration |  | Project Closure |  | 1400 | 0 | Philip Haskings | 100 | 1400 | 0 | 0 | 2012/06/11 | 2013/12/31 |  |  | 2013/12/31 | 2013/07/16 | Philip Haskings | [7 empty] | True | Michelle Robinson | 8748 | 01000-000174222 | 2012/06/08 | False
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2012/10/24 | 2012/10/24 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2012/11/09 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 100 | 77385 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2013/09/06 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Verizon Wireless - SO8905 - OnSite Host Card replacement **26 sites** |  | Project Closure | Hardware Install / Config | 77385 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/07/16 | 2013/12/31 |  |  | 2013/05/02 | 2013/09/06 | Philip Haskings | [7 empty] | True |  | 8905 | GPUR169135 | 2013/01/01 | True | 2013/09/06
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/06 | 2012/09/07 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/04 | 2012/09/04 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/08/09 | 2012/08/09 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Affiliated Computer Services - SO8353 NGX Cards and Server | ACS - SO8353 | Project Closure |  | 4700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/08/16 | 2012/08/24 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
CDW - State Auto - SO8846 Training Credits (No Services) | State Auto - SO8846 | 7 - Training |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/05 | 2012/07/27 |  |  | 2012/09/10 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | 8846 | JLQ7504
HSBC - SO8623 Verona Data Split |  | Project Closure |  | 18800 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/09/11 | 2012/09/28 |  |  | 2012/07/31 | 2012/07/31 | Kent Pylant | [7 empty] | True |  | 8623 | PEET 8367 |  | True
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 100 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/10 | 2012/08/17 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/31 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/07/10 | 2012/07/10 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
State of Texas - SO8803 - v7.8 Server Move | TX TRS - SO8803 | Project Closure |  | 0 | 0 | John Randall | 0 | 0 | 0 | 0 | 2012/06/22 | 2012/08/17 |  |  | 2012/08/02 | 2012/08/03 | Kent Pylant | [7 empty] | True |  | SO8803 | S200613
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/15/12 - 10/19/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Cocal Cola - SO1201569 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Product Installation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Product Integration | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Training | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
First Niagara Bank - SO1181658 10/15/12 - 10/19/12 Remote - Prisca W | Project Closure | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181658
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
World Travel - SO1198713 10/15/12 - 10/19/12 Remote - Robb D | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198173
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/15/12 - 10/16/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/15 | 2012/10/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Johns Hopkins Physics Lab - SO61120 10/17/12 - 10/17/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/17 | 2012/10/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 61120
Unused Resource - SO99999 10/18/12 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/18/12 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/18 | 2012/10/18 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Ally Financial - SO65577 10/19/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/19/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/19 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 | 2012/12/04 | 2012/12/05 | 2012/12/04 | 2012/12/05 | Philip Haskings | [7 empty] | True |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/31 | 2012/11/09 | 2012/12/05 | 2012/12/10 | 2012/12/06 | 2012/12/19 | Philip Haskings | [7 empty] | True |  | 9442 | JWW6380
CDW - Brady Corp. - SO9442 Additional Seat Licenses - Remote | Brady | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/09 |  |  |  |  | Philip Haskings | [7 empty] | False |  | 9442 | JWW6380
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2013/07/01 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  | 2013/02/28 | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
ACS Technologies - Xerox - Hamilton, NJ - SO9447 NGX Card Remote | ACS SO9447 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9447 | AC176269 | 2012/11/05 | True | 2013/07/16
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
CSC Holdings - SO1181602 10/22/12- 10/26/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181602
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/22/12 - 10/25/12 Remote - Prisca W | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Project Kick Off | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Planning & Design | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Hardware / Software Procurement | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Readiness Validation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Product Installation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Product Integration | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Training | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Consulting & Technical Reviews | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Support Turnover | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/16/12 - 10/19/12 WFM Training - Mary W | Project Closure | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/10/19 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Project Kick Off | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Planning & Design | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Hardware / Software Procurement | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Readiness Validation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Product Installation | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Product Integration | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Training | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Consulting & Technical Reviews | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Support Turnover | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
State of Utah - SO67451 10/22/12 - 10/25/12 WFM Training - Mary W | Project Closure | 7 - Training |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67451
Ally Financial - SO65577 10/22/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 10/22/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/22 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Auto Protection - SO1205178 10/25/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/25 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1205178
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused resource - SO99999 10/23/12 - 10/24/12 Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/23 | 2012/10/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 10/26/12 Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/26 | 2012/10/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Alorica - SO1202039FOC - 10/22/12 - 10/25/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202039FOC
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
Allstate - SO1181083 10/22/12 - 10/25/12 Remote - Robb D | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/10/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181083
HSBC - SO9454 - PM October - Matt Hogan | Project Kick Off | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Planning & Design | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Readiness Validation | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Product Installation | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Product Integration | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Training | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Support Turnover | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9454 | PEET 7511
HSBC - SO9454 - PM October - Matt Hogan | Project Closure | Project Closure |  | 20160 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  | 2012/10/31 | Kent Pylant | [7 empty] | True | Todd Folkes | 9454 | PEET 7511
HSBC - SO9455 October Admin | Project Kick Off | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Planning & Design | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Hardware / Software Procurement | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Readiness Validation | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Product Installation | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Product Integration | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Training | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Consulting & Technical Reviews | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Support Turnover | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9455 | PEET 7154
HSBC - SO9455 October Admin | Project Closure | Project Closure |  | 25024 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/31 |  |  | 2012/10/31 | 2012/10/31 | Kent Pylant | [7 empty] | True | Todd Folkes | 9455 | PEET 7154
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Project Kick Off | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Planning & Design | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Hardware / Software Procurement | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Readiness Validation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Product Installation | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Product Integration | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Training | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Consulting & Technical Reviews | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Support Turnover | Project Closure |  | 3295 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
MolDev - Cross Cancer Research - SO9470 HCS Solution - Fred J | Project Closure | Project Closure |  | 3295 | 0 | Philip Haskings | 100 | 3295 | 0 | 0 | 2012/11/07 | 2012/12/28 |  |  |  | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9470 | 41102206 | 2012/07/11
Baptist Hospital - SO9500 Remote Config | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/11/30 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/04 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/11 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2012/12/04 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
Baptist Hospital - SO9500 Remote Config | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/14 | 2012/11/30 |  |  |  | 2013/01/09 | Philip Haskings | [7 empty] | True |  | 9500 | 1191057
BBVA Compass Bank - SO9502 Global Monitor Trial | Project Kick Off | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/01/09 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Planning & Design | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Hardware / Software Procurement | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Readiness Validation | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Product Installation | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Product Integration | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/02/28 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Consulting & Technical Reviews | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9502 Global Monitor Trial | Project Closure | Project Closure | Hardware Install / Config | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2013/10/31 |  |  |  | 2013/09/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9502 | FOC | 2013/01/01 | True | 2013/09/05
BBVA Compass Bank - SO9515 SIP Trunk Change | Project Kick Off | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2012/11/29 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Planning & Design | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/01/03 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Consulting & Technical Reviews | Project Closure |  | 2150 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/03/05 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
BBVA Compass Bank - SO9515 SIP Trunk Change | Project Closure | Project Closure |  | 2150 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/11/15 | 2012/11/30 |  |  |  | 2013/03/27 | Philip Haskings | [7 empty] | True | Susan Tibbs | 9515 | 97931
CDW - Brady Corp - SO9518 Remote License Addition | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
CDW - Brady Corp - SO9518 Remote License Addition | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/11/19 | 2012/12/07 |  |  |  | 2012/12/10 | Philip Haskings | [7 empty] | True |  | 9518 | JYD7931
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Project Kick Off | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  | 2012/11/26 | 2012/11/27 | Kent Pylant | [7 empty] | True |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Planning & Design | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Hardware / Software Procurement | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Readiness Validation | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Product Installation | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Product Integration | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Training | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Consulting & Technical Reviews | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  | 2012/12/03 | 2012/12/21 | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Support Turnover | Project Closure |  | 40000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9528 | Lary Burke
LexisNexis - Reed ElSevier - SO9528 WFM Consulting (Mary Weiss) | Project Closure | Project Closure |  | 40000 | 0 | Kent Pylant | 100 | 40000 | 0 | 0 | 2012/11/26 | 2013/01/31 |  |  |  | 2013/01/29 | Kent Pylant | [7 empty] | True |  | 9528 | Lary Burke
Greater Toronto Airport Authority - SO9545 Card Install | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/01/26 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2012/11/26 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2012/12/03 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Readiness Validation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Product Integration | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Training | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Consulting & Technical Reviews | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Support Turnover | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/03/13 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Greater Toronto Airport Authority - SO9545 Card Install | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2012/11/26 | 2012/12/28 |  |  |  | 2013/04/04 | Philip Haskings | [7 empty] | True |  | 9545 | 2036299 |  | True
Pearson Education - SO9553 Voice Card Consolidation | Project Kick Off | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/03 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Planning & Design | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Hardware / Software Procurement | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Readiness Validation | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/06 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Product Installation | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/08 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Product Integration | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/08 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Training | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Consulting & Technical Reviews | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Support Turnover | Project Closure |  | 2000 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
Pearson Education - SO9553 Voice Card Consolidation | Project Closure | Project Closure |  | 2000 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/11/28 | 2012/12/07 |  |  |  | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9553 | 3112012 | 2012/11/28
HSBC - SO9601 - November PM - Matt Hogan | Project Kick Off | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Planning & Design | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Readiness Validation | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Product Installation | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Product Integration | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Training | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Support Turnover | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9601 - November PM - Matt Hogan | Project Closure | Project Closure |  | 12480 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9601 | PEET 7511
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Project Kick Off | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Planning & Design | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Hardware / Software Procurement | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Readiness Validation | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Product Installation | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Product Integration | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Training | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Consulting & Technical Reviews | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Support Turnover | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
HSBC - SO9602 11/01/12 - 11/30/12 - November Admin | Project Closure | Project Closure |  | 19176 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/01 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9602 | PEET 7154
Medtronic - SO1198187 10/29/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1198187
Medtronic - SO1198187 10/29/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 100 | 700 | 0 | 0 | 2012/10/29 | 2012/10/29 |  |  | 2012/10/29 | 2012/10/29 | Kent Pylant | [7 empty] | True | Tim Prince |  | 1198187
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Atos - SO1187660 10/30/12 - 11/01/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/30 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187660
Medtronic - SO1197187 11/02/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/02/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/02 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 - 10/29/12 - 11/02/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Patterson Dental - SO1190476 10/29/12 - 11/02/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190476
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 10/29/12 - 11/02/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/29 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 10/31/12 - 11/01/12 Remote - Prisca W | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/31 | 2012/11/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/05/12 - 11/09/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Commonwealth Financial - SO1191821 11/08/12 - 11/09/12 Remote - Robb D | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/08 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191821
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Project Kick Off | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Planning & Design | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Readiness Validation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Product Installation | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Product Integration | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Training | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Support Turnover | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Quest - SO1204845 11/05/12 - 11/09/12 Remote - Robb D | Project Closure | Project Closure |  | 3150 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204845
Medtronic - SO1197187 11/05/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Medtronic - SO1197187 11/05/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197187
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/06/12 - 11/09/12 Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/06 | 2012/11/09 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Excellerx - SO1202599 11/05/12 - 11/06/12 Remote - Prisca W | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/05 | 2012/11/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1202599
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/12/12 - 11/16/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 11/14/12 - 11/16/12 Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/14 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Skyhawke - SO1208101 11/12/12 - 11/13/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/12 | 2012/11/13 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1208101
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman-Marcus - SO1189207 11/16/12 Remote - Robb D | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/16 | 2012/11/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/19/12 - 11/21/12 Remote - Aziz H | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/19/12 - 11/21/12 Michael T | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 - 11/19/21 - 11/21/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/19 | 2012/11/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
HSBC - SO9619 v11 TDM Upgrades | Project Kick Off | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  | 2013/01/08 | 2013/02/05 | Philip Haskings | [7 empty] | True | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Planning & Design | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Hardware / Software Procurement | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Readiness Validation | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Product Installation | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Product Integration | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Training | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Consulting & Technical Reviews | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Support Turnover | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades | Project Closure | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 100 | 36000 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  | 2014/07/31 |  | John Randall | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
HSBC - SO9619 v11 TDM Upgrades |  | 1 - Project Kick Off | Hardware Install / Config | 36000 | 0 | John Randall | 0 | 0 | 0 | 0 | 2013/10/01 | 2014/08/29 |  |  |  |  | Kent Pylant | [7 empty] | False | Chad Curnutt | 9619 | PEET 9303 | 2013/01/01 | False
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Planning & Design | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Product Installation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Product Integration | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Training | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Support Turnover | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 11/26/12 - 11/30/12 Remote - Aziz H | Project Closure | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Sedgewick Claims Management - SO1204605 11/27/12 Remote - Aziz H | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/27 | 2012/11/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1204605
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
Northern Trust - SO1200263 11/26/12 - 11/30/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200263
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
City and County of Denver -Denver 911 - SO1200282 11/26/12 - 11/30/12 Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200282
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 11/26/12 - 11/30/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
Marchond Eyewear - SO1190348 11/26/12 - 11/30/12 Remote - Robb D | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/11/26 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190348
APAC - SO9641 Dialogic Card Install - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/12 |  | 2012/12/28 | 2012/12/20 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2012/12/20 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/02 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
APAC - SO9641 Dialogic Card Install - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/25 | Philip Haskings | [7 empty] | True |  | 9641 | 67896
HSBC - SO8991 Onshore/Offshore Screen Recorder Services |  | 1 - Project Kick Off |  | 0 | 0 | Scott Montgomery | 100 | 0 | 0 | 0 | 2012/08/03 | 2012/09/28 | 2012/12/03 | 2012/12/05 | 2012/12/03 | 2012/12/06 | Kent Pylant | [7 empty] | True | Todd Folkes | 8991 | PEET 9183
VistaCom - SO9654 - License Upgrade - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/11 |  | 2012/12/12 | 2013/01/04 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/11 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/14 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/14 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 | 2012/12/20 |  | 2012/12/21 | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
VistaCom - SO9654 - License Upgrade - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/10 | 2012/12/28 |  |  |  | 2013/01/17 | Philip Haskings | [7 empty] | True |  | 9654 | 10340
CDW - AFNI SO9677 Global Monitor Planning & Design | Project Kick Off | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Planning & Design | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Hardware / Software Procurement | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Readiness Validation | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Product Installation | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Product Integration | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Training | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Consulting & Technical Reviews | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Support Turnover | Project Closure |  | 6400 | 0 | Tim Johnson | 0 | 0 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Matt Brush | 9677 | 00003-0000013737 |  | True
CDW - AFNI SO9677 Global Monitor Planning & Design | Project Closure | Project Closure |  | 6400 | 0 | Tim Johnson | 100 | 6400 | 0 | 0 | 2012/12/10 | 2012/12/14 |  |  |  | 2013/05/01 | Kent Pylant | [7 empty] | True | Matt Brush | 9677 | 00003-0000013737 |  | True
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/01/16 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
APAC (Davenport) - SO9690 Dialogic Card Install - Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/12/13 | 2013/01/25 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9690 | APAC-DAV-67977
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
Agilent Technologies - SO1190128 12/03/12 - 12/07/12 Remote - Aziz H | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190128
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
HSBC - SO1200238 12/03/12 - 12/07/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1200238
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Neiman Marcus - SO1189207 12/04/12 - 12/06/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189207
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Coca Cola - SO1201569 12/03/12 - 12/06/12 Remote - Robb D | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1201569
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Planning & Design | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Product Installation | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Product Integration | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Training | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Support Turnover | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Enmax - SO1192215 12/03/12 - 12/06/12 Remote - Fred J | Project Closure | Project Closure |  | 1050 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/03 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1192215
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Service Master - SO1209343 12/04/12 - 12/06/12 Remote - Fred J | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/04 | 2012/12/06 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209343
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Project Kick Off | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Planning & Design | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Readiness Validation | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Product Installation | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Product Integration | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Training | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Support Turnover | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
Southern Maryland Electric Co. - SO1209220 12/06/12 - 12/07/12 Remote - Fred J | Project Closure | Project Closure |  | 875 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/12/06 | 2012/12/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1209220
TOS - Region of Waterloo - SO9735 V11 WFO | Project Kick Off | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/02/28 | 2013/02/28 | 2013/02/28 | 2013/02/28 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Planning & Design | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/03/04 | 2013/03/04 | 2013/03/22 | 2013/03/22 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Hardware / Software Procurement | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/02/25 | 2013/02/25 | 2013/02/28 | 2013/02/28 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Readiness Validation | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/04/08 | 2013/04/09 | 2013/04/10 | 2013/04/10 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Product Installation | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/05/20 | 2013/05/20 | 2013/05/31 | 2013/05/31 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Product Integration | Project Closure |  | 63700 | 0 | Stewart Futcher | 90 | 57330 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/05/20 | 2013/05/20 | 2013/05/31 | 2013/05/31 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Training | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/06/17 | 2013/06/17 | 2013/07/05 | 2013/07/05 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Consulting & Technical Reviews | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/07/01 | 2013/07/01 | 2013/07/12 | 2013/07/12 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Support Turnover | Project Closure |  | 63700 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/08/26 | 2013/09/18 | 2013/08/26 | 2013/09/18 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
TOS - Region of Waterloo - SO9735 V11 WFO | Project Closure | Project Closure |  | 63700 | 0 | Stewart Futcher | 10 | 6370 | 0 | 0 | 2012/12/27 | 2013/12/20 | 2013/08/30 |  | 2014/01/31 | 2014/02/03 | Stewart Futcher | [7 empty] | True | Jim Foster | 9735 | JMF-07122012-310 | 2013/01/14 | True | 2013/06/27
Seimens _ Medstar SO9740 QM Supervisor Training | Project Kick Off | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Planning & Design | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Hardware / Software Procurement | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Readiness Validation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Product Installation | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Product Integration | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Training | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Consulting & Technical Reviews | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Support Turnover | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
Seimens _ Medstar SO9740 QM Supervisor Training | Project Closure | Project Closure |  | 1800 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/12/28 | 2013/01/25 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9740 | 7700237041
CDW - Vectren Energy SO10032 Op QM | Project Kick Off | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/01/10 | 2013/01/10 | 2013/01/18 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Planning & Design | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/03/11 | 2013/03/11 | 2013/03/29 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Hardware / Software Procurement | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/04/15 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Readiness Validation | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/29 | 2013/05/01 | 2013/04/29 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Product Installation | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/05/03 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Product Integration | Project Closure |  | 11815 | 0 | Stewart Futcher | 100 | 11815 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/04/15 | 2013/04/15 | 2013/05/31 | 2013/05/29 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Training | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/09/12 |  | 2013/09/13 |  | Stewart Futcher | [7 empty] | False |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Consulting & Technical Reviews | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/05/20 | 2013/05/20 | 2013/05/24 | 2013/05/30 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Support Turnover | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/08/26 | 2013/09/27 | 2013/08/26 | 2013/09/27 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
CDW - Vectren Energy SO10032 Op QM | Project Closure | Project Closure |  | 11815 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/03/18 | 2013/03/22 | 2013/09/06 | 2013/09/24 | 2013/09/06 | 2013/09/24 | Stewart Futcher | [7 empty] | True |  | 10032 | 00003-0000014467 | 2013/04/22 | True | 2013/05/29
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Project Kick Off | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Planning & Design | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Hardware / Software Procurement | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Readiness Validation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Product Installation | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Product Integration | Project Closure |  | 1575 | 0 | Kent Pylant | 100 | 1575 | 0 | 0 | 2013/01/07 | 2013/01/28 | 2013/01/08 | 2013/01/08 | 2013/01/08 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Training | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Consulting & Technical Reviews | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  | 2013/01/10 | 2013/01/15 | 2013/01/15 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Support Turnover | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9770 | NCI - 0000236122
Black Box - Genentech - SO9770 - CTI Conversion to Vox - Bobby D | Project Closure | Project Closure |  | 1575 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/28 | 2013/01/25 | 2013/01/28 | 2013/01/25 | 2013/01/28 | Kent Pylant | [7 empty] | True |  | 9770 | NCI - 0000236122
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2013/01/07 | 2013/01/31 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9772 | 7700237080 |  | True | 2013/05/23
Siemens - Watson Clinic - SO9772 Add Licensing - Remote | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2013/01/07 | 2013/01/31 | 2013/03/04 | 2013/05/17 | 2013/03/29 | 2013/05/17 | Stewart Futcher | [7 empty] | True |  | 9772 | 7700237080 |  | True | 2013/05/23
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Norfolk Southern - SO1196550 10/08/12 - 10/12/12 Remote - P White | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1196550
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Project Kick Off | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Planning & Design | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Hardware / Software Procurement | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Readiness Validation | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Product Installation | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Product Integration | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Training | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Consulting & Technical Reviews | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Support Turnover | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
Discover Financial Services - SO1172115 10/08/12 - 10/12/12 Michael T | Project Closure | 6 - Product Integration |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/12 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172115
FabriCut, Inc. - SO9367 v11 Install | Project Kick Off | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2012/11/27 | 2012/10/29 | 2012/11/27 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Planning & Design | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2012/11/27 | 2012/11/27 | 2013/01/22 | 2013/03/12 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Hardware / Software Procurement | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2012/11/27 | 2013/01/15 | 2013/01/22 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Readiness Validation | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/01/15 | 2013/01/22 | 2013/01/17 | 2013/01/23 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Product Installation | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/02/18 | 2013/03/14 | 2013/02/28 | 2013/03/18 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Product Integration | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 100 | 16800 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/02/19 | 2013/03/12 | 2013/02/25 | 2013/03/22 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Training | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/04/02 | 2013/04/01 | 2013/04/05 | 2013/04/19 | Kent Pylant | [7 empty] | True | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Consulting & Technical Reviews | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2013/03/29 | 2013/02/22 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Support Turnover | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 | 2013/04/23 |  | 2013/04/23 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
FabriCut, Inc. - SO9367 v11 Install | Project Closure | 8 - Consulting & Technical Reviews |  | 16800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/16 | 2012/12/28 |  | 2013/04/30 | 2013/03/07 |  | Kent Pylant | [7 empty] | False | Ben Novak | 9367 | NCI-0000232729 | 2012/10/16 | True
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Project Kick Off | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Planning & Design | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Hardware / Software Procurement | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Readiness Validation | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Product Installation | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Product Integration | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Training | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Consulting & Technical Reviews | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Support Turnover | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
HSBC - SO9290 September Admin Resource 09/01/12 - 09/30/12 | Project Closure | Project Closure |  | 20672 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9290 | PEET 7154
Verizon - SO9291 Hardware Upgrade | Project Kick Off | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Planning & Design | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Hardware / Software Procurement | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Readiness Validation | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Product Installation | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/10 | 2012/10/10 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Product Integration | Project Closure |  | 2400 | 0 | Philip Haskings | 100 | 2400 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/12 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Training | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Consulting & Technical Reviews | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Support Turnover | Project Closure |  | 2400 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/11 | 2012/10/11 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
Verizon - SO9291 Hardware Upgrade | Project Closure | Project Closure |  | 2400 | 0 | Philip Haskings | 100 | 2400 | 0 | 0 | 2012/09/28 | 2012/10/26 |  |  | 2012/10/12 | 2012/10/16 | Kent Pylant | [7 empty] | True |  | 9291 | Pending
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Project Kick Off | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/06 | 2012/09/07 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Planning & Design | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Readiness Validation | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Product Installation | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Product Integration | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/27 | 2012/09/27 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Training | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  | 2012/09/27 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Support Turnover | Project Closure |  | 3125 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9090 | PO_IXM0829204
MolDev - MD Anderson Cancer Center - SO 9090 - 09/27/12 - Fred J | Project Closure | Project Closure |  | 3125 | 0 | Kent Pylant | 100 | 3125 | 0 | 0 | 2012/09/27 | 2012/09/27 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 9090 | PO_IXM0829204
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/24/12 - 09/28/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Gexel Telecom - SO64173 09/24/12 - 09/25/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/24 | 2012/09/25 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 64173
Covidien - SO1203233 09/26/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
Covidien - SO1203233 09/26/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/26 | 2012/09/26 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1203233
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Project Kick Off | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Planning & Design | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Hardware / Software Procurement | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Readiness Validation | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Product Installation | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Product Integration | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Training | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Consulting & Technical Reviews | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Support Turnover | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
HSBC - SO9296 09/01/12 - 09/30/12 Remote PM - Matt Hogan | Project Closure | Project Closure |  | 18240 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/01 | 2012/09/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9296 | PEET 7511
Knology - SO9038 Trunk Tap Remote | COS signed | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 500 | 0 | 0 | 2012/08/15 | 2012/09/14 |  |  | 2012/09/21 | 2012/09/25 | Kent Pylant | [7 empty] | True |  | 9038 | 414-126621
TBL Networks - VA Department of Taxation SO8518 WFO | Installation | Project Closure |  | 66889 | 0 | Stewart Futcher | 100 | 66889 | 0 | 0 | 2012/04/30 | 2012/10/10 | 2013/02/04 | 2013/02/04 | 2013/02/15 | 2013/02/22 | Kent Pylant | [7 empty] | True |  | 8518 | 2475 | 2012/09/21 | True
APAC - SO9058 Remote Dialogic Config | APAC - SO9058 | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/02 | 2012/10/07 | Kent Pylant | [7 empty] | True |  | 9058 | APAC-TUCE-66902
APAC - SO9058 Remote Dialogic Config | APAC - SO9058 | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/08/22 | 2012/09/14 |  |  | 2012/10/05 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9058 | APAC-TUCE-66902
TBL Networks - VA Department of Taxation SO8518 WFO | VA Dept of Tax - SO8518 | Project Closure |  | 66889 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/10/10 | 2013/01/25 | 2013/01/25 | 2013/01/28 | 2013/01/28 | Stewart Futcher | [7 empty] | True |  | 8518 | 2475 | 2012/09/21 | True
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/31 | 2012/08/31 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/02 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 100 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/05 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite | Worldcom - BCBS MA | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  | 2012/10/05 | 2012/10/05 | Philip Haskings | [7 empty] | True |  |  | 18562
Worldcom Exchange - SO8757 Trunk Tap Onsite |  | Project Closure |  | 0 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/06/13 | 2012/07/27 |  |  |  | 2012/10/04 | Philip Haskings | [7 empty] | True |  |  | 18562
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Windows Fashions - SO1177224 10/01/12 - 10/05/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Bose - SO1197934 10/01/12 - 10/05/12 Remote - Prisca W | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197934
Siemens - H E B Grocery SO9320 Op QM Install | Project Kick Off | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/16 | 2012/11/16 | 2012/11/16 | 2013/01/08 | Stewart Futcher | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Planning & Design | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/10 | 2012/12/10 | 2013/01/04 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Hardware / Software Procurement | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/10 | 2012/12/10 | 2013/01/02 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Readiness Validation | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/08 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Product Installation | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  | 2012/12/10 | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Product Integration | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  | 2012/12/21 | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Training | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Consulting & Technical Reviews | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Support Turnover | Project Closure |  | 19200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 |  |  |  | 2013/05/29 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
Siemens - H E B Grocery SO9320 Op QM Install | Project Closure | Project Closure |  | 19200 | 0 | Stewart Futcher | 100 | 19200 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/28 | 2013/01/28 | 2013/03/08 | 2013/03/22 | Kent Pylant | [7 empty] | True |  | 9320 | 7700234927 |  | True
CDW - Federal Mogul - SO8940 Planning & Design | Federal Mogul - SO8940 | Project Closure |  | 10000 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/08/31 |  |  | 2012/08/24 | 2012/08/24 | Stewart Futcher | [7 empty] | True |  | 8940 | 00003-0000012158
CDW - TMG - SO8721 WFO Consulting |  | Project Closure |  | 7550 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/06/07 | 2012/07/06 |  |  |  |  | Stewart Futcher | [7 empty] | False |  |  | 00003-0000011680
CDW - TMG - SO8721 WFO Consulting | CDW - TMG SO8721 | Project Closure |  | 7550 | 0 | Stewart Futcher | 100 | 7550 | 0 | 0 | 2012/06/07 | 2012/07/06 |  |  | 2012/07/13 | 2012/07/31 | Stewart Futcher | [7 empty] | True |  |  | 00003-0000011680
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Planning & Design | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/12/03 | 2012/12/04 | 2013/01/07 | 2013/01/11 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Hardware / Software Procurement | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/26 | 2012/11/26 | 2013/01/04 | 2013/01/07 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Readiness Validation | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/01/02 | 2013/01/02 | 2013/01/04 | 2013/01/04 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Product Installation | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/02/18 | 2013/02/18 | 2013/02/18 | 2013/03/01 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Product Integration | Project Closure |  | 19100 | 0 | Stewart Futcher | 100 | 19100 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/02/18 | 2013/02/18 | 2013/02/18 | 2013/03/01 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Training | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/03/04 | 2013/03/04 | 2013/03/04 | 2013/03/08 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Consulting & Technical Reviews | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/03/11 | 2013/03/11 | 2013/03/22 | 2013/03/22 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Support Turnover | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/09/26 | 2013/09/26 | 2013/09/26 | 2013/09/26 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Project Closure | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2013/08/26 | 2013/09/26 | 2013/08/30 | 2013/09/26 | Kent Pylant | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Siemens - Utah Retirement Systems SO9292 Upgrade to v11 | Utah Retirement Systems - SO9292 | Project Closure |  | 19100 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/05 | 2012/12/28 | 2012/11/15 | 2012/11/15 | 2012/11/15 | 2012/11/15 | Stewart Futcher | [7 empty] | True |  | 9292 | 7700233949 | 2012/12/17 | True | 2013/01/30
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Project Kick Off | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Planning & Design | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/10/07 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/08 | 2012/10/07 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Readiness Validation | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/15 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Product Installation | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/19 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Product Integration | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/19 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Training | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/20 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/21 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Support Turnover | Project Closure |  | 2800 | 0 | Philip Haskings | 100 | 2800 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/21 | 2012/12/27 | Philip Haskings | [7 empty] | True |  | 9325 | 002 2012
Mol Dev - Universitaet Tuebingen - SO9325 Server & Switch (Germany) | Project Closure | Project Closure |  | 2800 | 0 | Philip Haskings | 100 | 2800 | 0 | 0 | 2012/10/08 | 2012/11/23 |  |  | 2012/11/23 | 2012/12/27 | Kent Pylant | [7 empty] | True |  | 9325 | 002 2012
Siemens - Peoples Natural Gas SO9328 License Update Remote | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/08 | Philip Haskings | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Readiness Validation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/18 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  | 2012/10/12 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Training | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
Siemens - Peoples Natural Gas SO9328 License Update Remote | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/08 | 2012/10/31 |  |  |  | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9328 | 7700234981 | 2012/08/10
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/09/28 | 2012/09/14 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 100 | 36775 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/09/28 | 2012/10/25 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 100 | 36775 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/10/26 | 2012/10/22 | Kent Pylant | [7 empty] | True |  | 9016 | 00003-0000012388
CDW - TMG - SO9016 v11 Install | CDW - TMG SO9016 | Project Closure |  | 36775 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/24 |  |  | 2012/11/09 |  | Stewart Futcher | [7 empty] | False |  | 9016 | 00003-0000012388
CDW - Allianz SO9330 Telephone Playback Server | Project Kick Off | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Planning & Design | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Hardware / Software Procurement | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Readiness Validation | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Product Installation | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  | 2012/11/14 |  | 2012/11/15 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Product Integration | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Training | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Consulting & Technical Reviews | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  | 2012/11/30 |  | 2013/01/21 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Support Turnover | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9330 | 00003-0000012983
CDW - Allianz SO9330 Telephone Playback Server | Project Closure | Project Closure |  | 8000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/09 | 2012/11/30 | 2012/11/20 | 2013/01/15 | 2012/11/27 | 2013/01/28 | Kent Pylant | [7 empty] | True |  | 9330 | 00003-0000012983
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 - 10/01/12 - 10/05/12 Fred Jurs | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/10/01 | 2012/10/05 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Siemens - Medstar - SO9280 3rd site Op QM | Project Kick Off | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Planning & Design | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Readiness Validation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Product Installation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Product Integration | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Training | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Support Turnover | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/09 | 2013/01/25 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9280 | 7700234792 |  | True
Siemens - Medstar - SO9280 3rd site Op QM | Project Closure | Project Closure |  | 3200 | 0 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2012/10/09 | 2013/01/25 | 2012/11/05 | 2012/11/05 | 2012/11/16 | 2012/11/16 | Kent Pylant | [7 empty] | True |  | 9280 | 7700234792 |  | True
CDW - TMG Health - SO9372 Additional Training | Project Kick Off | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Planning & Design | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Hardware / Software Procurement | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Readiness Validation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Product Installation | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Product Integration | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Training | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Consulting & Technical Reviews | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Support Turnover | Project Closure |  | 0 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9372 | Adtech
CDW - TMG Health - SO9372 Additional Training | Project Closure | Project Closure |  | 0 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/10/22 | 2012/11/02 | 2012/10/22 | 2012/10/19 | 2012/10/19 | 2012/10/19 | Kent Pylant | [7 empty] | True |  | 9372 | Adtech
CDW - State Auto Insurance - SO8515 |  | Project Closure |  | 26000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/04/30 | 2012/09/21 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | False |  | 8515 | 00003-0000011329
Ronco Communications - SO9092 Remote NGX Configuration | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  |  | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2012/10/22 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Product Installation | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/01/31 | 2013/07/05 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Ronco Communications - SO9092 Remote NGX Configuration | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2012/10/11 | 2013/01/31 |  |  | 2013/02/08 | 2013/07/08 | Philip Haskings | [7 empty] | True |  | 9092 | TSDN324312AAGS | 2012/08/29 | True | 2013/07/08
Presidio - Lab Corp - SO8874 Remote Support | Lab Corp | Project Closure |  | 3500 | 0 | Stewart Futcher | 100 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/08/31 | 2012/09/21 | Kent Pylant | [7 empty] | True |  | 8874 | 36207989-01
Presidio - Lab Corp - SO8874 Remote Support |  | Project Closure |  | 3500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/09/28 | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 8874 | 36207989-01
Presidio - Lab Corp - SO8874 Remote Support | Lab Corp - SO8874 | Project Closure |  | 3500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/07/23 | 2012/09/28 |  |  | 2012/08/31 | 2012/08/31 | Stewart Futcher | [7 empty] | False |  | 8874 | 36207989-01
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Project Kick Off | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  | 2012/08/31 |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Planning & Design | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Hardware / Software Procurement | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Readiness Validation | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Product Installation | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Product Integration | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Training | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Consulting & Technical Reviews | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Support Turnover | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
2 Wire - SO1182386 - 02/27/12 -02/28/12 Remote - Bobby D | Project Closure | 2 - Planning & Design |  | 1000 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/02/27 | 2012/02/28 |  |  |  |  | Matt Pearson | [7 empty] | False | Tim Prince |  | 1182386
HSBC - SO9101 - August PM Resource - M Hogan | Project Kick Off | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Planning & Design | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Hardware / Software Procurement | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Readiness Validation | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Product Installation | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Product Integration | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Training | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Consulting & Technical Reviews | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Support Turnover | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9101 - August PM Resource - M Hogan | Project Closure | Project Closure |  | 22080 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9101 | Peet 7511
HSBC - SO9100 - August Admin Support Resources | Project Kick Off | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Planning & Design | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Hardware / Software Procurement | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Readiness Validation | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Product Installation | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Product Integration | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Training | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Consulting & Technical Reviews | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Support Turnover | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
HSBC - SO9100 - August Admin Support Resources | Project Closure | Project Closure |  | 20604 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Todd Folkes | 9100 | PEET 7154
Ericsson, Inc. - SO9111 Level 3 Support | Project Kick Off | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Planning & Design | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Readiness Validation | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Product Installation | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Product Integration | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Training | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Support Turnover | Project Closure |  | 3200 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/30 | 2012/09/30 | Kent Pylant | [7 empty] | True |  | 9111 | 4506966796
Ericsson, Inc. - SO9111 Level 3 Support | Project Closure | Project Closure |  | 3200 | 0 | Philip Haskings | 100 | 3200 | 0 | 0 | 2012/09/05 | 2012/09/28 |  |  | 2012/09/28 | 2012/09/28 | Philip Haskings | [7 empty] | True |  | 9111 | 4506966796
R J Reynolds - SO9109 - v11 Compliance | Project Kick Off | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/09/06 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Planning & Design | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Hardware / Software Procurement | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/09/12 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Readiness Validation | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Product Installation | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Product Integration | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  | 2012/10/02 |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Training | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Consulting & Technical Reviews | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Support Turnover | Project Closure |  | 12300 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/05 | 2012/12/21 |  |  |  |  | Stewart Futcher | [7 empty] | False |  | 9109 | 4534690692
R J Reynolds - SO9109 - v11 Compliance | Project Closure | Project Closure |  | 12300 | 0 | Stewart Futcher | 100 | 12300 | 0 | 0 | 2012/09/05 | 2012/12/21 | 2012/12/03 | 2012/12/03 | 2012/12/07 | 2012/12/07 | Stewart Futcher | [7 empty] | True |  | 9109 | 4534690692
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Progrexion Marketing - SO1189292 07/30/12 C McGuire - Remote | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/07/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1189292
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Project Kick Off | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Planning & Design | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Readiness Validation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Product Installation | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Product Integration | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Training | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Support Turnover | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Money Services - SO1174447 07/31 - 08/02/12 - 2.5 days Remote - Chris M | Project Closure | Project Closure |  | 1750 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/31 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/02/12 - .5 Days Remote - Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/02 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
Josten's - SO1191672 08/01/12 - .5 Days Remote - Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/01 | 2012/08/01 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1191672
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Project Kick Off | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Planning & Design | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Hardware / Software Procurement | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Readiness Validation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Product Installation | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Product Integration | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Training | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Support Turnover | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
TD Bank N.A. - SO1187532 - 08/01/12 .5 Days Remote Chris M | Project Closure | Project Closure |  | 350 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1187532
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
F5 Networks - SO1195134 - 07/30/12 0 08/02/12 Remote Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
Unused Resource - SO99999 08/03/12 Fred Jurs | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/03/12 Fred Jurs | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/03 | 2012/08/03 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Alabama Gas - SO1184566 07/30/12 - 08/03/12 Remote - Michael Taylor | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/07/30 | 2012/08/02 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater - SO1190084 - 08/07 - 08/10/12 Remote - Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/07 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
AGL Resources - SO67066 WWO 08/06/12 - 08/08/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/08 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67066 WWO
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/09/12 - 08/10/12 Fred Jurs | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/09 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
Aegon Money Services - SO1174447 08/06/12 - 08/10/12 Remote Chris M | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/06 | 2012/08/10 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1174447
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
D & H Partnership - SO1199305 08/13/12 - 08/17/12 - Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199305
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Wellmark - SO1172903 08/13/12 - 08/17/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/17 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1172903
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Capital One - SO65707 08/13/12 - 08/15/12 Remote Chris M | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/13 | 2012/08/15 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65707
Unused Resource - SO99999 08/16/12 Chris McGuire | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/16/12 Chris McGuire | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/16 | 2012/08/16 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Project Kick Off | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Planning & Design | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Readiness Validation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Product Installation | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Product Integration | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Training | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Support Turnover | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Wyndham Partners - SO1199774 08/22/12 - 08/23/12 Remote - Fred J | Project Closure | Project Closure |  | 1400 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/22 | 2012/08/23 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1199774
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Edward Jones - SO1180791 08/20/12 Remote - Michael T | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/20 | 2012/08/20 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1180791
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Health Partners - SO1181623 08/21/12 - 08/24/12 Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/21 | 2012/08/24 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1181623
Unused Resource - SO99999 Michael Taylor | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 Michael Taylor | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Unused Resource - SO99999 08/27/12 Fred Jurs | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/27 | 2012/08/27 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 99999
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Planning & Design | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Product Installation | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Product Integration | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Training | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Support Turnover | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Ally Financial - SO65577 08/28/12 -08/30/12 Remote - Fred J | Project Closure | Project Closure |  | 2100 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/28 | 2012/08/30 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 65577
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Project Kick Off | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Planning & Design | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Readiness Validation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Product Installation | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Product Integration | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Training | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Support Turnover | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
Sitel Moneygram - SO 1197806 08/31/12 Remote - Fred J | Project Closure | Project Closure |  | 700 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/08/31 | 2012/08/31 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1197806
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
5 Networks - SO1195134 09/04/12 - 09/07/12 Remote - Fred J | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1195134
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Project Kick Off | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Planning & Design | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Hardware / Software Procurement | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Readiness Validation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Product Installation | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Product Integration | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Training | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Consulting & Technical Reviews | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Support Turnover | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Purolater Courier - SO1190084 09/04/12 - 09/07/12 Remote - Michael T | Project Closure | Project Closure |  | 2800 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/04 | 2012/09/07 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1190084
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
Teleflex - SO67766 09/10/12 - 09/14/12 - Fred J | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 67766
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
SCANA Energy- SO1175807 09/10/12 - 09/14/12 - Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/10 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1175807
Telus Communications - Prospera SO9205 WFM Move | Project Kick Off | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  | 2012/09/20 |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Planning & Design | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Hardware / Software Procurement | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Readiness Validation | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Product Installation | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Product Integration | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Training | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Consulting & Technical Reviews | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Support Turnover | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Telus Communications - Prospera SO9205 WFM Move | Project Closure | Project Closure |  | 6900 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/13 | 2012/09/28 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9205 | 385333
Siemens - Capital City Bank - SO9240 eQM License Update | Project Kick Off | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/10 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Planning & Design | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/11 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/17 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Readiness Validation | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/18 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Product Installation | Project Closure |  | 500 | 0 | Stewart Futcher | 100 | 500 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Product Integration | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/26 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Training | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/09/28 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Consulting & Technical Reviews | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/08 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Support Turnover | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/08 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Siemens - Capital City Bank - SO9240 eQM License Update | Project Closure | Project Closure |  | 500 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/19 | 2012/10/05 |  |  |  | 2012/10/03 | Kent Pylant | [7 empty] | True |  | 9240 | 7700234542
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Johnson & Johnson - SO1184566 09/17/12 - 09/20/12 Remote - Prisca White | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1184566
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Project Kick Off | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Planning & Design | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Hardware / Software Procurement | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Readiness Validation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Product Installation | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Product Integration | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Training | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Consulting & Technical Reviews | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Support Turnover | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Springs Window Fashions - SO1177224 09/17/12 - 09/21/12 Michael T | Project Closure | Project Closure |  | 3500 | 0 | Kent Pylant | 0 | 0 | 0 | 0 | 2012/09/17 | 2012/09/21 |  |  |  |  | Kent Pylant | [7 empty] | False | Tim Prince |  | 1177224
Affiliated Computer Services - SO8353 NGX Cards and Server |  | Project Closure |  | 4700 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/04/02 | 2012/09/28 |  |  | 2012/09/10 | 2012/09/25 | Kent Pylant | [7 empty] | True |  | 8353 | AC145180
Knology - SO9038 Trunk Tap Remote |  | Project Closure |  | 500 | 0 | Kent Pylant | 100 | 0 | 0 | 0 | 2012/08/15 | 2012/09/14 |  |  | 2012/09/21 | 2012/09/21 | Kent Pylant | [7 empty] | True |  | 9038 | 414-126621
Siemens - Dematic Corp. - SO9847 | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/02/08 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/03/07 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Siemens - Dematic Corp. - SO9847 | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/01/28 | 2013/01/30 |  |  |  | 2013/04/10 | Philip Haskings | [7 empty] | True |  | 9847 | 7700237684 |  | True
Nissan North America - SO9777 On Site Services | Project Kick Off | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Planning & Design | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Hardware / Software Procurement | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/02/12 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Readiness Validation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Product Installation | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Product Integration | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Training | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Consulting & Technical Reviews | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Support Turnover | Project Closure |  | 4700 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
Nissan North America - SO9777 On Site Services | Project Closure | Project Closure |  | 4700 | 0 | Philip Haskings | 100 | 4700 | 0 | 0 | 2013/01/28 | 2013/02/01 |  |  |  | 2013/03/28 | Philip Haskings | [7 empty] | True |  | 9777 | 9400059162
CDW - TMG - SO9856 - Additional Recorders | Project Kick Off | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 | 2012/10/22 | 2012/10/22 | 2012/10/26 | 2012/10/26 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Planning & Design | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 | 2012/10/22 | 2012/10/22 | 2012/10/26 | 2012/10/26 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Hardware / Software Procurement | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Readiness Validation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Product Installation | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Product Integration | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Training | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Consulting & Technical Reviews | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Support Turnover | Project Closure |  | 3200 | 0 | Stewart Futcher | 0 | 0 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  |  | Kent Pylant | [7 empty] | False |  | 9856 | 00003-0000014080
CDW - TMG - SO9856 - Additional Recorders | Project Closure | Project Closure |  | 3200 | 0 | Stewart Futcher | 100 | 3200 | 0 | 0 | 2012/09/03 | 2012/09/14 |  |  |  | 2013/02/14 | Kent Pylant | [7 empty] | True |  | 9856 | 00003-0000014080
APAC - SO9862 Tucson - Dialogic Install | Project Kick Off | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Planning & Design | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Hardware / Software Procurement | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/02/13 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Product Integration | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Support Turnover | Project Closure |  | 500 | 0 | Philip Haskings | 0 | 0 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367
APAC - SO9862 Tucson - Dialogic Install | Project Closure | Project Closure |  | 500 | 0 | Philip Haskings | 100 | 500 | 0 | 0 | 2013/01/31 | 2013/02/08 |  |  |  | 2013/03/01 | Philip Haskings | [7 empty] | True |  | 9862 | APAC-TUCW-68367